## Legend
LEGEND
| Lanes in existing or final condition | One lane maintained, one lane detoured
| Two lanes maintained | Two lanes detoured

## Phases
Alternative | MOT Phase Duration | [10 empty] | Alternative | Road User Costs
| 2027 Construction Year | [11 empty] | ($5,000 per day per direction)
| Jan | Feb | Mar | Apr | May | Jun |  | Jul | Aug | Sep | Nov |  | Phase 1 | Phase 2 | Phase 3 | Total
1A |  |  | Phase 1 |  |  | Phase 2 | [5 empty] | 1A | 460000 | 0 | 0 | 460000
1B |  |  | Phase 1 |  |  | Phase 2 | [5 empty] | 1B | 460000 | 460000 | 0 | 920000
2 |  |  | Phase 1 |  |  | Phase 2 |  |  |  | Phase 3 |  | 2 | 0 | 0 | 0 | 0
3 |  |  | Phase 1 | [8 empty] | 3 | 1220000 | 0 | 0 | 1220000
4A |  |  | Phase 1 |  |  |  | Phase2 |  |  |  |  | 4A | 535000 | 0 | 0 | 535000
4B |  |  | Phase 1 |  |  |  | Phase2 |  |  |  |  | 4B | 535000 | 540000 | 0 | 1075000
5 |  |  | Phase 1 |  |  |  | Phase 2 |  |  |  | Phase 3 | 5 | 0 | 0 | 0 | 0
6 |  |  | Phase 1 | [8 empty] | 6 | 1370000 | 0 | 0 | 1370000

## Sheet1
Alternative | 1A | 1B | 2 | 3 | 4A | 4B | 5 | 6
MOT Cost | 100000 | 100000 | 100000 | 50000 | 100000 | 100000 | 100000 | 50000
Road User Cost | 460000 | 920000 | 0 | 1220000 | 535000 | 1075000 | 0 | 1370000
Total Cost | 560000 | 1020000 | 100000 | 1270000 | 635000 | 1175000 | 100000 | 1420000