ALTERNATIVE 1A

PHASE 1 (SEE SHEET 2)

1. CLOSE AND DETOUR SOUTHBOUND W. 220TH ST. MAINTAIN ONE NORTHBOUND LANE ON THE WEST SIDE OF THE BRIDGE.

2. PERFORM DECK REPLACEMENT ACTIVITIES ON THE WEST SIDE OF THE BRIDGE, INCLUDING SIDEWALK WIDENING, APPROACH SLABS, AND ROADWAY APPROACH WORK.

PHASE 2 (SEE SHEET 2)

1. SWITCH THE NORTHBOUND LANE OF W. 220TH ST. TO THE COMPLETED PORTION OF THE EAST SIDE OF THE BRIDGE. ALSO, PROVIDE A SINGLE SOUTHBOUND LANE ON THE COMPLETED PORTION OF THE BRIDGE.

2. PERFORM DECK REPLACEMENT ACTIVITIES ON THE WEST SIDE OF THE BRIDGE, INCLUDING SIDEWALK WIDENING, APPROACH SLABS, AND ROADWAY APPROACH WORK.

PHASE 3 (NO SECTION PROVIDED)

3. REMOVE ALL MOT DEVICES, PLACE FINAL SURFACE COURSES AND PAVEMENT MARKINGS USING SINGLE LANE CLOSURES. PLACE LANES INTO THEIR FINAL CONFIGURATION.

ALTERNATIVE 1B

PHASE 1 (SEE SHEET 2)

1. ALTERNATE 1B WILL HAVE THE SAME SEQUENCE OF CONSTRUCTION AS PHASE 1A.

PHASE 2 (NO SECTION PROVIDED)

1. ALTERNATE 1B WILL HAVE THE SAME SEQUENCE OF CONSTRUCTION AS ALTERNATE 1A EXCEPT THAT A SINGLE NORTHBOUND 12-FOOT LANE WITH 2-FOOT OFFSETS WILL BE MAINTAINED. SOUTHBOUND WILL CONTINUE TO BE DETOURED. THIS ALTERNATIVE ELIMINATES THE NEED TO ANCHOR BARRIER INTO THE NEW DECK.

PHASE 3 (NO SECTION PROVIDED)

3. ALTERNATE 1B WILL HAVE THE SAME SEQUENCE OF CONSTRUCTION AS PHASE 1A

ALTERNATIVE 2

PHASE 1 (SEE SHEET 3)

1. SHIFT NORTHBOUND AND SOUTHBOUND W. 220TH ST. TO THE WEST SIDE OF THE BRIDGE.

2. PERFORM DECK REPLACEMENT ACTIVITIES ON THE WEST SIDE OF THE BRIDGE, INCLUDING APPROACH SLABS, AND ROADWAY APPROACH WORK. ONLY PARTIAL CONSTRUCTION OF THE EAST SIDEWALK WILL OCCUR IN THIS PHASE.

PHASE 2 (SEE SHEET 3)

1. SHIFT NORTHBOUND AND SOUTHBOUND W. 220TH ST. TO THE COMPLETED PORTION OF THE EAST SIDE OF THE BRIDGE.

2. PERFORM DECK REPLACEMENT ACTIVITIES ON THE WEST SIDE OF THE BRIDGE, INCLUDING SIDEWALK WIDENING, APPROACH SLABS, AND ROADWAY APPROACH WORK.

PHASE 3 (SEE SHEET 4)

1. REMOVE ALL MOT DEVICES, PLACE FINAL SURFACE COURSES AND PAVEMENT MARKINGS USING SINGLE LANE CLOSURES. PLACE LANES INTO THEIR FINAL CONFIGURATION.

2. USING DRUMS, CLOSE THE NORTHBOUND SHOULDER ON THE BRIDGE AND COMPLETE SIDEWALK WIDENING ON THE EAST SIDE OF THE BRIDGE.