## SUMMARY
PID No. 1814168 |  | h | [7 empty] | BRIDGE NO. CUY-00480-06.120 WEST 220TH OVER CUY-480 |  |  |  |  | ms consultants, inc.
STRUCTURE QUANTITIES
ESTIMATED QUANTITIES | [15 empty] | LUMP SUM
ITEM | ITEM EXT. | PARTICIPATION |  |  | PARTICIPATION |  |  | TOTAL | UNIT | DESCRIPTION | ABUTMENTS | PIERS | SUPERSTRUCTURE | GENERAL | SHEET REF.
|  | 01/BRO/BR | 02/BRO/BR | 03/BRO/BR | 01/BRO | 02/IMS | 03/IMS | [8 empty] | EST. COST
202 | 11203 |  |  |  | LS |  |  | LS |  | PORTIONS OF STRUCTURE REMOVED, OVER 20 FOOT SPAN, AS PER PLAN |  |  |  | LS |  | 417300 | 202E11203
202 | 22900 |  |  |  | 268 |  |  | 268 | SY | APPROACH SLAB REMOVED |  |  |  | 268 |  |  | 202E22900
202 | 75264 |  |  |  | 574 |  |  | 574 | FT | VANDAL PROTECTION FENCE REMOVED FOR STORAGE |  |  |  | 574 |  |  | 202E75264
503 | 11101 |  |  |  | LS |  |  | LS |  | COFFERDAMS AND EXCAVATION BRACING, AS PER PLAN |  |  |  | LS |  | 25000 | 503E11101
509 | 10000 |  |  |  | 175393 |  |  | 175393 | LB | EPOXY COATED STEEL REINFORCEMENT | 3967 | 2181 | 169245 |  |  |  | 509E10000
E
510 | 10001 |  |  |  | 549 |  |  | 549 | EACH | DOWEL HOLES WITH NONSHRINK, NONMETALLIC GROUT, AS PER PLAN | 321 | 228
511 | 33500 |  |  |  | 4 |  |  | 4 | EACH | SEMI-INTEGRAL DIAPHRAGM GUIDE | 4 | [5 empty] | 511E33500
511 | 34447 |  |  |  | 561.9367 |  |  | 561.9367 | CY | CLASS QC2 CONCRETE WITH QC/QA, BRIDGE DECK, AS PER PLAN |  |  | 561.9367 |  |  |  | 511E34447
511 | 34450 |  |  |  | 85 |  |  | 85 | CY | CLASS QC2 CONCRETE WITH QC/QA, BRIDGE DECK (PARAPET) |  |  | 85 |  |  |  | 511E34450
511 | 42510 |  |  |  | 22 |  |  | 22 | CY | CLASS QC1 CONCRETE, PIER CAP |  | 22 |  |  |  |  | 511E42510
511 | 45710 |  |  |  | 29.7178 |  |  | 29.7178 | CY | CLASS QC1 CONCRETE, ABUTMENT | 29.7178 | [5 empty] | 511E45710
511 | 51512 |  |  |  | 140 |  |  | 140 | CY | CLASS QC2 CONCRETE WITH QC/QA, SIDEWALK |  |  | 140 |  |  |  | 511E51512
511 | 53012 | [5 empty] | 4 | 4 | CY | CLASS QC2 CONCRETE, MISC.: SLEEPER SLAB SUPPORT CONCRETE |  |  |  | 4
511 | 81200 |  |  |  |  | LS |  | LS |  | CONCRETE, MISC.: PARAPET LETTERING |  |  | LS
512 | 10050 |  |  |  | 492.052 |  |  | 492.052 | SY | SEALING OF CONCRETE SURFACES (NON-EPOXY) |  |  | 492.052
512 | 10100 |  |  |  | 1270.9227 |  |  | 1270.9227 | SY | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE) | 84.9861 | 545.5658 | 640.3708
512 | 33000 |  |  |  | 9.8333 |  |  | 9.8333 | SY | TYPE 2 WATERPROOFING | 9.8333
513 | 20000 |  |  |  | 6618 |  |  | 6618 | EACH | WELDED STUD SHEAR CONNECTORS |  |  | 6618 |  |  |  | 513E20000
513 | 90000 |  |  |  | 4144.365 |  | 2961.3 | 7105.665 | LB | STRUCTURAL STEEL, MISC.: ANGLES, CHANNELS, & PLATES |  |  | 7105.665 |  |  |  | 513E90000
514 | 27700 |  |  |  | 428.5924 |  |  | 428.5924 | SF | FIELD PAINTING, MISC.: COATING OF BEAM ENDS |  |  | 428.5924
516 | 10011 |  |  |  | 138.5 |  |  | 138.5 | FT | ARMORLESS PREFORMED JOINT SEAL, AS PER PLAN |  |  |  | 138.5
516 | 12310 |  |  |  | 288 |  |  | 288 | LB | SIDEWALK COVER PLATE |  |  | 288
516 | 13600 |  |  |  | 36.3135 |  |  | 36.3135 | SF | 1" PREFORMED EXPANSION JOINT FILLER |  |  | 36.3135 |  |  |  | 516E13600
516 | 13900 |  |  |  | 15 |  |  | 15 | SF | 2" PREFORMED EXPANSION JOINT FILLER | 15
516 | 14020 |  |  |  | 146.4397 |  |  | 146.4397 | FT | SEMI-INTEGRAL ABUTMENT EXPANSION JOINT SEAL | 146.4397
516 | 14600 |  |  |  | 12 |  |  | 12 | FT | STRUCTURAL JOINT OR JOINT SEALER, MISC.: COMPRESSED FOAM EXPANSION JOINT SEAL | 12
516 | 44100 |  |  |  | 16 |  |  | 16 | EACH | ELASTOMERIC BEARING (14" X 18" X 2.668") WITH INTERNAL LAMINATES AND LOAD PLATE (NEOPRENE) (15" X 19" X 2.0") |  | 16
516 | 44100 |  |  |  | 8 |  |  | 8 | EACH | ELASTOMERIC BEARING (16" X 18" X 2.668") WITH INTERNAL LAMINATES AND LOAD PLATE (NEOPRENE) (17" X 19" X 2.0") |  | 8
516 | 44200 |  |  |  | 17 |  |  | 17 | EACH | ELASTOMERIC BEARING (12" X 16" X 3.273") WITH INTERNAL LAMINATES AND LOAD PLATE (NEOPRENE) (13" X 17" X 1.5") | 17 | [5 empty] | 516E44200
516 | 47001 |  |  |  | LS |  |  | LS |  | JACKING AND TEMPORARY SUPPORT OF SUPERSTRUCTURE, AS PER PLAN |  |  |  | LS |  | 61500 | 516E47001
518 | 12201 |  |  |  | 7 |  |  | 7 | EACH | SCUPPERS, INCLUDING SUPPORTS, AS PER PLAN |  |  | 7
518 | 21200 |  |  |  | 77 |  |  | 77 | CY | POROUS BACKFILL WITH GEOTEXTILE FABRIC | 77 | [5 empty] | 518E21200
518 | 40000 |  |  |  | 131 |  |  | 131 | FT | 6" PERFORATED CORRUGATED PLASTIC PIPE | 131
518 | 40011 |  |  |  | 80 |  |  | 80 | FT | 6" NON-PERFORATED CORRUGATED PLASTIC PIPE, INCLUDING SPECIALS, AS PER PLAN | 80
519 | 11101 |  |  |  | 100 |  |  | 100 | SF | PATCHING CONCRETE STRUCTURE, AS PER PLAN | 50 | 50
526 | 15011 |  |  |  | 308 |  |  | 308 | SY | REINFORCED CONCRETE APPROACH SLABS WITH QC/QA (T=13"), AS PER PLAN |  |  |  | 308 |  |  | 526E15011
526 | 90030 |  |  |  | 139 |  |  | 139 | FT | TYPE C INSTALLATION |  |  |  | 139 |  |  | 526E90030
SPECIAL | 53000400 |  |  |  | 240 |  |  | 240 | EACH | STRUCTURES: GROUT AND SEAL TEMPORARY VANDAL PROTECTION FENCE ANCHOR HOLES |  |  | 240
SPECIAL | 53000600 | [5 empty] | 842 | 842 | SF | STRUCTURES: TEMPORARY FALSE DECKING FOR ENBRIDGE GAS LINES |  |  | 842
SPECIAL | 53013000 |  |  |  | 1224 |  |  | 1224 | SF | FORM LINER |  |  |  | 1224 |  |  | SPECIALE53013000
607 | 39901 |  |  |  | 582 |  |  | 582 | FT | VANDAL PROTECTION FENCE, 6' STRAIGHT, COATED FABRIC, AS PER PLAN |  |  | 582 |  |  |  | 607E39901
SPECIAL | 69098400 | [5 empty] | LS | LS |  | ENBRIDGE GAS LINE ROLLER GUIDE/SUPPORT |  |  | LS
E

## STR REMOVED
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 202E11203
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 1
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | PORTIONS OF STRUCTURE REMOVED, OVER 20 FOOT SPAN, AS PER PLAN | [6 empty] | PAY UNIT | LS
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
| LUMP SUM ITEM | [8 empty] | ESTIMATE LUMP SUM COST:
[11 empty] | AREA = | 16689 | SF | measured in ORD
[11 empty] | COST/SF = | 25
[11 empty] | TOTAL COST = | 417300
TOTAL | [7 empty] | 0 | LS

## APPR SLAB REMOVED
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 202E22900
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 2
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | APPROACH SLAB REMOVED | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
| Location |  | Length | Width | Area (SF) | Area (SY)
| Rear Abutment |  |  |  | 1353.6794 | 150
(Area by CADD)
| Fwd Abutment |  | 20 | 53 | 1060 | 118
[5 empty] | Total | 268 |  |  | 268
TOTAL | [8 empty] | 268 | 268

## VPL REMOVED
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 202E75264
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 3
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | VANDAL PROTECTION FENCE REMOVED FOR STORAGE | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
| Location |  | Length
| Left Parapet |  | 289.4
| Right Parapet |  | 284.6
|  | Total | 574 | [5 empty] | 574
TOTAL | [8 empty] | 574 | 574

## EXC. BRACING
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 503E11101
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 4
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | COFFERDAMS AND EXCAVATION BRACING, AS PER PLAN | [6 empty] | PAY UNIT | LS
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
LUMP SUM ITEM
-Required at approach slabs for part-width construction.
TOTAL | [7 empty] | 0 | LS

## REBAR
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 509E10000
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 5
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | EPOXY COATED STEEL REINFORCEMENT | [6 empty] | PAY UNIT | LB
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
From Reinforcing Schedules
LB
[5 empty] | Abutments | 3967
[5 empty] | Pier Cap | 2181
[5 empty] | Superstructure | 157649 | (Included Diaphragm)
[5 empty] | Railings | 11596
[5 empty] | TOTAL | 175393 |  |  | 175393
TOTAL | [8 empty] | 175393 | 175393

## DOWEL
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 510E10001
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 6
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | DOWEL HOLES WITH NONSHRINK, NONMETALLIC GROUT, AS PER PLAN | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| No. of dowels (each) |  |  |  | Total No. of Dowels
| 146 |  |  |  | 146 |  |  |  | 146
Piers
| No. of dowels per pier (each) |  | No. of piers (each) |  | Total No. of Dowels
| 76 |  | 3 |  | 228 |  |  |  | 228
Forward Abutment
| No. of dowels (each) |  |  |  | Total No. of Dowels
| 130 |  |  |  | 130 |  |  |  | 130
Rear Abutment SE Wingwall
| No. of dowels (each) |  |  |  | Total No. of Dowels
| 45 |  |  |  | 45 |  |  |  | 45
TOTAL | [8 empty] | 549 | 549

## DIAPHRAGM GUIDE
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E33500
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 7
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | SEMI-INTEGRAL DIAPHRAGM GUIDE | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
Rear Abutment
Number
| 2 | [6 empty] | 2
Piers
Number
| 0 | [6 empty] | 0
Forward Abutment
Number
| 2 | [6 empty] | 2
TOTAL | [7 empty] | 4 | 4

## DECK CONC.
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E34447
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 8
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | CLASS QC2 CONCRETE WITH QC/QA, BRIDGE DECK, AS PER PLAN | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Deck
| Area F/F abut. (ft^2) |  | Thickness (ft) | Volume (ft^3) | Volume (CY)
| 16839 |  | 0.70833 | 11927.625 | 442 |  |  |  | 442
Typical Haunch
| Girder # | Flange Width (in) | Fillet Width (in) | Avg. Height (in) | Area (sq in) | Length (ft) | Volume (ft^3) | Volume (CY)
| 1 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
| 2 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
| 3 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
| 4 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
| 5 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
| 6 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
| 7 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
| 8 | 12.115 | 0 | 2.3674 | 28.6807 | 252 | 50.1912 | 2
[6 empty] | Total = | 401.53 | 16 | 16
Additional Haunch Overhang
| Girder # | Width (in) | Height (in) | Area (ft^2) | Length (ft) | Volume (ft^3) | Volume (CY)
| 1 | 35.6925 | 3.6274 | 0.8991 | 252 | 226.5725 | 9
| 8 | 31.6925 | 3.6274 | 0.79834 | 237 | 189.2058 | 8
| 9 |  | 3.1475 | 43.866 |  | 11.5057 | 1
| Lt. Pilaster |  | 14.6 | 5.106 |  | 6.2123 | 0.23009
| Lt. Pilaster |  | 14.6 | 5.106 |  | 6.2123 | 0.23009
| Rt. Pilaster |  | 14.6 | 5.106 |  | 6.2123 | 0.23009
| Rt. Pilaster |  | 14.6 | 5.106 |  | 6.2123 | 0.23009
[5 empty] | Total = | 452.1331 | 18.9203 |  | 18.9203
Semi-Integral Abutment Diaphragm
| Abut. | Width (ft) | Height (ft) | Deduct Appr Slab Seat (ft^2) | Area (ft^2) | Length (ft) | Volume (ft^3) | Volume (CY)
| Rear | 3.75 | 4.6183 | 0.54167 | 16.7771 | 73 | 1224.7271 | 45.3603
| Forward | 3.75 | 4.6183 | 0.54167 | 16.7771 | 63.82 | 1070.7135 | 39.6561
[6 empty] | Total = | 2295.4405 | 85.0163 | 85.0163
TOTAL | [8 empty] | 561.9367 | 561.9367

## PARAPET
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E34450
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 9
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | CLASS QC2 CONCRETE WITH QC/QA, BRIDGE DECK (PARAPET) | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Railing
|  | Width (ft) | Height (ft) | Length (ft) | Volume (ft^3) | Volume (CY)
| left | 1.3333 | 3 | 298.51 | 1194.04 | 44.2237
| right | 1.1667 | 3 | 253.8 | 888.3 | 32.9
| right radius | 1.1667 | 3 | 34.79 | 121.765 | 4.5098
[5 empty] | Total | 82 |  |  | 82
Light Pole Pilasters
|  | Area (SF) | Height (ft) | Volume (ft^3) | Volume (CY)
| 1 | 4.6181 | 3 | 13.8542 | 0.51312
| 2 | 4.6181 | 3 | 13.8542 | 0.51312
| 3 | 4.6181 | 3 | 13.8542 | 0.51312
| 4 | 4.6181 | 3 | 13.8542 | 0.51312
|  |  |  | Total | 3 |  |  |  | 3
TOTAL | [8 empty] | 85 | 85

## PIER CAP
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E42510
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 10
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | CLASS QC1 CONCRETE, PIER CAP | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Pier Cap |  | Adding cap depth to raise profile
| Pier | Length | Width | Height | Vol (CF) | Vol (CY)
| 1 | 56 | 3 | 0.89 | 149.52 | 5.5378
| 2 | 56 | 3 | 1.27 | 213.36 | 7.9022
| 3 | 56 | 3 | 1.35 | 226.8 | 8.4
[5 empty] | Total | 22 |  |  | 22
TOTAL | [8 empty] | 22 | 22

## ABUTM.
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E45710
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 11
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | CLASS QC1 CONCRETE, ABUTMENT | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
| Abutment | Height | Width | Length | Vol (CF) | Vol (CY)
| Rear | 1 | 73 | 3.75 | 273.75 | 10.1389
| Fwd | 1.5 | 63.8 | 3.75 | 358.875 | 13.2917
|  |  |  | Total | 632.625 | 23.4306 |  |  | 23.4306
Semi-Integral Blockouts
|  | Height | Width | Length | Quantity (each) | Vol (CF) | Vol (CY)
| Rear | 1.25 | 3 | 3.75 | 2 | 28.125 | 1.0417
| Fwd | 0.75 | 3 | 3.75 | 2 | 16.875 | 0.625
[5 empty] | Total | 45 | 1.6667 |  | 1.6667
| Wingwall |  | Plan Area | Height | Vol (CF) | Vol (CY)
| RA Rt wall area |  | 18.67 | 5 | 93.35 | 3.4574
| RA Rt slab area |  | 32.144 | 0.977 | 31.4047 | 1.1631
|  |  |  | Total | 124.7547 | 4.6205 |  |  | 4.6205
TOTAL | [8 empty] | 29.7178 | 29.7178

## SIDEWALK CONC.
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E51512
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 12
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | CLASS QC2 CONCRETE WITH QC/QA, SIDEWALK | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Sidewalk
| Side | Length (ft) | Width (ft) | Area (sq. ft.) | Ave. Thick. (ft) | Volume (ft^3) | Volume (CY)
| Left | 298.51 | 7.33 | 2188.0783 | 0.77918 | 1704.8976 | 64
| Right | 280.09 | 9 | 2520.81 | 0.80589 | 2031.4881 | 76
[5 empty] | Total = | 3736.3857 | 140 |  | 140
length includes sidewalk on approach slabs
TOTAL | [8 empty] | 140 | 140

## SLEEPER SLAB SUPPORT CONC.
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E53012
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 13
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | CLASS QC2 CONCRETE, MISC.: SLEEPER SLAB SUPPORT CONCRETE | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Approach Slab
| Length (ft.) | Width (ft.) | Depth ft.) | Quantity (each) | Total (CF) | Total (CY)
| 6 | 1.3333 | 1.3333 | 4 | 42.6667 | 1.5802 |  |  | 1.5802
Forward Approach Slab
| Length (ft.) | Width (ft.) | Depth ft.) | Quantity (each) | Total (CF) | Total (CY)
| 6 | 1.3333 | 1.3333 | 4 | 42.6667 | 1.5802 |  |  | 1.5802
TOTAL | [8 empty] | 4 | 4

## PARAPET LETTERING
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 511E81200
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 14
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | CONCRETE, MISC.: PARAPET LETTERING | [6 empty] | PAY UNIT | LS
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
LUMP SUM ITEM
TOTAL | [7 empty] | 0 | LS

## NON EPOXY SEALER
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 512E10050
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 15
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SEALING OF CONCRETE SURFACES (NON-EPOXY) | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Superstructure
Left Sidewalk
|  | Location |  | Perim. (ft) | Length (ft) (along edge of deck) | Area (ft^2) | Area (yd^2)
|  |  | Sidewalk | 6.6667 | 298.511 | 1990.0733 | 221.1193 |  | 221.1193
Right Sidewalk
|  | Location |  | Perim. (ft) | Length (ft) (along edge of deck) | Area (ft^2) | Area (yd^2)
|  |  | Sidewalk | 8.5 | 286.87 | 2438.395 | 270.9328 |  | 270.9328
[8 empty] | Total Superstructure Sealing = | 492.052
TOTAL | [8 empty] | 492.052 | 492.052

## EPOXY SEALING
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 512E10100
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 16
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE) | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Piers
Pier 1 Cap Areas (areas from ORD measure tool)
| Front (ft^2) | Back (ft^2) | Left End (ft^2) | Right End (ft^2) | Underside (ft^2) | Pier 1 Total (SF) | Pier 1 Total (SY)
| 255.787 | 255.787 | 23.76 | 23.7 | 131.5885 | 690.6225 | 125.0509 |  | 125.0509
Pier 1 Columns
| Avg. Height (ft) | Perimeter (ft) | No. of Columns | Area (ft^2) | Area (SY)
| 16.248 | 9.4248 | 4 | 612.5352 | 68.0595 |  |  |  | 68.0595
Pier 2 Cap Areas (areas from ORD measure tool)
| Front (ft^2) | Back (ft^2) | Left End (ft^2) | Right End (ft^2) | Underside (ft^2) | Pier 2 Total (SF) | Pier 2 Total (SY)
| 277.347 | 277.347 | 20.07 | 20.01 | 131.5885 | 726.3625 | 130.5976 |  | 130.5976
Pier 2 Columns
| Height (ft) | Perimeter (ft) | No. of Columns | Area (ft^2) | Area (SY)
| 8.946 | 9.4248 | 4 | 337.2563 | 37.4729 |  |  |  | 37.4729
Pier 3 Cap Areas (areas from ORD measure tool)
| Front (ft^2) | Back (ft^2) | Left End (ft^2) | Right End (ft^2) | Underside (ft^2) | Pier 3 Total (SF) | Pier 3 Total (SY)
| 281.63 | 281.63 | 17.28 | 17.22 | 131.5885 | 729.3485 | 130.7852 |  | 130.7852
Pier 3 Columns
| Avg. Height (ft) | Perimeter (ft) | No. of Columns | Area (ft^2) | Area (SY)
| 12.796 | 9.4248 | 4 | 482.3978 | 53.5998 |  |  |  | 53.5998
[8 empty] | Total Pier Sealing = | 545.5658
TOTAL
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 512E10100
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 17
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE) | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
Front Face Area
| Area (by CADD)(sq. ft.) |  |  | Area (SY)
| 332.453 |  |  | 36.9392 |  |  |  |  | 36.9392
SW Wingwall area
| Area (by CADD)(sq. ft.) |  |  | Area (SY)
| 16.463 |  |  | 1.8292 |  |  |  |  | 1.8292
SE Wingwall Area
| Area (by CADD)(sq. ft.) |  |  | Area (SY)
| 47.764 |  |  | 5.3071 |  |  |  |  | 5.3071
Forward Abutment
Front Face Area
| Area (by CADD)(sq. ft.) |  |  | Area (SY)
| 325.945 |  |  | 36.2161 |  |  |  |  | 36.2161
NW Wingwall area
| Area (by CADD)(sq. ft.) |  |  | Area (SY)
| 21.265 |  |  | 2.3628 |  |  |  |  | 2.3628
NE Wingwall Area
| Area (by CADD)(sq. ft.) |  |  | Area (SY)
| 20.985 |  |  | 2.3317 |  |  |  |  | 2.3317
[8 empty] | Total Abutment Sealing = | 84.9861
TOTAL
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 512E10100
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 18
PID NO. |  | 105792 |  | PROJECT | CUY-090-13.45 |  | STRUCTURE | CUY-090-1345
ITEM NAME |  | SEALING OF CONCRETE SURFACES (EPOXY-URETHANE) | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Superstructure
Left Edge of Deck
|  | Location |  | Perim. (ft) | Length (ft) (along edge of deck) | Area (ft^2) | Area (yd^2)
|  |  | Edge of Deck and Parapet Perimeter | 9.8161 | 298.511 | 2930.2261 | 325.5807 |  | 325.5807
Right Edge of Deck
|  | Location |  | Perim. (ft) | Length (ft) (along edge of deck) | Area (ft^2) | Area (yd^2)
|  |  | Edge of Deck and Parapet Perimeter | 9.8759 | 286.87 | 2833.1112 | 314.7901 |  | 314.7901
[8 empty] | Total Superstructure Sealing = | 640.3708
TOTAL | [8 empty] | 1270.9227 | 1270.9227

## WATERPROOFING
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 512E33000
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 19
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | TYPE 2 WATERPROOFING | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Waterproofing at Abutment
| Location | Height (ft) | Width (ft) | Area (ft^2) | Area (yd^2)
| R.A. Left Corner | 5.5 | 3 | 16.5 | 1.8333 |  |  |  | 1.8333
| F.A. Left Corner | 6 | 3 | 18 | 2 |  |  |  | 2
| F.A. Right Corner | 6 | 3 | 18 | 2 |  |  |  | 2
| R.A. Phase C.J. | 6 | 3 | 18 | 2 |  |  |  | 2
| F.A. Phase C.J. | 6 | 3 | 18 | 2 |  |  |  | 2
NOTE: 3'-0" strip of waterproofing applied in wingwall outside corner from top of wingwall to 1'-6" below adjacent existing beam seat
TOTAL | [8 empty] | 9.8333 | 9.8333

## SHEAR STUDS
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 513E20000
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 20
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | WELDED STUD SHEAR CONNECTORS | [6 empty] | PAY UNIT | EACH
[9 empty] | SUB TOTAL | TOTAL
5" X 7/8" dia studs on Girders, 3 per row:
|  | Spaces | Number
| Beam 1 | 273 | 822
| Beam 2 | 273 | 822
| Beam 3 | 273 | 822
| Beam 4 | 273 | 822
| Beam 5 | 273 | 822
| Beam 6 | 273 | 822
| Beam 7 | 273 | 822
| Beam 8 | 273 | 822
| Beam 9 | 13 | 42
| Total |  | 6618 | [5 empty] | 6618
TOTAL | [8 empty] | 6618 | 6618

## STEEL MEMBERS MISC
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 513E90000
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 21
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | STRUCTURAL STEEL, MISC.: ANGLES, CHANNELS, & PLATES | [6 empty] | PAY UNIT | LB
[9 empty] | SUB TOTAL | TOTAL
Center bay of cross frames getting replaced
Replacement Crossframe Members
3x3x5/16 ANGLE
|  | Length | Weight |  |  |  | Locations | Weight
|  | (ft) | (lb) |  |  |  | (each) | (lbs)
| DIAGONAL | 8.6343 | 6.1 |  |  |  | 21 | 1106.0497
| DIAGONAL | 8.6343 | 6.1 |  |  |  | 21 | 1106.0497
| BOTTOM | 8.2258 | 6.1 |  |  |  | 21 | 1053.7292
Additional Bottom Angles in Bay 2
3x3x5/16 ANGLE
|  | Length | Weight |  |  |  | Locations | Weight
|  | (ft) | (lb) |  |  |  | (each) | (lbs)
| BOTTOM | 8.2258 | 6.1 |  |  |  | 10 | 501.7758
[6 empty] | Total Weight per frame | 3767.6046 | lb
[6 empty] | Number of bays | 1
[6 empty] | Total Replacement Crossframes Weigtht = | 3767.6046 |  | 3767.6046
Supports of Enbridge Gas Utility lines
ASSUME MC6x18
|  | Length | Weight |  |  |  | Locations | Weight
|  | (ft) | (lb) |  |  |  | (each) | (lbs)
| SUPPORT | 8.2258 | 18 |  |  |  | 20 | 2961.3 | 2961.3
[7 empty] | 10% CONTINGENCY | 376.7605 | 376.7605
TOTAL | [8 empty] | 4144.365 | 4144.365

## BEAM END COATING
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 514E27700
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 22
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | FIELD PAINTING, MISC.: COATING OF BEAM ENDS | [6 empty] | PAY UNIT | SF
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| Beam no. | Length (ft) | Perimeter (ft) | Area (ft^2)
| 1 | 2.5024 | 10 | 25.0239
| 2 | 2.5024 | 10 | 25.0239
| 3 | 2.5024 | 10 | 25.0239
| 4 | 2.5024 | 10 | 25.0239
| 5 | 2.5024 | 10 | 25.0239
| 6 | 2.5024 | 10 | 25.0239
| 7 | 2.5024 | 10 | 25.0239
| 8 | 2.5024 | 10 | 25.0239
| 9 | 2.821 | 10 | 28.21
|  |  | Total = | 228.4012 |  |  |  |  | 228.4012
Forward Abutment
| Beam no. | Length (ft) | Perimeter (ft) | Area (ft^2)
| 1 | 2.5024 | 10 | 25.0239
| 2 | 2.5024 | 10 | 25.0239
| 3 | 2.5024 | 10 | 25.0239
| 4 | 2.5024 | 10 | 25.0239
| 5 | 2.5024 | 10 | 25.0239
| 6 | 2.5024 | 10 | 25.0239
| 7 | 2.5024 | 10 | 25.0239
| 8 | 2.5024 | 10 | 25.0239
|  |  | Total = | 200.1912 |  |  |  |  | 200.1912
TOTAL | [8 empty] | 428.5924 | 428.5924

## ARMOR
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E10011
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 26
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | ARMORLESS PREFORMED JOINT SEAL, AS PER PLAN | [6 empty] | PAY UNIT | FT
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
|  | Location |  | Length
|  | Rear |  | 73.7
|  | Forward |  | 64.8
|  |  | Total | 138.5 |  |  |  | 138.5
TOTAL | [7 empty] | 138.5 | 138.5

## SIDEWALK COVER PLATE
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E12310
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 23
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SIDEWALK COVER PLATE | [6 empty] | PAY UNIT | LB
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Forward Abutment
| Location | Length | Width | Thickness | Vol (CF) | Weight (lb/ft^3) | Total Weight (lb)
| Lt. Sidewalk | 5.3333 | 1.5036 | 0.03125 | 0.2506 | 490 | 122.7928
| Rt. Sidewalk | 7.1667 | 1.5036 | 0.03125 | 0.33674 | 490 | 165.0028
[6 empty] | Total | 288 |  | 288
TOTAL | [8 empty] | 288 | 288

## 1" PEJF
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E13600
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 24
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | 1" PREFORMED EXPANSION JOINT FILLER | [6 empty] | PAY UNIT | SF
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| End of Parapet at Approach Slab |  |  |  | Width = |  | 1.3333 | ft.
| (Left Side) |  |  |  | Height = |  | 3 | ft.
[5 empty] | Total = |  | 4 | SF | 4
| End of Sidewalk at Approach Slab |  |  |  | Width = |  | 7.35 | ft.
| (Left Side) |  |  |  | Average Height = |  | 0.77067 | ft.
[5 empty] | Total = |  | 5.6644 | SF | 5.6644
| End of Sidewalk at Approach Slab |  |  |  | Width = |  | 5.5 | ft.
| (Right Side) |  |  |  | Height = |  | 1 | ft.
[5 empty] | Total = |  | 5.5 | SF | 5.5
Forward Abutment
| End of Parapet at Approach Slab |  |  |  | Width = |  | 1.1667 | ft.
| (Left and Right) |  |  |  | Height = |  | 3 | ft.
[5 empty] | Total = |  | 7 | SF | 7
| End of Sidewalk at Approach Slab |  |  |  | Width = |  | 9.02 | ft.
| (Left and Right) |  |  |  | Average Height = |  | 0.78432 | ft.
[5 empty] | Total = |  | 14.1491 | SF | 14.1491
TOTAL | [8 empty] | 36.3135 | 36.3135

## 2" PEJF
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E13900
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 25
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | 2" PREFORMED EXPANSION JOINT FILLER | [6 empty] | PAY UNIT | SF
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| End of Diaphragm |  |  |  | Width = |  | 3.75 | ft.
| (Right Side) |  |  |  | Height = |  | 4 | ft.
[5 empty] | Total = |  | 15 | SF | 15
TOTAL | [8 empty] | 15 | 15

## S.I. ABUT. EXP. JT. SEAL
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E14020
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 26
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | SEMI-INTEGRAL ABUTMENT EXPANSION JOINT SEAL | [6 empty] | PAY UNIT | FT
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
|  | Location |  | Length
|  | Rear Abutment |  | 78.6033
|  | Forward Abutment |  | 67.8363
|  |  | Total | 146.4397 |  |  |  | 146.4397
TOTAL | [7 empty] | 146.4397 | 146.4397

## COMPRESSED FOAM EXP. JOINT SEAL
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E14600
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 27
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | STRUCTURAL JOINT OR JOINT SEALER, MISC.: COMPRESSED FOAM EXPANSION JOINT SEAL | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
SE Wingwall
|  |  | Height = | 4 | FT.
|  |  | Total = | 4 | FT. |  |  |  | 4
Forward Abutment
NW Wingwall
|  |  | Height = | 4 | FT.
NE Wingwall
|  |  | Height = | 4 | FT.
|  |  | Total = | 8 | FT. |  |  |  | 8
TOTAL | [8 empty] | 12 | 12

## ELASTOMERIC BRG. (1)
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E44100
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 28
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | ELASTOMERIC BEARING (14" X 18" X 2.668") WITH INTERNAL LAMINATES AND LOAD PLATE (NEOPRENE) (15" X 19" X 2.0") | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Pier 1 & 3
| No. of Beams | Bearings per Beam | No. of Piers | Total
| 8 | 1 | 2 | 16 |  |  |  |  | 16
TOTAL | [8 empty] | 16 | 16

## ELASTOMERIC BRG. (2)
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E44100
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 29
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | ELASTOMERIC BEARING (16" X 18" X 2.668") WITH INTERNAL LAMINATES AND LOAD PLATE (NEOPRENE) (17" X 19" X 2.0") | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Pier 2
| No. of Beams | Bearings per Beam | No. of Piers | Total
| 8 | 1 | 1 | 8 |  |  |  |  | 8
TOTAL | [8 empty] | 8 | 8

## ELASTOMERIC BRG. (3)
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E44200
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 30
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | ELASTOMERIC BEARING (12" X 16" X 3.273") WITH INTERNAL LAMINATES AND LOAD PLATE (NEOPRENE) (13" X 17" X 1.5") | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| No. of Beams | Bearings per Beam | Total
| 9 | 1 | 9 | [5 empty] | 9
Forward Abutment
| No. of Beams | Bearings per Beam | Total
| 8 | 1 | 8 | [5 empty] | 8
TOTAL | [8 empty] | 17 | 17

## JACKING
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 516E47001
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 31
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | JACKING AND TEMPORARY SUPPORT OF SUPERSTRUCTURE, AS PER PLAN | [6 empty] | PAY UNIT | LS
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
LUMP SUM ITEM
41 BEARINGS TO RAISE AT $1500 PER BEARING
61500
TOTAL | [7 empty] | 0 | LS

## SCUP
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 518E12201
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 32
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SCUPPERS, INCLUDING SUPPORTS, AS PER PLAN | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Deck -Left Side only
| Span 1 | 4 | [6 empty] | 4
| Span 4 | 3 | [6 empty] | 3
TOTAL | [8 empty] | 7 | 7

## POROUS BACKFILL
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 518E21200
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 33
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | POROUS BACKFILL WITH GEOTEXTILE FABRIC | [6 empty] | PAY UNIT | CY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| Avg. Height (ft) | Width (ft) | Length (ft) | Volume (ft^3) | Volume (yd^3)
| 6.9562 | 2 | 80.108 | 1114.5025 | 42 |  |  |  | 42
Forward Abutment
| Height (ft) | Width (ft) | Length (ft) | Volume (ft^3) | Volume (yd^3)
| 7.7287 | 2 | 60.821 | 940.1406 | 35 |  |  |  | 35
TOTAL | [8 empty] | 77 | 77

## P.C.P.P.
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 518E40000
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 34
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | 6" PERFORATED CORRUGATED PLASTIC PIPE | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| Length = | 75.666 | FT. | [5 empty] | 75.666
Forward Abutment
| Length = | 55.158 | FT. | [5 empty] | 55.158
TOTAL | [8 empty] | 131 | 131

## N.P.C.P.P.
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 518E40011
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 35
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | 6" NON-PERFORATED CORRUGATED PLASTIC PIPE, INCLUDING SPECIALS, AS PER PLAN | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| Length = | 40 | FT. | [5 empty] | 40
Forward Abutment
| Length = | 40 | FT. | [5 empty] | 40
TOTAL | [8 empty] | 80 | 80

## PATCHING CONC.
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 519E11101
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 36
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | PATCHING CONCRETE STRUCTURE, AS PER PLAN | [6 empty] | PAY UNIT | SF
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
| Abutment Contingency |  |  | 50 | SF |  |  |  | 50
| Pier Contingency |  |  | 50 | SF |  |  |  | 50
TOTAL | [8 empty] | 100 | 100

## CONC. APPR. SLABS
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 526E15011
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 37
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | REINFORCED CONCRETE APPROACH SLABS WITH QC/QA (T=13"), AS PER PLAN | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Approach Slab
| Length (ft.) | Width (ft.) | Area (yd^2)
| 20 | 73.5 | 163.3333 | [5 empty] | 163.3333
Forward Approach Slab
| Length (ft.) | Width (ft.) | Area (yd^2)
| 20 | 64.6667 | 143.7037 | [5 empty] | 143.7037
TOTAL | [8 empty] | 308 | 308

## TYPE C INSTALLATION
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 526E90030
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 38
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | TYPE C INSTALLATION | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Approach Slab
Length (ft.)
| 73.6757 | [7 empty] | 73.6757
Forward Approach Slab
Length (ft.)
| 64.8212 | [7 empty] | 64.8212
TOTAL | [8 empty] | 139 | 139

## ANCH
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 530E00400
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 39
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SPECIAL - STRUCTURES: GROUT AND SEAL TEMPORARY VANDAL PROTECTION FENCE ANCHOR HOLES | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
No. of Dowels per
| Post Spacing |  | Length Required |  | Base Plate BP-1 * |  | Total No. of Dowel Holes
| 5 |  | 300 |  | 4 |  | 240 |  | 240
|  |  | * | As per BP-1 of SCD VPF-1-90
TOTAL | [8 empty] | 240 | 240

## FALSE DECKING
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 530E00600
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 40
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SPECIAL - STRUCTURES: TEMPORARY FALSE DECKING FOR ENBRIDGE GAS LINES | [6 empty] | PAY UNIT | SF
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Spans 1 and 4 Between Beams 5 and 6
| Length (ft.) | Width (ft.) | Area (ft^2)
| 101.5 | 8.2917 | 841.6042 | [5 empty] | 841.6042
TOTAL | [8 empty] | 842 | 842

## FORM LINER
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 530E13000
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 41
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SPECIAL - FORM LINER | [6 empty] | PAY UNIT | SF
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Left Parapet on Approach Slabs and Deck
|  | Length (ft.) | Height (ft.)
|  | 298.511 | 2.1667 | [5 empty] | 646.7738
Right Parapet on Approach Slabs and Deck
|  | Length (ft.) | Height (ft.)
|  | 266.069 | 2.1667 | [5 empty] | 576.4828
TOTAL | [8 empty] | 1224 | 1224

## VANDAL PROTECT FENCE
QUANTITY |  |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 607E39901
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 42
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | VANDAL PROTECTION FENCE, 6' STRAIGHT, COATED FABRIC, AS PER PLAN | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Left Parapet
Length (ft.)
| 294.5 | [7 empty] | 294.5
Right Parapet
Length (ft.)
| 287 | [7 empty] | 287
TOTAL | [8 empty] | 582 | 582

## GAS LINE SUPPORT
QUANTITY |  | MADE BY: | JSE | DATE: | 2025-08-26 | ITEM NUMBER: | 690E98400
CALCULATIONS |  | CHECKED BY: | SJR | DATE: | 2025-08-26 | PAGE NUMBER: | 43
PID NO. | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME | SPECIAL - ENBRIDGE GAS LINE ROLLER GUIDE/SUPPORT | [6 empty] | PAY UNIT | LS
DESCRIPTION | [7 empty] | SUB TOTAL | TOTAL
LUMP SUM ITEM
TOTAL | [7 empty] | 0 | LS

## TEMP VANDAL PROTECT FENCE
QUANTITY |  |  | MADE BY: | JSP | DATE: | 2024-09-23 | ITEM NUMBER: | 607E39992
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-02-07 | PAGE NUMBER: | 43
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | TEMPORARY VANDAL PROTECTION FENCE, TYPE A | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Phase 1 Construction
Length (ft.)
|  |  | 298 | [5 empty] | 298
Phase 2 Construction
Length (ft.)
|  |  | 299 | [5 empty] | 299
TOTAL | [8 empty] | 597 | 597

## GRND
QUANTITY |  |  | MADE BY: | JSP | DATE: | 2024-09-23 | ITEM NUMBER: | 625E33000
CALCULATIONS |  |  | CHECKED BY: | SJR | DATE: | 2025-02-07 | PAGE NUMBER: | 44
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | STRUCTURE GROUNDING SYSTEM | [6 empty] | PAY UNIT | EACH
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
| STRUCTURE GOUNDING SYSTEM | [7 empty] | 1
TOTAL | [8 empty] | 1 | 1

## CONC. REPAIR BY EPOXY INJECTION
QUANTITY |  |  | MADE BY: | LAW | DATE: | 2024-01-22 | ITEM NUMBER: | 512E10600
CALCULATIONS |  |  | CHECKED BY: |  | DATE: |  | PAGE NUMBER: | 1
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | CONCRETE REPAIR BY EPOXY INJECTION | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
Length (ft)
| 21.2 | [7 empty] | 21.2
Forward Abutment
Length (ft)
| 7.42 | [7 empty] | 7.42
Piers
Length (ft)
P1 | 0 | [7 empty] | 0
P2 | 0 | [7 empty] | 0
P3 | 0 | [7 empty] | 0
P4 | 0 | [7 empty] | 0
P5 | 41.67 | [7 empty] | 41.67
P6 | 16.5 | [7 empty] | 16.5
TOTAL | [8 empty] | 86.79 | 86.79

## EXPANSION JOINT
QUANTITY |  |  | MADE BY: | JSP | DATE: | 2024-09-23 | ITEM NUMBER: | 516E11210
CALCULATIONS |  |  | CHECKED BY: |  | DATE: |  | PAGE NUMBER: | 1
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | STRUCTURAL EXPANSION JOINT INCLUDING ELASTOMERIC STRIP SEAL | [6 empty] | PAY UNIT | FT
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Rear Abutment
| Length = | 72.8403 | FT. | [5 empty] | 72.8403
Forward Abutment
| Length = | 63.8188 | FT. | [5 empty] | 63.8188
TOTAL | [8 empty] | 137 | 137

## HMWM RESIN
QUANTITY |  |  | MADE BY: | JSP | DATE: | 2024-09-23 | ITEM NUMBER: | 512E10300
CALCULATIONS |  |  | CHECKED BY: |  | DATE: |  | PAGE NUMBER: | 1
PID NO. |  | 1814168 |  | PROJECT | CUY-00480-06.120 |  | STRUCTURE | WEST 220TH OVER CUY-480
ITEM NAME |  | SEALING CONCRETE BRIDGE DECKS WITH HMWM RESIN | [6 empty] | PAY UNIT | SY
DESCRIPTION | [8 empty] | SUB TOTAL | TOTAL
Waterproofing at Abutment Corners
| Location | Length (ft) | Width (ft) | Area (ft^2) | Area (yd^2)
| PG & CROWN | 258.5108 | 2 | 517.0215 | 57.4468 |  |  |  | 57.4468
| PHASE C.J. | 258.5108 | 2 | 517.0215 | 57.4468 |  |  |  | 57.4468
NOTE: 3'-0" strip of waterproofing applied in wingwall outside corner from top of wingwall to 1'-6" below adjacent existing beam seat
TOTAL | [8 empty] | 114.8937 | 114.8937