## UPDATED CONFLICTS
Utility Conflict Matrix
| Project: | CUY-480-06.12 | PID 115826 | [7 empty] | By: | Jonathan Hren
| West 220th Street Bridge over I-480 Redecking, Fairview Park, Ohio | [6 empty] | Updated: | 2025-02-14 |  | Designer: | ms consultants, inc.
PLAN SHEET | Utility Company | Contact | Utility Type and Location | Near | Begin Station/ Offset | End SR 615 Station/ Offset | Conflict? | Utility Review? | Utility Review Date | Stage reviewed | Test Hole Required (Level A) | Utility Review Comments | Designer comments and action
| AT&T Ohio | Wendy Jack | Overhead telecom supported by light poles on the east side of bridge |  |  |  | Yes | Yes/No | 2024-12-16 | Stage 1 | No | Johathan, the above plans were received in our office. Plans are logged and reviewed according to the date they are received and the project construction dates. Once this new stage has been reviewed, you will be notified. Thank you for your patience. - Denise Plant | Utility responded at Stage 1 review that they would plan relocation. No response received from Stage 2 submittal. Will send Stage 3 plans to utility for review
| AT&T Transmission | Dan Gardner | n/a |  |  |  | No | Yes | 2023-08-04 | AER | No | On behalf of Bill Taggart, AT&T Transmission / Long Lines does not have facilities in the project area described. I have attached a map that shows this. I am not responding for AT&T Metro/LNS/ AT&T Ohio/Ohio Bell or any other affiliate of the AT&T Corp. These affiliates will respond on their own behalf. Thank you, Dan Gardner | Since utility not present no action.
| Breezeline | Joe Diaz | n/a |  |  |  | No | Yes | 2023-08-04 | AER | No | I sent you a print of our cable route in and around the W 220th St bridge Fairview Park OH 44126 and we do not have any cables in the vicinity of your construction area. Let me know if you have any questions. Thanks | Since utility not present no action.
| CEI Distribution - Overhead | John Zassick | Overhead Electric at northeast end of bridge for bridge lighting connection |  |  |  | Yes | Yes | 2024-09-27 | Stage 2 | No | Here is the response from engineering: See attached, Exhibit 9 of the customer guide. The customer would need to extend their conduit to the base of the pole following this exhibit. CEI will make final connections into the overhead. Also added is Exhibit 12 as well. This is for a stand along meter stanchion, which would be applicable if the customer wanted to provide their own lighting downstream of a single utility meter. We would prefer this. Sincerely, Dave Conley Regional External | Plans follow the utility's recommendations. Will send Stage 3 plans to utility for final review.
| CEI Distribution - Underground | Matt Hess | Conduits supported by bridge with electric cables | Entire bridge length |  |  | Yes | Yes | 2024-12-20 | Stage 2 | No | Johnathan: Our plan is to de-energize and remove the cables running through the bridge so that the bridge can be raised. We will then have to come back and reconnect the conduits from either side of the bridge once the bridge work is complete so we can re-run the cables through the bridge. Once we have drawings for our work we will send them over for coordination. Please let us know if you have any questions or concerns. Thanks. - Matt Hess | Plans follow the utility's recommendations. Will send Stage 3 plans to utility for final review.
| Cox | Craig Smith | n/a |  |  |  | No | Yes | 2024-12-16 | Stage 2 | No | Morning, When last we spoke, I had mentioned we are not on the bridge. We cross on the Mastick Road bridge not the one on West 220th. Craig | We will send Stage 3 plans to utility for final review.
| Cleveland Water Department | Rasheed Warith | n/a |  |  |  | No | Yes | 2024-05-10 | Stage 1 | No | Good afternoon Jonathan, I have reviewed the plans for the above referenced project. At this stage, Cleveland Water sees no potential conflicts. Thanks, Rasheed J. Warith | No respeonse from Stage 2 review. Will send Stage 3 plans to utility for final review.
| Enbridge | Cole D. Rudy, PE | Two gas mains supported by the bridge, one near each fascia beam |  |  |  | Yes | Yes | 2024-10-24 | Stage 2 | No | Good Morning Jonathan, Please find our comments on stage two drawings attached. Please let me know if you have any questions. Respectfully, Cole | Enbridge provided plan markups which we have included in the Stage 3 plans. We will send Stage 3 plans to utility for final review.
| Fairview Park | Megan Otter/Bryan Hitch | Signal Interconnect supported by bridge beams, lighting, and pedestrian traffic pushbotton |  |  |  | Yes | Partial | various | Stage 2 | No | I’m good Megan, Thank you - Bryan Hitch City of Fairview Park Hello Jonathan, The letter looks good to me. Bryan/Kim – any comments on the utilities and lighting? Thank you. - Megan Otter | We will send Stage 3 plans to utility/City for final review.
| Mastec | Brian Morris | n/a |  |  |  | No | Yes | 2023-08-04 | Stage 1 | No | Good Morning – Any cable placed by MasTec in this area is under the ownership of MCI. daniel.arz@verizon.com Thank you Brian Morris | Since utility not present no action.
| MCI/Verizon | Al Guest | n/a |  |  |  | No | Yes | 2003-09-28 | AER | No | Jonathan - MCI/Verizon has no facilities within the project area. Thanks, Al Guest | Since utility not present no action.
| Cleveland Water Pollution Control | Alan Schiely | n/a |  |  |  | No | Yes | 2023-08-04 | AER | No | We have reviewed the plans for the afore-mentioned project submitted to the Division of Water Pollution Control (WPC) on August 3, 2023. Being that the site is not located in the City of Cleveland, WPC does not have any sewer in the area and does not foresee any future involvement in this project. If you have any questions please feel free to call me at (216) 664-3638 or Elie Ramy at (216) 664-2756. Alan Schiely, | Since utility not present no action.