## Sheet1
Utility Company | Telephone # | Contact Name | Email ID | Address | Stage 1 Request sent date | Stage 2 Request Sent Date | Stage 2 Request Sent Date | Stage 3 Request Sent Date | Stage 3 Date Replied | Stage 3 Comments
DOMINION | 330-664-2409 |  | RELOCATION@DOMINIONENERGY.COM | 320 SPRINGSIDE DR, SUITE 320 AKRON, OHIO 44333 |  |  |  | 2025-05-20 | 2025-07-05 | We have a design team assembled to work on relocating the gas line off this bridge. Please forward CAD files so that we can use it for the relocation design. Brett Bell is the PM for the gas work.
| 888-504-0126 | Fax Number
AT&T Ohio | 216-534-7285 | JAMES JANIS | PJ8191@ATT.COM | 13630 LORAIN AVE - 2ND FLOOR CLEVELAND, OH 44111 Columbus, Ohio 43215 |  |  |  | 2025-05-20
SPECTRUM/CHARTER COMMS. | 440-701-4053 | BRANDON MCCULLOUGH | BRANDON.MCCULLOUGH@CHARTER.COM | 7820 DIVISION DRIVE MENTOR, OH 44060 Lancaster, Ohio 43130 |  |  |  | 2025-05-20
|  | EMIL SYMISTER | EMIL.SYMISTER@CHARTER.COM |  |  |  |  | cc'd 5-20-25
ILLUMINATING COMPANY | 440-546-8706 | JOHN ZASSICK | JMZASSICK@FIRSTENERGYCORP.COM | 3601 RIDGE ROAD CLEVELAND, OH 44102 |  |  |  | 2025-05-20 | 2025-05-21 | The Illuminating Company has facilities very close to, or in conflict with the proposed design and may need to modify them. Redesign or use extreme caution during installation.
CLEVELAND WATER DEPARTMENT | 330-664-2409 |  | INFO@CLEVELANDWATER.COM | 1201 LAKESIDE AVENUE CLEVELAND, OH 44114 Lancaster, Ohio 43130 |  |  |  | 2025-05-20
CUYAHOGA COUNTY SANITARY ENGINEERS | 216-443-8205 | LAURA WEBER | LAWEBER@CUYAHOGACOUNTY.US | 2709 N. 9TH STREET CLEVELAND, OH 44115 Lancaster, Ohio 43130 |  |  |  | 2025-05-20
VERIZON/MCI COMUNICATIONS | 330-622-5967 | AI GUEST |  | 120 RAVINE ST. AKRON, OH 44303
NORTHEAST OHIO REGIONAL SEWER | 216-881-6600 | ROBERT STOERKEL | STOERKELR@NEORSD.ORG | 3900 EUCLID AVENUE CLEVELAND, OH 44113 |  |  |  | 2025-05-20
ODOT OFFICE OF TECHNICAL SERVICES | 614-965-4463 | DARREN GERSTENSLAGER | DARREN.GERSTENSLAGER@DOT.OHIO.GOV | 2709 N. 9TH STREET CLEVELAND, OH 44115 Lancaster, Ohio 43130 |  |  |  | 2025-05-20
| 614-965-4463 | RONDA KELLER | RONDA.KELLER@DOT.OHIO.GOV |  |  |  |  | cc'd 5-20-25