## GR NOTES
PID# | 105784 |  |  | On NHS? | YES (southern segment only)/ NO (northern segment) |  | Function Class= | PR. ARTERIAL (southern segment only) / MAJOR COLLECTOR (northern segment) |  | Posted Speed Limit= |  | 55 MPH | ADT= | 12712 - 4842 |  | Required Offset from TW = |  | 10' - 8'
PLAN SPLIT: 02/NHS
PLAN SPLIT: 01/STR
EXISTING | [9 empty] | PROPOSED
0.00018939
GR Run | Side | SLM start | SLM end | App. Unit | Dep. Unit | Rail Length (LF) | Culvert? Y/N (#): Fillover Depth, (pipe size) | Offset from TW | Comments | SLM start | SLM end | Rail Length (LF) | App. Unit | Dep. Unit | App. LON (FT) | Dep. LON (FT) | App. CZ (FT) | Dep. CZ (FT) | Approach Hazard | Departure Hazard | Omit post for culvert? Y/N | Reduce post spacing for UT Poles? Y/N | Benching Required? Y/N | Recommendations
1 | LT | 0.214 | 0.157 | TYPE E | TYPE T | 237.5 | Y, 44" PIPE W/ 3' OF COVER | 6' |  | 0.214 | 0.15463 | 250 | TYPE E | TYPE T | 240 | 130 | 30 | 30 | PIPE | PIPE | N |  | N | watch post spacing at culvert. Omit 1 post if necessary.
Install Type E at approach end
LON on departure can not be met due to field drive. Lengthen departure end by 12.5' (to get rail out of ditch).
Install Type T at departure & wrap field drive, 12.5' @ 10' R
2 | RT | 0.154 | 0.196 | TYPE T | TYPE E | 162.5 | Y, 44" PIPE W/ 3' OF COVER | 4' |  | 0.154 | 0.196 | 162.5 | TYPE T | TYPE E | 260 | 150 | 30 | 30 | PIPE | PIPE | N |  | N | watch post spacing at culvert. Omit 1 post if necessary.
LON on approach can not be met due to field drive
Install Type T at approach end & wrap field drive, 12.5' @ 10' R
Install Type E at departure end
3 | LT | 1.134 | 1.05 | TYPE E | TYPE E | 337.5 | Y, 72" PIPE W/ 2' OF COVER | 4' |  | 1.1364 | 1.05 | 387.5 | TYPE T | TYPE E | 260 | 150 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert
Lengthen approach end by 12.5'. Install Type T & wrap drive, 12.5' @ 15' R
Install Type E at departure end
4 | RT | 1.033 | 1.097 | TYPE E | TYPE T | 275 | Y, 72" PIPE W/ 2' OF COVER | 4' |  | 1.0212 | 1.097 | 375 | TYPE T | TYPE T | 260 | 150 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert
Lenghten approach end by 62.5'. Install Type T & wrap drive, 12.5' @ 10' R
LON on departure can not be met due to drive.
Install Type T at departure & wrap drive, 12.5' @ 10' R
5 | LT | 1.486 | 1.397 | TYPE E | TYPE E | 375 | Y, 96" PIPE W/ 2' OF COVER | 6' |  | 1.486 | 1.3923 | 437.5 | TYPE E | TYPE T | 240 | 130 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert
Install Type E at approach end
Lengthen departure end by 25'. Install Type T & wrap drive, 12.5' @ 15' R
6 | RT | 1.373 | 1.47 | TYPE E | TYPE E | 412.5 | Y, 96" PIPE W/ 2' OF COVER | 4' |  | 1.373 | 1.47 | 412.5 | TYPE E | TYPE E | 260 | 150 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert
Install Type E at approach end
Install Type E at departure end
7 | LT | 2.56 | 2.404 | TYPE E | TYPE T | 762.5 | Y, 17.5' SPAN BOX CULVERT | 7' | BRIDGE LIC-62-02.39 | 2.56 | 2.404 | 725 | TYPE E | TYPE T | 230 | 120 | 30 | 30 | ??? | CULVERT | N, 50' LONG SPAN |  | N | Install 50' Long span at bridge. Remove 25' existing bridge rail.
Install Type E at approach end
Install Type T & wrap drive, 25' @ 8' R (due to long span)
8 | RT | 2.376 | 2.449 | TYPE T | TYPE E | 325 | Y, 17.5' SPAN BOX CULVERT | 5' | BRIDGE LIC-62-02.39 | 2.376 | 2.449 | 275 | TYPE T | TYPE E | 250 | 110 | 30 | 30 | CULVERT | CULVERT | N, 50' LONG SPAN |  | N | Install 50' Long span at bridge. Remove 25' existing bridge rail.
LON on approach can not be met due to drive.
Install Type T at approach & wrap drive, 12.5' @ 15' R
Install Type E at departure end
9 | LT | 2.904 | 2.797 | TYPE E | TYPE E | 462.5 | Y, 75" PIPE W/ 2' OF COVER | 5' |  | 2.904 | 2.797 | 462.5 | TYPE E | TYPE E | 250 | 140 | 30 | 30 |  |  | YES |  | N | Omit 1 post at culvert. (Replace in kind)
Install Type E at approach end
Install Type E at departure end
10 | RT | 2.828 | 2.888 | TYPE T | TYPE E | 250 | Y, 75" PIPE W/ 2' OF COVER | 4' |  | 2.828 | 2.888 | 250 | TYPE T | TYPE E | 260 | 150 | 30 | 30 |  |  | YES |  | N | LON on approach can not be met due to drive. Omit 1 post at culvert. (Replace in kind)
Install Type T at approach & wrap drive, 12.5' @ 20' R
Install Type E at departure end
11 | LT | 3.27 | 3.259 | BTA 4 | TYPE T | 25 | BRIDGE |  |  | 3.27 | 3.259 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
12 | RT | 3.264 | 3.273 | TYPE T | BTA 4 | 25 | BRIDGE |  |  | 3.264 | 3.273 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
13 | LT | 3.279 | 3.281 | TYPE T | BTA 4 | 0 | BRIDGE |  |  | 3.279 | 3.281 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
14 | RT | 3.284 | 3.324 | BTA 4 | TYPE E | 137.5 | BRIDGE |  |  | 3.284 | 3.324 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
15 | LT | 3.859 | 3.843 | BTA 1 | TYPE E | 12.5 | BRIDGE |  |  | 3.859 | 3.843 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
16 | RT | 3.829 | 3.855 | TYPE E | BTA 1 | 62.5 | BRIDGE |  |  | 3.829 | 3.855 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
17 | LT | 3.903 | 3.888 | TYPE E | BTA 1 | 12.5 | BRIDGE |  |  | 3.903 | 3.888 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
18 | RT | 3.884 | 3.9 | BTA 1 | TYPE E | 12.5 | BRIDGE |  |  | 3.884 | 3.9 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
19 | LT | 5.945 | 5.912 | BTA 4 | TYPE T | 137.5 | 49' SPAN BRIDGE | 7' | BRIDGE LIC-62-05.95 | 5.945 | 5.912 | 137.5 | BTA 4 | TYPE T | - | 100 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 125' of MGS (transition height)
Install Type T at departure end & wrap drive, 12.5' @ 10' R
20 | RT | 5.914 | 5.945 | TYPE T | BTA 4 | 125 | 49' SPAN BRIDGE | 9' | BRIDGE LIC-62-05.95 | 5.914 | 5.945 | 125 | TYPE T | BTA 4 | 175 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 112.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 10' R
21 | LT | 5.996 | 5.955 | TYPE T | BTA 4 | 175 | 49' SPAN BRIDGE | 7' | BRIDGE LIC-62-05.95 | 5.996 | 5.955 | 175 | TYPE T | BTA 4 | 192 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 162.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 15' R
22 | RT | 5.956 | 5.98 | BTA 4 | TYPE E | 50 | 49' SPAN BRIDGE | 9' | BRIDGE LIC-62-05.95 | 5.956 | 5.98 | 50 | BTA 4 | TYPE E | - | 84 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 50' of MGS (transition height)
Install Type E at departure end
23 | LT | 8.49 | 8.43 | TYPE T | TYPE E | 250 | 12' SPAN BRIDGE W/ 1' OF COVER | 10' | BRIDGE LIC-62-08.45 | 8.49 | 8.43 | 200 | TYPE T | TYPE E | 167 | 75 | 30 | 30 | CULVERT | CULVERT | N, 43.75' LONG SPAN |  | N | Install 43.75 Long Span unit at culvert. Remove 18.75' of bridge railing
Install Type T at approach & wrap drive, 12.5' @ 15' R
Install Type E at departure end
24 | RT | 8.426 | 8.48 | TYPE T | TYPE E | 225 | 12' SPAN BRIDGE W/ 1' OF COVER | 6' | BRIDGE LIC-62-08.45 | 8.426 | 8.48 | 137.5 | TYPE E | TYPE E | 200 | 109 | 30 | 30 | CULVERT | CULVERT | N, 43.75' LONG SPAN |  | N | Install 43.75 Long Span unit at culvert. Remove 18.75' of bridge railing
Install Type E at approach end
Install Type E at departure end
25 | LT | 9.385 | 9.29 | TYPE E | TYPE E | 400 | Y, 72" PIPE W/ 3' OF COVER | 6' |  | 9.385 | 9.2782 | 462.5 | TYPE E | TYPE E | 200 | 109 | 30 | 30 |  | CULVERT | Y |  | N | Omit 1 post at culvert
Install Type E at approach end
Lenghten departure end by 62.5' to meet LON. Install Type E at departure end
26 | RT | 10.375 | 10.417 | TYPE E | TYPE T | 162.5 | Y, 60" PIPE W/ 2' OF COVER | 5' |  | 10.3726 | 10.417 | 175 | TYPE E | TYPE T | 209 | 117 | 30 | 30 | CULVERT | CULVERT | N |  | N | Watch post spacing at pipe. (Can't omit 1 post at departure)
Lenghten the approach end by 12.5' to meet LON. Install Type E
Can not meet LON on departure end due to drive
Install Type T & wrap drive, 12.5' @ 20' R
27 | LT | 10.57 | 10.522 | BTA 4 | TYPE E | 175 | 23' SPAN BOX CULVERT | 11' | BRIDGE LIC-62-10.57 | 10.57 | 10.522 | 175 | BTA 4 | TYPE E | - | 67 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 175' of MGS (transition height)
Install Type E at departure end
28 | RT | 10.475 | 10.57 | TYPE E | BTA 4 | 425 | 23' SPAN BOX CULVERT | 10' | BRIDGE LIC-62-10.57 | 10.475 | 10.57 | 425 | TYPE E | BTA 4 | 167 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 425' of MGS (transition height)
Install Type E at approach end
29 | LT | 10.605 | 10.581 | TYPE E | BTA 4 | 87.5 | 23' SPAN BOX CULVERT | 12' | BRIDGE LIC-62-10.57 | 10.605 | 10.581 | 87.5 | TYPE E | BTA 4 | 45 | - | 8 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 87.5' of MGS (transition height) & wrap side road
Install Type E at approach end (along side road)
30 | RT | 10.581 | 10.616 | BTA 4 | TYPE T | 150 | 23' SPAN BOX CULVERT | 8' | BRIDGE LIC-62-10.57 | 10.581 | 10.616 | 150 | BTA 4 | TYPE T | - | 92 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 125' of MGS (transition height)
Install Type T at departure end & wrap drive, 25' @ 20' R
31 | RT | 10.621 | 10.741 | TYPE T | TYPE T | 612.5 | N | 10' |  | 10.621 | 10.7386 | 562.5 | TYPE T | TYPE E | 167 | 75 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap drive, 12.5' @ 15' R
Shorten departure end by 12.5' & Install Type E
32 | LT | 11.043 | 11.002 | BTA 4 | TYPE E | 137.5 | 48' SPAN BRIDGE | 12' | BRIDGE LIC-62-11.04 | 11.043 | 11.002 | 137.5 | BTA 4 | TYPE E | - | 59 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 137.5' of MGS (transition height)
Install Type E at departure end
33 | RT | 10.994 | 11.038 | TYPE E | BTA 4 | 150 | 48' SPAN BRIDGE | 9' | BRIDGE LIC-62-11.04 | 10.994 | 11.038 | 150 | TYPE E | BTA 4 | 175 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 150' of MGS (transition height)
Install Type E at approach end
34 | LT | 11.082 | 11.067 | TYPE T | BTA 4 | 50 | 48' SPAN BRIDGE | 12' | BRIDGE LIC-62-11.04 | 11.082 | 11.067 | 50 | TYPE T | BTA 4 | 150 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 37.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 10' R
35 | RT | 11.063 | 11.095 | BTA 4 | TYPE T | 137.5 | 48' SPAN BRIDGE | 9' | BRIDGE LIC-62-11.04 | 11.063 | 11.095 | 137.5 | BTA 4 | TYPE T | - | 84 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 125' of MGS (transition height)
Install Type T at departure end & wrap drive, 12.5' @ 10' R
36 | LT | 11.214 | 11.088 | TYPE E | TYPE T | 600 | N | 12' |  | 11.214 | 11.088 | 600 | TYPE E | TYPE T | 150 | 59 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install Type T at departure & wrap drive, 12.5' @ 10' R
37 | LT | 11.496 | 11.409 | TYPE T | TYPE E | 400 | N | 10' |  | 11.496 | 11.409 | 400 | TYPE T | TYPE E | 167 | 75 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap drive, 12.5' @ 15' R
Install Type E at departure end
38 | RT | 11.385 | 11.478 | TYPE E | TYPE T | 437.5 | N | 6' |  | 11.385 | 11.478 | 437.5 | TYPE E | TYPE T | 200 | 109 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install Type T at departure & wrap drive, 25' @ 20' R
39 | LT | 12.996 | 12.964 | BTA 4 | TYPE E | 87.5 | 55' SPAN BRIDGE | 11' | BRIDGE LIC-62-13.00 | 12.996 | 12.9474 | 87.5 | BTA 4 | TYPE E | - | 67 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 87.5' of MGS (transition height)
Install Type E at departure end
40 | RT | 12.961 | 13.002 | TYPE E | BTA 4 | 137.5 | 55' SPAN BRIDGE | 8' | BRIDGE LIC-62-13.00 | 12.961 | 13.002 | 137.5 | TYPE E | BTA 4 | 184 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 137.5' of MGS (transition height)
Install Type E at approach end
41 | LT | 13.075 | 13.025 | TYPE E | BTA 4 | 187.5 | 55' SPAN BRIDGE | 12' | BRIDGE LIC-62-13.00 | 13.075 | 13.025 | 187.5 | TYPE E | BTA 4 | 150 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 187.5' of MGS (transition height)
Install Type E at approach end
42 | RT | 13.031 | 13.064 | BTA 4 | TYPE E | 87.5 | 55' SPAN BRIDGE | 8' | BRIDGE LIC-62-13.00 | 13.031 | 13.064 | 87.5 | BTA 4 | TYPE E | - | 92 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 87.5' of MGS (transition height)
Install Type E at departure end
43 | RT | 13.215 | 13.323 | TYPE E | TYPE T | 512.5 | N | 8' |  | 13.2008 | 13.323 | 625 | TYPE T | TYPE T | 184 | 92 | 30 | 30 |  |  | N |  | N | Lenghten approach end by 75'. Install Type T & wrap drive, 12.5' @ 15' R
Install 600' of MGS
Install Type T at departure end & wrap drive, 12.5' @ 10' R
44 | LT | 13.94 | 13.886 | TYPE E | TYPE T | 200 | 13' SPAN BOX CULVERT, UNKNOWN COVER | 9' | BRIDGE LIC-62-13.89. No future bridge work anticipated | 13.9495 | 13.886 | 312.5 | TYPE T | TYPE T | 175 | 84 | 30 | 30 |  |  | N, 43.75' LONG SPAN |  | N | Lengthen approach end by 50' & Install Type T. Wrap drive, 12.5' @ 20' R
Install 43.75' Long Span unit at culvert. Remove 18.75' of bridge railing
Can not meet LON due to drive. Wrap driveway 25' @ 15' R
Install 12.5' of MGS and Type T at departure end (along drive). Wrap drive at end of rail at fence, 12.5' @ 10' R
45 | RT | 13.844 | 13.914 | TYPE E | TYPE E | 250 | 13' SPAN BOX CULVERT, UNKNOWN COVER | 8' | BRIDGE LIC-62-13.89. No future bridge work anticipated | 13.844 | 13.914 | 225 | TYPE E | TYPE E | 184 | 92 | 30 | 30 |  |  | N, 43.75' LONG SPAN |  | N | Install Type E at approach end
Install 43.75' Long Span unit at culvert. Remove 18.75' of bridge railing
Install 225' of MGS
Install Type E at departure end
46 | RT | 14.334 | 14.392 | TYPE T | TYPE T | 287.5 | N | 6' |  | 14.334 | 14.392 | 287.5 | TYPE T | TYPE T | 200 | 109 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap field drive, 12.5' @ 10' R
Install Type T at departure & wrap drive, 12.5' @ 10' R
47 | LT | 15.391 | 15.377 | TYPE T | BTA 4 | 50 | 21' SPAN BOX CULVERT | 10' | BRIDGE LIC-62-15.37 | 15.391 | 15.377 | 50 | TYPE T | BTA 4 | - | 63 | - | 30 |  |  | N |  |  | NO FUTURE BRIDGE WORK PLANNED
SKIP RUN WEST OF BRIDGE ONLY, CAN NOT DO LONG SPAN OR MGS DUE TO DRIVEWAY
Install new BTA 4 at east side of bridge. Install 37.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 8' R
48 | RT | 15.358 | 15.395 | TYPE T | TYPE E | 112.5 | 21' SPAN BOX CULVERT | 12' | BRIDGE LIC-62-15.37 | 15.358 | 15.395 | 87.5 | TYPE T | TYPE E | 126 | - | 30 | - |  |  | N, 50' LONG SPAN |  |  | NO FUTURE BRIDGE WORK PLANNED
Install 50' Long Span unit at culvert. Remove 25' of existing bridge railing
Install 87.5' of MGS
Install Type T at approach & wrap drive, 12.5' @ 20' R
49 | RT | 15.834 | 15.91 | TYPE T | TYPE E | 350 | N | 9' |  | 15.834 | 15.91 | 350 | TYPE T | TYPE E | 147 | 70 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap field drive, 12.5' @ 10' R
Install Type E at departure end
50 | LT | 16.177 | 16.297 | TYPE T | TYPE E | 587.5 | N | 10' |  | 16.177 | 16.297 | 587.5 | TYPE T | TYPE E | 138 | 86 | 39 | 39 |  |  | N |  | N | Install Type T at approach & wrap field drive, 12.5' @ 10' R
Install Type E at departure end
51 | RT | 16.189 | 16.293 | TYPE E | TYPE E | 450 | N | 9' |  | 16.189 | 16.293 | 450 | TYPE E | TYPE E | 147 | 70 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 450' of MGS
Install Type E at departure end
52 | LT | 17.654 | 17.799 | TYPE E | TYPE T | 712.5 | N | 8' |  | 17.654 | 17.799 | 712.5 | TYPE E | TYPE T | 154 | 77 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 700' of MGS
Install Type T at departure & wrap drive, 12.5' @ 15' R
53 | RT | 17.64 | 17.81 | TYPE E | TYPE E | 800 | N | 7' |  | 17.64 | 17.81 | 800 | TYPE E | TYPE E | 161 | 84 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 800' of MGS
Install Type E at departure end
54 | LT | 18.096 | 18.194 | TYPE T | TYPE T | 512.5 | N | 7' |  | 18.096 | 18.194 | 512.5 | TYPE T | TYPE T | 161 | 84 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap drive, 12.5' @ 10' R
Install Type T at departure & wrap drive, 12.5' @ 15' R
Install 487.5' of MGS
55 | LT | 18.245 | 18.386 | TYPE A | TYPE E | 700 | N | 7' |  | 18.245 | 18.386 | 700 | TYPE A | TYPE E | 10 | 84 | 8 | 30 |  |  | N |  | N | Install Type A at approach end (on side road)
wrap LIC-62, 37.5' @ 25' R. Install 662.5' of MGS
Install Type E at departure end
56 | LT | 18.392 | 18.401 | BTA 4 | TYPE A | 50 | BRIDGE | 7' | BRIDGE LIC-62-18.45 | 18.392 | 18.401 | 37.5 | BTA 4 | TYPE T | - | 84 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
[14 empty] | TYPE A | [9 empty] | Install 37.5' of MGS (transition height) & wrap side road
Install Type A at departure end (along side road)
57 | RT | 18.395 | 18.406 | TYPE E | BTA 4 | 62.5 | BRIDGE | 7' | BRIDGE LIC-62-18.45 | 18.395 | 18.406 | 87.5 | TYPE A | BTA 4 | 149 | - | 36 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 87.5' of MGS (transition height) & wrap side road
Install Type A at approach end (along side road)
58 | LT | 18.477 | 18.444 | TYPE E | BTA 4 | 100 | BRIDGE | 8' | BRIDGE LIC-62-18.45 | 18.477 | 18.444 | 187.5 | TYPE T | BTA 4 | 154 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 187.5' of MGS (transition height)
Lenghten app end by 50'. Install Type T at approach end & wrap drive, 12.5' @ 15' R.
59 | RT | 18.45 | 18.461 | BTA 4 | TYPE T | 12.5 | BRIDGE | 8' | BRIDGE LIC-62-18.45 | 18.45 | 18.461 |  |  |  | - | 88 | - | 36 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
SKIP RUN, CAN NOT DO LONG SPAN OR MGS DUE TO DRIVEWAY
60 | LT | 18.891 | 18.72 | BTA TST | TYPE E | 912.5 | BRIDGE |  |  | 18.891 | 18.72 | [12 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
61 | RT | 18.721 | 18.893 | TYPE E | BTA TST | 912.5 | BRIDGE |  |  | 18.721 | 18.893 | [12 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
62 | LT | 19.049 | 18.928 | TYPE E | BTA TST | 650 | BRIDGE |  |  | 19.049 | 18.928 | [12 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
63 | RT | 18.928 | 19.045 | BTA TST | TYPE E | 625 | BRIDGE |  |  | 18.928 | 19.045 | [12 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
64 | RT | 19.287 | 19.321 | TYPE T | TYPE E | 125 |  |  |  | 19.287 | 19.321 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
65 | LT | 19.447 | 19.384 | TYPE E | TYPE E | 225 |  |  |  | 19.447 | 19.384 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
66 | RT | 19.356 | 19.469 | TYPE E | TYPE T | 537.5 |  |  |  | 19.356 | 19.469 | [12 empty] | SKIP. OWNED BY MUNICIPALITY
67 | LT | 19.767 | 19.603 | TYPE E | TYPE A | 800 | N | 9' |  | 19.767 | 19.603 | 812.5 | TYPE E | TYPE A | 147 | 70 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 762.5' of MGS
Wrap side road, 50' @ 60' R
Lengthen departure by 12.5' & Install Type A (on side road)
68 | RT | 19.613 | 19.685 | TYPE T | TYPE T | 362.5 | N | 7' |  | 19.613 | 19.685 | 362.5 | TYPE T | TYPE T | 161 | 84 | 30 | 30 |  |  | N |  | N | Install Type T at approach end & wrap drive, 12.5' @ 10' R
Install 337.5' of MGS
Install Type T at departure end & wrap drive, 12.5' @ 15' R
69 | LT | 20.265 | 20.214 | TYPE E | TYPE E | 162.5 | N | 7' |  | 20.265 | 20.214 | 162.5 | TYPE E | TYPE E | 161 | 84 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 162.5' of MGS
Install Type E at departure end

## QTY
GR Run | App. Unit | Dep. Unit | Rail Length | Rail Length | App. Unit | Dep. Unit | LONG SPAN UNIT | Reset/Relocate mailbox(es) # | Signs # | Barrier Reflector,Bi-directional* | Reshaping Berm | Benched Rail | Remove Bridge Railing | Replace Bridge W-beam rail
1 | TYPE E | TYPE T | 237.5 | 250 | TYPE E | TYPE T | 0 | 0 | 2 | 5 | 250 | 0 | 0 | 0 | * Tangent or greater than 1,148' radius = 100' spacing less than 1,148' radius = 50' spacing
2 | TYPE T | TYPE E | 162.5 | 162.5 | TYPE T | TYPE E | 0 | 0 | 2 | 4 | 163 | 0 | 0 | 0
3 | TYPE E | TYPE E | 337.5 | 387.5 | TYPE T | TYPE E | 0 | 0 | 0 | 6 | 388 | 0 | 0 | 0
4 | TYPE E | TYPE T | 275 | 375 | TYPE T | TYPE T | 0 | 1 | 0 | 6 | 375 | 0 | 0 | 0
5 | TYPE E | TYPE E | 375 | 437.5 | TYPE E | TYPE T | 0 | 0 | 2 | 7 | 438 | 0 | 0 | 0
6 | TYPE E | TYPE E | 412.5 | 412.5 | TYPE E | TYPE E | 0 | 0 | 0 | 7 | 413 | 0 | 0 | 0
7 | TYPE E | TYPE T | 737.5 | 725 | TYPE E | TYPE T | 50 | 0 | 8 | 10 | 775 | 0 | 25 | 0
8 | TYPE T | TYPE E | 300 | 275 | TYPE T | TYPE E | 50 | 0 | 1 | 6 | 325 | 0 | 25 | 0
9 | TYPE E | TYPE E | 462.5 | 462.5 | TYPE E | TYPE E | 0 | 0 | 1 | 7 | 463 | 0 | 0 | 0
10 | TYPE T | TYPE E | 250 | 250 | TYPE T | TYPE E | 0 | 1 | 0 | 5 | 250 | 0 | 0 | 0
02/NHS PLAN SPLIT: |  |  | 3550 | 3737.5 |  |  | 100 | 2 | 16 | 63 | 3840 | 0 | 50 | 0 | 14 -TYPE E REMOVED, 6 - TYPE T REMOVED; 11 - TYPE E NEW, 9 - TYPE T NEW
11
12
13
14
15
16
17
18
19 | BTA 4 | TYPE T | 137.5 | 137.5 | BTA 4 | TYPE T | 0 | 1 | 0 | 4 | 138 | 0 | 0 | 25
20 | TYPE T | BTA 4 | 125 | 125 | TYPE T | BTA 4 | 0 | 0 | 0 | 4 | 125 | 0 | 0 | 25
21 | TYPE T | BTA 4 | 175 | 175 | TYPE T | BTA 4 | 0 | 0 | 0 | 4 | 175 | 0 | 0 | 25
22 | BTA 4 | TYPE E | 50 | 50 | BTA 4 | TYPE E | 0 | 0 | 0 | 3 | 50 | 0 | 0 | 25
23 | TYPE T | TYPE E | 231.25 | 200 | TYPE T | TYPE E | 43.75 | 0 | 0 | 5 | 244 | 0 | 18.75 | 0
24 | TYPE T | TYPE E | 206.25 | 137.5 | TYPE E | TYPE E | 43.75 | 0 | 6 | 4 | 182 | 0 | 18.75 | 0
25 | TYPE E | TYPE E | 400 | 462.5 | TYPE E | TYPE E | 0 | 0 | 1 | 7 | 463 | 0 | 0 | 0
26 | TYPE E | TYPE T | 162.5 | 175 | TYPE E | TYPE T | 0 | 0 | 0 | 4 | 175 | 0 | 0 | 0
27 | BTA 4 | TYPE E | 175 | 175 | BTA 4 | TYPE E | 0 | 0 | 0 | 4 | 175 | 0 | 0 | 31.25
28 | TYPE E | BTA 4 | 425 | 425 | TYPE E | BTA 4 | 0 | 0 | 0 | 7 | 425 | 0 | 0 | 31.25
29 | TYPE E | BTA 4 | 87.5 | 87.5 | TYPE E | BTA 4 | 0 | 0 | 1 | 3 | 88 | 0 | 0 | 31.25
30 | BTA 4 | TYPE T | 150 | 150 | BTA 4 | TYPE T | 0 | 0 | 0 | 4 | 150 | 0 | 0 | 31.25
31 | TYPE T | TYPE T | 612.5 | 562.5 | TYPE T | TYPE E | 0 | 1 | 0 | 8 | 563 | 0 | 0 | 0
32 | BTA 4 | TYPE E | 137.5 | 137.5 | BTA 4 | TYPE E | 0 | 0 | 0 | 4 | 138 | 0 | 0 | 68.75
33 | TYPE E | BTA 4 | 150 | 150 | TYPE E | BTA 4 | 0 | 0 | 2 | 4 | 150 | 0 | 0 | 68.75
34 | TYPE T | BTA 4 | 50 | 50 | TYPE T | BTA 4 | 0 | 0 | 0 | 3 | 50 | 0 | 0 | 68.75
35 | BTA 4 | TYPE T | 137.5 | 137.5 | BTA 4 | TYPE T | 0 | 0 | 0 | 4 | 138 | 0 | 0 | 68.75
36 | TYPE E | TYPE T | 600 | 600 | TYPE E | TYPE T | 0 | 0 | 0 | 8 | 600 | 0 | 0 | 0
37 | TYPE T | TYPE E | 400 | 400 | TYPE T | TYPE E | 0 | 0 | 0 | 6 | 400 | 0 | 0 | 0
38 | TYPE E | TYPE T | 437.5 | 437.5 | TYPE E | TYPE T | 0 | 0 | 0 | 7 | 438 | 0 | 0 | 0
39 | BTA 4 | TYPE E | 87.5 | 87.5 | BTA 4 | TYPE E | 0 | 0 | 0 | 3 | 88 | 0 | 0 | 75
40 | TYPE E | BTA 4 | 137.5 | 137.5 | TYPE E | BTA 4 | 0 | 0 | 4 | 4 | 138 | 0 | 0 | 75
41 | TYPE E | BTA 4 | 187.5 | 187.5 | TYPE E | BTA 4 | 0 | 0 | 1 | 4 | 188 | 0 | 0 | 75
42 | BTA 4 | TYPE E | 87.5 | 87.5 | BTA 4 | TYPE E | 0 | 0 | 4 | 3 | 88 | 0 | 0 | 75
43 | TYPE E | TYPE T | 512.5 | 625 | TYPE T | TYPE T | 0 | 1 | 3 | 9 | 625 | 0 | 0 | 0
44 | TYPE E | TYPE T | 181.25 | 312.5 | TYPE T | TYPE T | 43.75 | 0 | 0 | 6 | 357 | 0 | 18.75 | 0
45 | TYPE E | TYPE E | 231.25 | 225 | TYPE E | TYPE E | 43.75 | 0 | 0 | 5 | 269 | 0 | 18.75 | 0
46 | TYPE T | TYPE T | 287.5 | 287.5 | TYPE T | TYPE T | 0 | 0 | 0 | 5 | 288 | 0 | 0 | 0
47 | TYPE T | BTA 4 | 50 | 50 | TYPE T | BTA 4 | 0 | 0 | 0 | 3 | 50 | 0 | 0 | 0
48 | TYPE T | TYPE E | 87.5 | 87.5 | TYPE T | TYPE E | 50 | 0 | 0 | 4 | 138 | 0 | 25 | 0
49 | TYPE T | TYPE E | 350 | 350 | TYPE T | TYPE E | 0 | 1 | 0 | 6 | 350 | 0 | 0 | 0
50 | TYPE T | TYPE E | 587.5 | 587.5 | TYPE T | TYPE E | 0 | 0 | 0 | 8 | 588 | 0 | 0 | 0
51 | TYPE E | TYPE E | 450 | 450 | TYPE E | TYPE E | 0 | 0 | 0 | 7 | 450 | 0 | 0 | 0
52 | TYPE E | TYPE T | 712.5 | 712.5 | TYPE E | TYPE T | 0 | 0 | 0 | 10 | 713 | 0 | 0 | 0
53 | TYPE E | TYPE E | 800 | 800 | TYPE E | TYPE E | 0 | 0 | 3 | 10 | 800 | 0 | 0 | 0
54 | TYPE T | TYPE T | 512.5 | 512.5 | TYPE T | TYPE T | 0 | 7 | 0 | 8 | 513 | 0 | 0 | 0
55 | TYPE A | TYPE E | 700 | 700 | TYPE A | TYPE E | 0 | 5 | 0 | 9 | 700 | 0 | 0 | 0
56 | BTA 4 | TYPE A | 50 | 37.5 | BTA 4 | TYPE T & TYPE A | 0 | 0 | 1 | 3 | 38 | 0 | 0 | 100
57 | TYPE E | BTA 4 | 62.5 | 87.5 | TYPE A | BTA 4 | 0 | 0 | 4 | 3 | 88 | 0 | 0 | 100
58 | TYPE E | BTA 4 | 100 | 187.5 | TYPE T | BTA 4 | 0 | 0 | 2 | 4 | 188 | 0 | 0 | 100
59 | [13 empty] | 100
60
61
62
63
64
65
66
67 | TYPE E | TYPE A | 800 | 812.5 | TYPE E | TYPE A | 0 | 0 | 3 | 11 | 813 | 0 | 0 | 0
68 | TYPE T | TYPE T | 362.5 | 362.5 | TYPE T | TYPE T | 0 | 1 | 1 | 6 | 363 | 0 | 0 | 0
69 | TYPE E | TYPE E | 162.5 | 162.5 | TYPE E | TYPE E | 0 | 0 | 2 | 4 | 163 | 0 | 0 | 0
01/STR PLAN SPLIT: |  |  | 12350 | 12625 |  |  | 225 | 17 | 38 | 232 | 12863 | 0 | 100 | 1200
TOTAL = |  |  | 15900 | 16362.5 |  |  | 325 | 19 | 54 | 295 | 16703 | 0 | 150 | 1200

## ESTIMATE
LIC-62 Preliminary Estimate
Item No. | Description | Quantity | Unit | Unit Price | Total
ROADWAY
202E38000 | Guardrail Removed | 15900 | FT | 2 | 31800
202E38001 | Guardrail Removed, As Per Plan | 0 | FT | 2.25 | 0
202E38500 | Bridge Railing Removed | 150 | FT | 4.5 | 675
202E42000 | Anchor Assembly Removed, Type A | 3 | EA | 270 | 810
202E42010 | Anchor Assembly Removed, Type E | 50 | EA | 150 | 7500 | Project Disturbed Area (acres):
202E42040 | Anchor Assembly Removed, Type T | 33 | EA | 100 | 3300 | (x)SY/ 4840 sy per acre
202E42050 | Anchor Assembly Removed, Type B | 0 | EA | 130 | 0
202E47000 | Bridge Terminal Assembly Removed | 20 | EA | 80 | 1600 | 5567.6667
0
606E15100 | Guardrail, Type MGS w/ Long Posts | 16362.5 | FT | 20 | 327250 | 416.6667
606E16001 | Guardrail Rebuilt, As Per Plan | 1200 | FT |  | 0
606E17360 | Guardrail, Type MGS, Long-Span | 325 | FT | 22 | 7150 | 84
606E19001 | Guardrail Post, Steel, As Per Plan | 163.625 | EA | 75 | 12271.875 | 2250
606E25550 | Anchor Assembly MGS, Type A | 4 | EA | 1450 | 5800 | 418
606E26150 | Anchor Assembly MGS, Type E | 45 | EA | 2500 | 112500 | 8736.3333 | SY
606E26550 | Anchor Assembly MGS, Type T | 38 | EA | 1100 | 41800 | 1.805 | ACRES
606E34600 | MGS Bridge Terminal Assembly, Type TST-2 | 0 | EA | 2400 | 0
606E35002 | MGS Bridge Terminal Assembly, Type 1 | 0 | EA | 2325 | 0
606E35140 | Bridge Terminal Assembly, Type 4 | 20 | EA | 800 | 16000
606E50000 | Reshaping Berm | 16703 | FT | 0.3 | 5010.9
606E98000 | Guardrail, Misc.: Existing W-Beam for Shoulder Support Benching | 0 | FT | 7 | 0
606E98000 | Guardrail, Misc.: Shoulder Support Benching | 0 | FT | 7 | 0
690E50350 | Mailbox Removed & Reset | 19 | EA | 35 | 665
|  |  |  | SUB-TOTAL | 574132.775
TRAFFIC CONTROL
626E00110 | Barrier Reflector, Type 2, Bi-Directional | 295 | EA | 8 | 2360 |  | Tangent or greater than 1,148' radius = 100' spacing / less than 1,148' radius = 50' spacing
630E03100 | Ground Mounted Support, No. 3 Post | 810 | FT | 8 | 6480 |  | Length per post = 15'
630E85100 | Removal of Ground Mounted Sign & Reerection | 54 | EA | 35 | 1890
630E86002 | Removal of Ground Mounted Post Support & Disposal | 54 | EA | 15 | 810
|  |  |  | SUB-TOTAL | 11540
| EROSION CONTROL | [5 empty] | GRADING: |  | SY | EMBANKMENT:
203E20001 | Embankment | 1710 | CY | 28 | 47880 |  | TYPE E UNIT = |  | 50 | TYPE E UNIT = 34 CY | 33.3333
204E50001 | Geotextile Fabric, As Per Plan | 0 | SY | 2.5 | 0 |  | TYPE A UNIT = |  | 21 | TYPE A UNIT = 7 CY | 6.9444
659E00510 | Seeding & Mulching, Class 2 | 2752 | SY | 1.3 | 3577.6 |  | TYPE T UNIT = |  | 11 | TYPE T UNIT = 4 CY | 3.4722
659E20000 | Commercial Fertilizer | 0.37139 | Ton | 680 | 252.5452 |  | TYPE B UNIT = |  | 32 | TYPE B UNIT = 11 CY | 10.4167
659E31000 | Lime | 0.5686 | Acre | 65 | 36.9587
659E35000 | Water | 14.8608 | Mgal | 1 | 14.8608
670E00500 | Slope Erosion Protection | 2752 | SY | 1.6 | 4403.2
832E30000 | Erosion Control | 800 | EA | 1 | 800
|  |  |  | SUB-TOTAL | 56965.1647
687837.9397
INCIDENTALS
614E11000 | Maintaining Traffic |  | LS | 12852.7588 | 13000
623E10001 | Construction Layout Stakes & Surveying |  | LS | 6426.3794 | 7000
624E10000 | Mobilization |  | LS | 25705.5176 | 26000
|  |  |  | SUB-TOTAL | 46000
|  |  |  | TOTAL= | 688637.9397
|  |  |  | *From Project 108312: | Project Total | *From Project 101235: | Project Total
| INCIDENTALS | USE: |  |  | 2972093.75 |  | 1957620.79 | AVG:
| Maintaining Traffic | 2% |  | 35000 | 1.178% | 22000 | 1.124% | 1.151%
| Construction Layout Stakes & Surveying | 1% |  | 25000 | 0.8412% | 16000 | 0.8173% | 0.8292%
| Mobilization | 4% |  | 100000 | 3.365% | 58000 | 2.963% | 3.164%
* Avg. Costs from All Bidders

## FIELD NOTES
PID# | 105784 |  |  | On NHS? | YES (southern segment only)/ NO (northern segment) |  | Function Class= | PR. ARTERIAL (southern segment only) / MAJOR COLLECTOR (northern segment) |  | Posted Speed Limit= |  | 55 MPH | ADT= | 12712 - 4842 |  | Required Offset from TW = |  | 10' - 8'
PLAN SPLIT:
PLAN SPLIT:
EXISTING | [9 empty] | PROPOSED
0.00018939
GR Run | Side | SLM start | SLM end | App. Unit | Dep. Unit | Rail Length (LF) | Culvert? Y/N (#): Fillover Depth, (pipe size) | Offset from TW | Comments | SLM start | SLM end | Rail Length (LF) | App. Unit | Dep. Unit | App. LON (FT) | Dep. LON (FT) | App. CZ (FT) | Dep. CZ (FT) | Approach Hazard | Departure Hazard | Omit post for culvert? Y/N | Reduce post spacing for UT Poles? Y/N | Benching Required? Y/N | Recommendations
1 | LT | 0.214 | 0.157 | TYPE E | TYPE T | 237.5 | Y, 44" PIPE W/ 3' OF COVER | 6' |  | 0.214 | 0.15463 | 250 | TYPE E | TYPE T | 240 | 130 | 30 | 30 | PIPE | PIPE | N |  | N | watch post spacing at culvert. Omit 1 post if necessary.
Install Type E at approach end.
Install 237.5' of MGS. LON on departure can not be met due to field drive.
Lengthen departure end by 12.5' (to get rail out of ditch). Install Type T & wrap field drive, 12.5' @ 10' R
2 | RT | 0.154 | 0.196 | TYPE T | TYPE E | 162.5 | Y, 44" PIPE W/ 3' OF COVER | 4' |  | 0.154 | 0.196 | 162.5 | TYPE T | TYPE E | 260 | 150 | 30 | 30 | PIPE | PIPE | N |  | N | watch post spacing at culvert. Omit 1 post if necessary.
LON on approach can not be met due to field drive. Install Type T & wrap field drive, 12.5' @ 10' R
Install 150' of MGS
Install Type E at departure end
3 | LT | 1.134 | 1.05 | TYPE E | TYPE E | 337.5 | Y, 72" PIPE W/ 2' OF COVER | 4' |  | 1.1364 | 1.05 | 387.5 | TYPE T | TYPE E | 260 | 150 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert
Lengthen approach end by 12.5'. Install Type T & wrap drive, 12.5' @ 15' R
Install 375' of MGS
Install Type E at departure end
4 | RT | 1.033 | 1.097 | TYPE E | TYPE T | 275 | Y, 72" PIPE W/ 2' OF COVER | 4' |  | 1.0212 | 1.097 | 375 | TYPE T | TYPE T | 260 | 150 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert. Lenghten approach end by 62.5'.
Install Type T at approach end & wrap drive, 12.5' @ 10' R.
Install 350'of MGS
LON on departure can not be met due to drive. Install Type T & wrap drive, 12.5' @ 10' R
5 | LT | 1.486 | 1.397 | TYPE E | TYPE E | 375 | Y, 96" PIPE W/ 2' OF COVER | 6' |  | 1.486 | 1.3923 | 437.5 | TYPE E | TYPE T | 240 | 130 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert
Install Type E at approach end
Install 425' of MGS
Lengthen departure end by 25'. Install Type T & wrap drive, 12.5' @ 15' R
6 | RT | 1.373 | 1.47 | TYPE E | TYPE E | 412.5 | Y, 96" PIPE W/ 2' OF COVER | 4' |  | 1.373 | 1.47 | 412.5 | TYPE E | TYPE E | 260 | 150 | 30 | 30 | CULVERT | CULVERT | YES |  | N | Omit 1 post at culvert
Install Type E at approach end
Install 412.5' of MGS
Install Type E at departure end
7 | LT | 2.56 | 2.404 | TYPE E | TYPE T | 762.5 | Y, 17.5' SPAN BOX CULVERT | 7' | BRIDGE LIC-62-02.39 | 2.56 | 2.404 | 725 | TYPE E | TYPE T | 230 | 120 | 30 | 30 | ??? | CULVERT | N, 50' LONG SPAN |  | N | Install 50' Long span at bridge. Remove 25' existing bridge rail.
Install Type E at approach end
Install 700' of MGS
Install Type T at departure end & wrap drive, 25' @ 8' R (due to long span)
8 | RT | 2.376 | 2.449 | TYPE T | TYPE E | 325 | Y, 17.5' SPAN BOX CULVERT | 5' | BRIDGE LIC-62-02.39 | 2.376 | 2.449 | 275 | TYPE T | TYPE E | 250 | 110 | 30 | 30 | CULVERT | CULVERT | N, 50' LONG SPAN |  | N | Install 50' Long span at bridge. Remove 25' existing bridge rail.
LON on approach can not be met due to drive. Install Type T & wrap drive, 12.5' @ 15' R
Install 262.5' of MGS
Install Type E at departure end
9 | LT | 2.904 | 2.797 | TYPE E | TYPE E | 462.5 | Y, 75" PIPE W/ 2' OF COVER | 5' |  | 2.904 | 2.797 | 462.5 | TYPE E | TYPE E | 250 | 140 | 30 | 30 |  |  | YES |  | N | Omit 1 post at culvert. (Replace in kind)
Install Type E at approach end
Install 462.5' of MGS
Install Type E at departure end
10 | RT | 2.828 | 2.888 | TYPE T | TYPE E | 250 | Y, 75" PIPE W/ 2' OF COVER | 4' |  | 2.828 | 2.888 | 250 | TYPE T | TYPE E | 260 | 150 | 30 | 30 |  |  | YES |  | N | LON on approach can not be met due to drive. Omit 1 post at culvert. (Replace in kind)
Install Type T at approach & wrap drive, 12.5' @ 20' R
Install 237.5' of MGS
Install Type E at departure end
11 | LT | 3.27 | 3.259 | BTA 4 | TYPE T | 25 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
12 | RT | 3.264 | 3.273 | TYPE T | BTA 4 | 25 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
13 | LT | 3.279 | 3.281 | TYPE T | BTA 4 | 0 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
14 | RT | 3.284 | 3.324 | BTA 4 | TYPE E | 137.5 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
15 | LT | 3.859 | 3.843 | BTA 1 | TYPE E | 12.5 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
16 | RT | 3.829 | 3.855 | TYPE E | BTA 1 | 62.5 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
17 | LT | 3.903 | 3.888 | TYPE E | BTA 1 | 12.5 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
18 | RT | 3.884 | 3.9 | BTA 1 | TYPE E | 12.5 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY
19 | LT | 5.945 | 5.912 | BTA 4 | TYPE T | 137.5 | 49' SPAN BRIDGE | 7' | BRIDGE LIC-62-05.95 | 5.945 | 5.912 | 137.5 | BTA 4 | TYPE T | - | 100 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 125' of MGS (transition height)
Install Type T at departure end & wrap drive, 12.5' @ 10' R
20 | RT | 5.914 | 5.945 | TYPE T | BTA 4 | 125 | 49' SPAN BRIDGE | 9' | BRIDGE LIC-62-05.95 | 5.914 | 5.945 | 125 | TYPE T | BTA 4 | 175 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 112.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 10' R
21 | LT | 5.996 | 5.955 | TYPE T | BTA 4 | 175 | 49' SPAN BRIDGE | 7' | BRIDGE LIC-62-05.95 | 5.996 | 5.955 | 175 | TYPE T | BTA 4 | 192 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 162.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 15' R
22 | RT | 5.956 | 5.98 | BTA 4 | TYPE E | 50 | 49' SPAN BRIDGE | 9' | BRIDGE LIC-62-05.95 | 5.956 | 5.98 | 50 | BTA 4 | TYPE E | - | 84 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 50' of MGS (transition height)
Install Type E at departure end
23 | LT | 8.49 | 8.43 | TYPE T | TYPE E | 250 | 12' SPAN BRIDGE W/ 1' OF COVER | 10' | BRIDGE LIC-62-08.45 | 8.49 | 8.43 | 200 | TYPE T | TYPE E | 167 | 75 | 30 | 30 | CULVERT | CULVERT | N, 43.75' LONG SPAN |  | N | Install 43.75' Long Span unit at culvert.
Install Type T at approach & wrap drive, 12.5' @ 15' R
Install 187.5' of MGS
Install Type E at departure end
24 | RT | 8.426 | 8.48 | TYPE T | TYPE E | 225 | 12' SPAN BRIDGE W/ 1' OF COVER | 6' | BRIDGE LIC-62-08.45 | 8.426 | 8.48 | 137.5 | TYPE E | TYPE E | 200 | 109 | 30 | 30 | CULVERT | CULVERT | N, 43.75' LONG SPAN |  | N | Install 43.75' Long Span unit at culvert.
Install Type E at approach end
Install 137.5' of MGS
Install Type E at departure end
25 | LT | 9.385 | 9.29 | TYPE E | TYPE E | 400 | Y, 72" PIPE W/ 3' OF COVER | 6' |  | 9.385 | 9.2782 | 462.5 | TYPE E | TYPE E | 200 | 109 | 30 | 30 |  | CULVERT | Y |  | N | Omit 1 post at culvert
Install Type E at approach end
Install 462.5' of MGS
Lenghten departure end by 62.5' to meet LON. Install Type E at departure end
26 | RT | 10.375 | 10.417 | TYPE E | TYPE T | 162.5 | Y, 60" PIPE W/ 2' OF COVER | 5' |  | 10.3726 | 10.417 | 175 | TYPE E | TYPE T | 209 | 117 | 30 | 30 | CULVERT | CULVERT | N |  | N | Watch post spacing at pipe. (Can't omit 1 post at departure)
Lenghten the approach end by 12.5' to meet LON. Install Type E
Install 162.5' of MGS
Can not meet LON on departure end due to drive. Install Type T & wrap drive, 12.5' @ 20' R
27 | LT | 10.57 | 10.522 | BTA 4 | TYPE E | 175 | 23' SPAN BOX CULVERT | 11' | BRIDGE LIC-62-10.57 | 10.57 | 10.522 | 175 | BTA 4 | TYPE E | - | 67 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 175' of MGS (transition height)
Install Type E at departure end
28 | RT | 10.475 | 10.57 | TYPE E | BTA 4 | 425 | 23' SPAN BOX CULVERT | 10' | BRIDGE LIC-62-10.57 | 10.475 | 10.57 | 425 | TYPE E | BTA 4 | 167 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 425' of MGS (transition height)
Install Type E at approach end
29 | LT | 10.605 | 10.581 | TYPE E | BTA 4 | 87.5 | 23' SPAN BOX CULVERT | 12' | BRIDGE LIC-62-10.57 | 10.605 | 10.581 | 112.5 | TYPE A | BTA 4 | 45 | - | 8 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 112.5' of MGS (transition height) & wrap side road
Install Type A at approach end (along side road)
30 | RT | 10.581 | 10.616 | BTA 4 | TYPE T | 150 | 23' SPAN BOX CULVERT | 8' | BRIDGE LIC-62-10.57 | 10.581 | 10.616 | 150 | BTA 4 | TYPE T | - | 92 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 125' of MGS (transition height)
Install Type T at departure end & wrap drive, 25' @ 20' R
31 | RT | 10.621 | 10.741 | TYPE T | TYPE T | 612.5 | N | 10' |  | 10.621 | 10.7386 | 562.5 | TYPE T | TYPE E | 167 | 75 | 30 | 30 |  |  | N |  | ?? | Install Type T at approach & wrap drive, 12.5' @ 15' R
Install 550' of MGS
Shorten departure end by 12.5' & Install Type E
32 | LT | 11.043 | 11.002 | BTA 4 | TYPE E | 137.5 | 48' SPAN BRIDGE | 12' | BRIDGE LIC-62-11.04 | 11.043 | 11.002 | 137.5 | BTA 4 | TYPE E | - | 59 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 137.5' of MGS (transition height)
Install Type E at departure end
33 | RT | 10.994 | 11.038 | TYPE E | BTA 4 | 150 | 48' SPAN BRIDGE | 9' | BRIDGE LIC-62-11.04 | 10.994 | 11.038 | 150 | TYPE E | BTA 4 | 175 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 150' of MGS (transition height)
Install Type E at approach end
34 | LT | 11.082 | 11.067 | TYPE T | BTA 4 | 50 | 48' SPAN BRIDGE | 12' | BRIDGE LIC-62-11.04 | 11.082 | 11.067 | 50 | TYPE T | BTA 4 | 150 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 37.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 10' R
35 | RT | 11.063 | 11.095 | BTA 4 | TYPE T | 137.5 | 48' SPAN BRIDGE | 9' | BRIDGE LIC-62-11.04 | 11.063 | 11.095 | 137.5 | BTA 4 | TYPE T | - | 84 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 125' of MGS (transition height)
Install Type T at departure end & wrap drive, 12.5' @ 10' R
36 | LT | 11.214 | 11.088 | TYPE E | TYPE T | 600 | N | 12' |  | 11.214 | 11.088 | 600 | TYPE E | TYPE T | 150 | 59 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 587.5' of MGS
Install Type T at departure & wrap drive, 12.5' @ 10' R
37 | LT | 11.496 | 11.409 | TYPE T | TYPE E | 400 | N | 10' |  | 11.496 | 11.409 | 400 | TYPE T | TYPE E | 167 | 75 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap drive, 12.5' @ 15' R
Install 387.5' of MGS
Install Type E at departure end
38 | RT | 11.385 | 11.478 | TYPE E | TYPE T | 437.5 | N | 6' |  | 11.385 | 11.478 | 437.5 | TYPE E | TYPE T | 200 | 109 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 412.5' of MGS
Install Type T at departure & wrap drive, 25' @ 20' R
39 | LT | 12.996 | 12.964 | BTA 4 | TYPE E | 87.5 | 55' SPAN BRIDGE | 11' | BRIDGE LIC-62-13.00 | 12.996 | 12.9474 | 87.5 | BTA 4 | TYPE E | - | 67 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 87.5' of MGS (transition height)
Install Type E at departure end
40 | RT | 12.961 | 13.002 | TYPE E | BTA 4 | 137.5 | 55' SPAN BRIDGE | 8' | BRIDGE LIC-62-13.00 | 12.961 | 13.002 | 137.5 | TYPE E | BTA 4 | 184 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 137.5' of MGS (transition height)
Install Type E at approach end
41 | LT | 13.075 | 13.025 | TYPE E | BTA 4 | 187.5 | 55' SPAN BRIDGE | 12' | BRIDGE LIC-62-13.00 | 13.075 | 13.025 | 187.5 | TYPE E | BTA 4 | 150 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 187.5' of MGS (transition height)
Install Type E at approach end
42 | RT | 13.031 | 13.064 | BTA 4 | TYPE E | 87.5 | 55' SPAN BRIDGE | 8' | BRIDGE LIC-62-13.00 | 13.031 | 13.064 | 87.5 | BTA 4 | TYPE E | - | 92 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 87.5' of MGS (transition height)
Install Type E at departure end
43 | RT | 13.215 | 13.323 | TYPE E | TYPE T | 512.5 | N | 8' |  | 13.2008 | 13.323 | 625 | TYPE T | TYPE T | 184 | 92 | 30 | 30 |  |  | N |  | N | Lenghten approach end by 75'. Install Type T & wrap drive, 12.5' @ 15' R
Install 600' of MGS
Install Type T at departure end & wrap drive, 12.5' @ 10' R
44 | LT | 13.94 | 13.886 | TYPE E | TYPE T | 200 | 13' SPAN BOX CULVERT, UNKNOWN COVER | 9' | BRIDGE LIC-62-13.89. No future bridge work anticipated | 13.9495 | 13.8694 | 312.5 | TYPE T | TYPE E | 175 | 84 | 30 | 30 |  |  | N, 43.75' LONG SPAN |  | N | Install 43.75' Long Span unit at culvert. Remove 18.75' of bridge railing
Lengthen approach end by 50' & Install Type T. Wrap drive, 12.5' @ 20' R.
Install 300' of MGS
Lenghten departure end by 87.5' to meet LON & Long Span requirements. Install Type E at departure end
45 | RT | 13.844 | 13.914 | TYPE E | TYPE E | 250 | 13' SPAN BOX CULVERT, UNKNOWN COVER | 8' | BRIDGE LIC-62-13.89. No future bridge work anticipated | 13.844 | 13.914 | 225 | TYPE E | TYPE E | 184 | 92 | 30 | 30 |  |  | N, 43.75' LONG SPAN |  | N | Install 43.75' Long Span unit at culvert. Remove 18.75' of bridge railing
Install Type E at approach end
Install 225' of MGS
Install Type E at departure end
46 | RT | 14.334 | 14.392 | TYPE T | TYPE T | 287.5 | N | 6' |  | 14.334 | 14.392 | 287.5 | TYPE T | TYPE T | 200 | 109 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap field drive, 12.5' @ 10' R
Install 262.5' of MGS
Install Type T at departure & wrap drive, 12.5' @ 10' R
47 | LT | 15.391 | 15.366 | TYPE T | TYPE T | 100 | 21' SPAN BOX CULVERT | 10' | BRIDGE LIC-62-15.37 | 15.391 | 15.366 |  |  |  | - | 63 | - | 30 |  |  | N |  |  | NO FUTURE BRIDGE WORK PLANNED
SKIP RUN, CAN NOT DO LONG SPAN OR MGS DUE TO DRIVEWAY
48 | RT | 15.358 | 15.395 | TYPE T | TYPE E | 112.5 | 21' SPAN BOX CULVERT | 12' | BRIDGE LIC-62-15.37 | 15.358 | 15.395 | 87.5 | TYPE T | TYPE E | 126 | - | 30 | - |  |  | N, 50' LONG SPAN |  |  | NO FUTURE BRIDGE WORK PLANNED
Install 50' Long Span unit at culvert. Remove 25' of existing bridge railing
Install 87.5' of MGS
Install Type T at approach & wrap drive, 12.5' @ 20' R
49 | RT | 15.834 | 15.91 | TYPE T | TYPE E | 350 | N | 9' |  | 15.834 | 15.91 | 350 | TYPE T | TYPE E | 147 | 70 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap field drive, 12.5' @ 10' R
Install 337.5' of MGS
Install Type E at departure end
50 | LT | 16.177 | 16.297 | TYPE T | TYPE E | 587.5 | N | 10' |  | 16.177 | 16.297 | 625 | TYPE T | TYPE T | 138 | 86 | 39 | 39 |  |  | N |  | N | Install Type T at approach & wrap field drive, 12.5' @ 10' R
Install 600' of MGS
Install Type T at departure & wrap drive, 12.5' @ 20' R
51 | RT | 16.189 | 16.293 | TYPE E | TYPE E | 450 | N | 9' |  | 16.189 | 16.293 | 450 | TYPE E | TYPE E | 147 | 70 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 450' of MGS
Install Type E at departure end
52 | LT | 17.654 | 17.799 | TYPE E | TYPE T | 712.5 | N | 8' |  | 17.654 | 17.799 | 712.5 | TYPE E | TYPE T | 154 | 77 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 700' of MGS
Install Type T at departure & wrap drive, 12.5' @ 15' R
53 | RT | 17.64 | 17.81 | TYPE E | TYPE E | 800 | N | 7' |  | 17.6353 | 17.81 | 862.5 | TYPE T | TYPE E | 161 | 84 | 30 | 30 |  |  | N |  | N | Lenghten approach end by 25'. Install Type T & wrap drive, 12.5' @ 20' R
Install 850' of MGS
Install Type E at departure end
54 | LT | 18.096 | 18.194 | TYPE T | TYPE T | 512.5 | N | 7' |  | 18.096 | 18.194 | 512.5 | TYPE T | TYPE T | 161 | 84 | 30 | 30 |  |  | N |  | N | Install Type T at approach & wrap drive, 12.5' @ 10' R
Install 487.5' of MGS
Install Type T at departure & wrap drive, 12.5' @ 15' R
55 | LT | 18.245 | 18.386 | TYPE A | TYPE E | 700 | N | 7' |  | 18.245 | 18.386 | 700 | TYPE A | TYPE E | 10 | 84 | 8 | 30 |  |  | N |  | ?? | Install Type A at approach end (on side road)
wrap LIC-62, 37.5' @ 25' R.
Install 662.5' of MGS
Install Type E at departure end
56 | LT | 18.392 | 18.401 | BTA 4 | TYPE A | 50 | BRIDGE | 7' | BRIDGE LIC-62-18.45 | 18.392 | 18.401 | 37.5 | BTA 4 | TYPE T | - | 84 | - | 30 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
[14 empty] | TYPE A | [9 empty] | Install 37.5' of MGS (transition height) & wrap side road
Install Type A at departure end (along side road)
57 | RT | 18.395 | 18.406 | TYPE E | BTA 4 | 62.5 | BRIDGE | 7' | BRIDGE LIC-62-18.45 | 18.395 | 18.406 | 87.5 | TYPE A | BTA 4 | 149 | - | 36 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 87.5' of MGS (transition height) & wrap side road
Install Type A at approach end (along side road)
58 | LT | 18.477 | 18.444 | TYPE E | BTA 4 | 100 | BRIDGE | 8' | BRIDGE LIC-62-18.45 | 18.477 | 18.444 | 187.5 | TYPE T | BTA 4 | 154 | - | 30 | - |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
Remove existing BTA 4 & replace with new BTA 4
Install 187.5' of MGS (transition height)
Install Type T at approach end & wrap drive, 12.5' @ 15' R.
59 | RT | 18.45 | 18.461 | BTA 4 | TYPE T | 12.5 | BRIDGE | 8' | BRIDGE LIC-62-18.45 | [5 empty] | - | 88 | - | 36 |  |  | N |  | N | NO FUTURE BRIDGE WORK PLANNED
SKIP RUN, CAN NOT DO LONG SPAN OR MGS DUE TO DRIVEWAY
60 | LT | 18.891 | 18.72 | BTA TST | TYPE E | 912.5 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
61 | RT | 18.721 | 18.893 | TYPE E | BTA TST | 912.5 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
62 | LT | 19.049 | 18.928 | TYPE E | BTA TST | 650 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
63 | RT | 18.928 | 19.045 | BTA TST | TYPE E | 625 | BRIDGE | [16 empty] | SKIP. OWNED BY MUNICIPALITY & RAIL IS MGS
64 | RT | 19.287 | 19.321 | TYPE T | TYPE E | 125 | [17 empty] | SKIP. OWNED BY MUNICIPALITY
65 | LT | 19.447 | 19.384 | TYPE E | TYPE E | 225 | [17 empty] | SKIP. OWNED BY MUNICIPALITY
66 | RT | 19.356 | 19.469 | TYPE E | TYPE T | 537.5 | [17 empty] | SKIP. OWNED BY MUNICIPALITY
67 | LT | 19.767 | 19.603 | TYPE E | TYPE A | 800 | N | 9' |  | 19.767 | 19.603 | 812.5 | TYPE E | TYPE A | 147 | 70 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 762.5' of MGS
Wrap side road, 50' @ 60' R
Lengthen departure by 12.5' & Install Type A (on side road)
68 | RT | 19.613 | 19.685 | TYPE T | TYPE T | 362.5 | N | 7' |  | 19.613 | 19.685 | 362.5 | TYPE T | TYPE T | 161 | 84 | 30 | 30 |  |  | N |  | ?? | Install Type T at approach end & wrap drive, 12.5' @ 10' R
Install 337.5' of MGS
Install Type T at departure end & wrap drive, 12.5' @ 15' R
69 | LT | 20.265 | 20.214 | TYPE E | TYPE E | 162.5 | N | 7' |  | 20.265 | 20.214 | 162.5 | TYPE E | TYPE E | 161 | 84 | 30 | 30 |  |  | N |  | N | Install Type E at approach end
Install 162.5' of MGS
Install Type E at departure end

## ESTIMATE - RUNS 1-5 (hidden)
Item No. | Description | Quantity | Unit | Unit Price | Total | ESTIMATE FOR GR RUNS 1 - 5 ONLY
ROADWAY
202E38000 | Guardrail Removed | 2212.5 | FT | 1.75 | 3871.875
202E42010 | Anchor Assembly Removed, Type E | 1 | EA | 165 | 165
202E42040 | Anchor Assembly Removed, Type T | 9 | EA | 110 | 990
606E15100 | Guardrail, Type MGS w/ Long Posts | 2175 | FT | 23 | 50025
606E26150 | Anchor Assembly MGS, Type E | 1 | EA | 2700 | 2700
606E26550 | Anchor Assembly MGS, Type T | 9 | EA | 1160 | 10440
606E50000 | Reshaping Berm | 2337.5 | FT | 0.3 | 701.25
690E50350 | Mailbox Removed & Reset | 4 | EA | 75 | 300
|  |  |  | SUB-TOTAL | 69193.125
TRAFFIC CONTROL
626E00110 | Barrier Reflector, Type 2, Bi-Directional | 31.75 | EA | 9 | 285.75
630E03100 | Ground Mounted Support, No. 3 Post | 60 | FT | 10 | 600
630E85100 | Removal of Ground Mounted sign & Reerection | 4 | EA | 35 | 140
|  |  |  | SUB-TOTAL | 1025.75
EROSION CONTROL
203E20001 | Embankment | 45 | CY | 60 | 2700
659E00510 | Seeding & Mulching, Class 2 | 50 | SY | 1.5 | 75
659E20000 | Commercial Fertilizer | 0.0067476 | Ton | 650 | 4.386
659E31000 | Lime | 0.010331 | Acre | 150 | 1.5496
659E35000 | Water | 0.27 | Mgal | 2 | 0.54
670E00500 | Slope Erosion Protection | 50 | SY | 2 | 100
|  |  |  | SUB-TOTAL | 2881.4756
INCIDENTALS
614E11000 | Maintaining Traffic | 1 | LS | 1462.007 | 1500
623E10001 | Construction Layout Stakes & Surveying | 1 | LS | 731.0035 | 800
624E10000 | Mobilization | 1 | LS | 2193.0105 | 2200
|  |  |  | SUB-TOTAL | 4500
|  |  |  | TOTAL= | 77600.3506
| 102492 CONSTRUCTION COSTS | 1472424.25 |  | % of construction costs
USE:
| Maintaining Traffic | 25000 | = | 1.698% | 2%
| Construction Layout Stakes & Surveying | 15000 | = | 1.019% | 1%
| Mobilization | 40000 | = | 2.717% | 3%

## Prelim Estimate (hidden)
GR Run | Side | SLM start | SLM end | Approach Unit | Departure Unit | Rail Length | Item No. | Description | Quantity | Unit | Unit Price | Total
ROADWAY
1 | Left | 19.833 | 19.77 | Type T | Type T | 300 | 202E38000 | Guardrail Removed | 16350 | FT | 1.75 | 28612.5
2 | Right | 19.777 | 19.861 | Type T | Type T | 400 | 202E42000 | Anchor Assembly Removed, Type A | 69 | EA | 300 | 20700
3 | Left | 19.881 | 19.842 | Type E (SKT) | Type T | 150 | 202E42010 | Anchor Assembly Removed, Type E | 4 | EA | 165 | 660
4 | Left | 20.119 | 19.99 | Type T | Type T | 637.5 | 202E42040 | Anchor Assembly Removed, Type T | 19 | EA | 110 | 2090
5 | Right | 19.988 | 20.121 | Type T | Type T | 675 | 202E47000 | Bridge Terminal Assembly Removed | 0 | EA | 100 | 0
6 | Left | 20.617 | 20.556 | Type T | Type A | 300
7 | Right | 20.567 | 20.617 | Type A | Type T | 237.5 | 606E15100 | Guardrail, Type MGS w/ Long Posts | 16350 | FT | 23 | 376050
8 | Right | 20.655 | 20.726 | Type A | Type A | 325 | 606E26150 | Anchor Assembly MGS, Type E | 73 | EA | 2700 | 197100
9 | Left | 20.737 | 20.676 | Type A | Type A | 275 | 606E26550 | Anchor Assembly MGS, Type T | 19 | EA | 1160 | 22040
10 | Left | 21.552 | 21.522 | Type A | Type A | 100 | 606E5000 | Reshaping Berm | 20237.5 | FT | 0.3 | 6071.25
11 | Right | 21.538 | 21.555 | Type T | Type A | 75 | 626E00110 | Barrier Reflector, Type 2, Bi-Directional | 260 | EA | 9 | 2340
16 | Right | 23.759 | 23.796 | Type A | Type A | 150
17 | Left | 23.813 | 23.77 | Type A | Type A | 175 |  |  |  |  | SUB-TOTAL | 647252.5
18 | Right | 23.914 | 23.89 | Type A | Type A | 75
19 | Right | 23.973 | 23.92 | Type A | Type A | 237.5 |  | EROSION CONTROL
20 | Right | 24.09 | 24.016 | Type A | Type A | 350 | 203E20001 | Embankment | 3285 | CY | 60 | 197100
25 | Left | 25.336 | 25.315 | Type T | Type A | 100 | 659E00510 | Seeding & Mulching, Class 2 | 3650 | SY | 1.5 | 5475
26 | Right | 25.32 | 25.375 | Type A | Type A | 250 | 659E20000 | Commercial Fertilizer | 0.49258 | Ton | 650 | 320.1754
27 | Left | 25.574 | 25.555 | Type T | Type A | 75 | 659E31000 | Lime | 0.75413 | Acre | 150 | 113.1198
28 | Right | 25.556 | 25.584 | Type A | Type A | 100 | 659E35000 | Water | 19.71 | Mgal | 2 | 39.42
29 | Left | 25.757 | 25.719 | Type A | Type A | 150 | 670E00500 | Slope Erosion Protection | 3650 | SY | 2 | 7300
30 | Right | 25.71 | 25.76 | Type A | Type T | 250 | 832E3000 | Erosion Control | 1 | EA | 2000 | 2000
31 | Right | 25.764 | 25.829 | Type T | Type A | 325
32 | Right | 26.548 | 26.599 | Type A | Type A | 212.5 |  |  |  |  | SUB-TOTAL | 212347.7153
33 | Left | 26.607 | 26.559 | Type A | Type A | 200
34 | Right | 27.073 | 27.297 | Type A | Type A | 1137.5 |  | INCIDENTALS
35 | Left | 27.24 | 27.085 | Type A | Type A | 775 | 614E11000 | Maintaining Traffic | 1 | LS | 14594.982 | 15000
36 | Left | 27.551 | 27.477 | Type A | Type A | 337.5 | 623E10001 | Construction Layout Stakes & Surveying | 1 | LS | 8756.9892 | 10000
37 | Left | 27.638 | 27.618 | Type T | Type A | 75 | 624E10000 | Mobilization | 1 | LS | 23351.9712 | 25000
42 | Right | 28.456 | 28.477 | Type A | Type A | 62.5
43 | Right |  |  | Type T | Type A | 212.5 | 630E03100 | Ground Mounted Support, No. 3 Post |  | FT |  | 8000
44 | Right | 29.404 | 29.443 | Type A | Type A | 200 | 630E85100 | Removal of Ground Mounted sign & Reerection |  | EA |  | 2000
45 | Right | 29.526 | 29.629 | Type A | Type A | 437.5 | 690E50350 | Mailbox Removed & Reset |  | EA |  | 1000
46 | Right | 29.649 | 29.783 | Type A | Type A | 600
47 | Left | 30.13 | 30.076 | Type A | Type A | 250 |  |  |  |  | SUB-TOTAL | 61000
48 | Right | 30.074 | 30.123 | Type A | Type A | 212.5
53 | Right | 30.616 | 30.823 | Type A | Type A | 1037.5 |  |  |  |  | TOTAL= | 920600.2153
54 | Left | 31.206 | 30.991 | Type A | Type A | 1075
55 | Left | 31.353 | 31.301 | Type T | Type E (ET-Plus) | 212.5
56 | Right | 31.292 | 31.369 | Type E (ET-Plus) | Type E (ET-Plus) | 300 |  | 102492: |  |  | 117544
57 | Right | 31.453 | 31.484 | Type A | Type A | 112.5 |  | PROJECT COSTS PER LF OF RAIL INSTALLED | 39.3891 | = | 797137.6025
66 | Left | 32.888 | 32.608 | Type A | Type A | 1437.5
67 | Right | 32.766 | 32.871 | Type A | Type A | 500 |  | 102492 CONSTRUCTION COSTS | 1472424.25 |  | Percentage of construction costs
68 | Left | 33.622 | 33.494 | Type A | Type A | 625 |  | Maintaining Traffic | 25000 | = | 1.698%
69 | Left | 34.392 | 34.314 | Type A | Type A | 362.5 |  | Construction Layout Stakes & Surveying | 15000 | = | 1.019%
70 | Right | 34.311 | 34.371 | Type A | Type A | 262.5 |  | Mobilization | 40000 | = | 2.717%
[6 empty] | 16350 |  | Ground Mounted Support, No. 3 Post | 12000 | = | 0.815%
[8 empty] | Removal of Ground Mounted sign & Reerection | 2555 | = | 0.1735%
[8 empty] | Mailbox Removed & Reset | 1425 | = | 0.09678%