## Sheet1
WINDOW CONTRACT TABLE
DESCRIPTION OF CRITICAL WORK | CALENDAR DAYS TO COMPLETE | DISINCENTIVE $ PER DAY | WORK WINDOW
|  |  | START | END
CLOSURE OF U.S. 20 FOR CONSTRUCTION OF IMPROVEMENTS | 25 | 5000 | AT CONTRACT EXECUTION | 2026-11-15