## Utility Coordination Log
GPD Group, Utility Coordination Services Log
GPD Group, Utility Coordination Services Project Number: |  | 2019254 |  | Project Name: |  |  | GEA-306-4.45 | Date for OUPS Contact: | 2019-09-20
Project Manager: |  | Mark Grossman |  | Project Folder Location: |  |  | O:\2019\2019254\GEA\99694
Utility Company, Name & Address, Phone Number, & Email Address | Utility Contact Representative, Phone Number, & Email Address | OUPS Ticket Number | Date Positive Response Received | Date Plans Requested / Received | Hyperlink to Utility Company Plan Folder | Remarks
Windstream Ohio, 245 N. Main Street, Hudson, OH, 44236, (216) 385-1669, windstreamprs@korweb.com | Jeff Gulyas, (216) 385-1669 | A926301329/A926301339 | 2019-10-02 | 2019-10-02 | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\Fiber\Windstream | Automatic response generated by Windstream; No plans received; Sent copy of Stage 1 plans on 10/16/19; Sent copy of Stage 2 plans on 1/06/20; Sent copy of Stage 3 plans on 3/20/20; Sent copy of Final Tracings plans on 5/18/20
Dominion Energy Ohio, 320 Springside Drive, Suite 320, Akron, OH 44333, (330) 664-2409 | Kevin Birt, (330) 664-2409 | A926301329/A926301339 | 2019-09-23 | 2019-09-23 | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\Gas\Dominion Energy | Letter and Map of utilities received; Sent copy of Stage 1 plans on 10/16/19; Received a letter from John Meerdink of Dominion Energy Ohio stating that Dominion has facilities in conflict with the proposed work and a list of conflicts on 12/4/19. Sent copy of Stage 2 plans on 1/06/20; Received e-mail from John Meerdink of Domion Energy Ohio containing a response letter to Stage 2 plans and list of conflicts with proposed work on 1/16/20; Sent copy of Stage 3 plan on 3/20/20; Sent copy of Final Tracings plans on 5/18/20
ODOT - District 12, 5500 Transportation Blvd, Garfield Heights, OH 44125, (216) 581-2100 | Keith Hamilton, (216) 581-2100 | A926301329/A926301339 | 2019-09-24 | 2019-09-24 | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\ODOT | Plans provided by Curtis Wills of ODOT-District 12; Sent copy of Stage 1 plans on 10/16/19; Sent copy of Stage 2 plans on 1/06/20; Sent copy of Stage 3 plans on 3/20/20; Sent copy of Final Tracings plans on 5/18/20
Geauga County Water Resources, 470 Center Street, Bldg. 3, Chardon, OH 44024, (440) 279-1970 | Steve Oluic, (440) 279-1970 | A926301329/A926301339 | 2019-09-20 | 2019-09-20 | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\Sanitary | Plans provided by Rob Edmonds of Geauga County Water Resources; Sent copy of Stage 1 plans on 10/16/19; Sent copy of Stage 2 plans on 1/06/20; Received plans from Brien Croff of Geauga County Water Resources on 1/9/20; Sent copy of Stage 3 plans on 3/20/20; Sent copy of Final Tracings plans on 5/18/20
CEI First Energy, 6896 Miller Road, Brecksville, OH 44141, (440) 546-8706 | John Zassick, (440) 546-8706 | A926301329/A926301339 | 2019-10-21 |  | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\Electric\CEI - First Energy | Stage 1 Plans originally sent to Frederick Randolph, CEI First Energy, 7755 Auburn Road, Painesville, OH 44077 on 10/16/19; Forwarded by Frederick Randolph to John Zassick; Request for future submittals to be made to John Zassick; Request for design changes from John Zassick (see CEI - First Energy folder in Utilities Directory for details); Sent copy of Stage 2 plans on 1/06/20; Received a response letter in regards to the Stage 2 plans from John Zassick of CEI First Energy indicating location of underground electric; Sent copy of Stage 3 plans on 3/20/20; Sent copy of Final Tracings plans on 5/18/20
Bainbridge Township Service Department, 17800 Haskins Road, Chagrin Falls, OH 44023, (440) 543-9871 | Jim Stanek, (440) 543-9871 | A926301329/A926301339 |  |  |  | Sent copy of Stage 1 plans on 10/16/19; Sent copy of Stage 2 plans on 1/06/20; Sent copy of Stage 3 plans on 3/20/20; Sent copy of Final Tracings plans on 5/18/20
Charter Communications, 7820 Division Drive, Mentor, OH 44060, (216) 575-8016 | Emil Symister, (216) 575-8016 | A926301329/A926301339 |  |  | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\Cable | Sent copy of Stage 1 plans on 10/16/19; Sent copy of Stage 2 plans on 1/06/20; Sent copy of Stage 3 plans on 3/20/20; Sent copy of Final Tracings plans on 5/18/20
Everstream Solutions, 1228 Euclid Avenue, Suite 250, Cleveland, Oh 44115, (216) 923-2206 | Sarah Hatfield, (216) 923-2206 | A926301329/A926301339 |  |  | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\Fiber\Everstream | Sent copy of Stage 1 plans on 10/16/19; Received an email from Rob Wood of Everstream on Oct. 28, 2019 indicating that they do not have any facilities affected by the work
AT&T, 13630 Lorain Avenue, 2nd Floor, Cleveland, OH 44111, (216) 476-6142 | James Janis, (216) 476-6142 | A926301329/A926301339 | 2019-11-26 |  | O:\2019\2019254\GEA\99694\Design\Utilities\OUPS_Information\Telephone | Sent copy of Stage 1 plans on 11/22/19; Received response from Scott Klebe of AT&T indicating they have no facilities within the project area.