## Sheet1
Portable Changeable Sign Months
Construction duration |  |  | 9 | months
|  |  | 3 | months at each bridge
HAM-71-0226 | Sign 1 | Sign 2 | Sign 3 | Sign 4 | Sign 5
I-71 |  |  |  |  | 3
NB Entrance - Gilbert | 0.75
NB Entrance - I-471 |  | 0.375
NB Exit - US 42/Reading/Eden Park | 0.75
SB Entrance - US42/Reading/Eden Park | 0.75
Elsinore - WB |  |  | 3
Elsinore - EB |  |  |  | 3
Totals | 2.25 | 0.375 | 3 | 3 | 3 | USE | 12
HAM-71-0294 | Sign 1 | Sign 2 | Sign 3 | Sign 4 | Sign 5
I-71 |  |  |  |  | 3
NB Entrance - Reading Road | 0.375
SB Exit - US42/Reading | 0.75
SB Exit - Gilbert | 0.375
McGregor - WB |  |  | 3
McGregor - EB |  |  |  | 3
Totals | 1.5 | 0 | 3 | 3 | 3 | USE | 11
HAM-71-0344 | Sign 1 | Sign 2 | Sign 3 | Sign 4 | Sign 5
I-71 |  |  |  |  | 3
NB Entrance - McMillan | 0.75
SB Exit - Taft | 0.375
SB Entrance - MLK | 0.75
Oak - WB |  |  | 3
Oak - EB |  |  |  | 3
Totals | 1.875 | 0 | 3 | 3 | 3 | USE | 11
ASSUMPTIONS:
Outside lane closure will be closed for at least 1/4 of construction time (both single and 2-lane closures)
Inside lane closure will only be closed for 1/8 of construction time during 2-lane closures only