## Stage 1 Coordination
Utility Contact and Coordination |  | Updated: 7/11/2023
HAM Inverts FY2025
Company | Contact Info | Stage 1 plans sent 5/12/2023
Duke Energy Gas | Denise Gross | Plans Sent to OH/KYHouseBill@duke-energy.com | 2023-05-12
| 139 East 4th St., Room 460A |  | Erhart, Shane Michael <Shane.Erhart@duke-energy.com>
| Cincinnati, OH 45202 |  | No Conflict
513-287-2532 (Denise Gross)
Denise.Gross@duke-energy.com
Altafiber | Breck Cowan | Plans sent to breck.cowan@altafiber.com & kevin.clapp@altafiber.com | 2023-05-15
| 221 E 4th Street (Building 205-120) |  | Cowan, Breck <breck.cowan@altafiber.com>
| Cincinnati, OH 45202 |  | No UG involvment and no aerial conflicts
(513)565-7187 – Office
breck.cowan@altafiber.com
Greater Cincinnati Water Works | Michael Cossins | Plans sent to Michael.Cossins@gcww.cincinnati-oh.gov | 2023-05-17
| 4747 Spring Grove Avenue |  | Michael Cossins <Michael.Cossins@gcww.cincinnati-oh.gov>
| Cincinnati, OH 45232 |  | No Conflict
| 513-591-6581 (Michael Cossins) |  | GCWW HAM-110633-Stage1.pdf
Michael.Cossins@gcww.cincinnati-oh.gov
Charter Communications | Kent Reiger | Plans Sent to DL-Southern-Ohio-Outside-Plant@charter.com | 2023-05-16
| 10920 Kenwood Road |  | Kent Rieger <kent.rieger@charter.com>
| Blue Ash, Ohio 45242 |  | No Involvement
513-386-5499 (Kent Rieger)
kent.rieger@charter.com
ODOT District 8 Traffic | Teri Scanlon | Plans sent to teri.scanlon@dot.ohio.gov | 2023-05-15
| 505 South SR741 |  | Teri Scanlon <teri.scanlon@dot.ohio.gov>
| Lebanon, Ohio 45036 |  | The I-75 and HAM-50 locations have highway lighting in the vicinity of the work.
| 513-933-6620 (Teri Scanlon) |  | but impacts could be possible due to contractors accessing the work sites. Plans will need to address this if any cable or light poles are impacted.
| teri.scanlon@dot.ohio.gov |  | The I-75 lighting is maintained by ODOT and the HAM-50 lighting is maintained by either Cincinnati or Fairfax.

## Stage 2 Coordination
Utility Contact and Coordination |  | Updated: 11/11/2022
BUT SR 4 23.17
Company | Contact Info | Stage 2 plans sent
Duke Energy Electric - Distribution | Chris Tepe | Plans sent to Chris.Tepe@Duke-Energy.com
2010 Dana Ave
Cincinnati, OH 45207
513-514-8209 (Chris Tepe)
Chris.Tepe@Duke-Energy.com
Duke Energy Electric - Transmission | Tim Meyer | Plans sent to Tim.Meyer@duke-energy.com
139 E. 4th St, Rm 552A
Cincinnati, OH 45202
513-287-1266 (Tim Meyer)
Tim.Meyer@duke-energy.com
Duke Energy Gas | Denise Gross | Plans Sent to OH/KYHouseBill@duke-energy.com
139 East 4th St., Room 460A
Cincinnati, OH 45202
513-287-2532 (Denise Gross)
Denise.Gross@duke-energy.com
AT&T Ohio | Alan Stutes | Plans sent to AS1634@att.com
7201 Far Hills Ave.
Dayton Ohio 45459
937-708-1026 (Alan Stutes)
AS1634@att.com
Southwest Regional Water District | Tom Puckett | Plans sent to Puckettt@swwater.org
3640 Old Oxford Highway
Hamilton, OH 45013
513-863-0828 (Tom Puckett)
Puckettt@swwater.org
Charter Communications | Kent Reiger | Plans Sent to DL-Southern-Ohio-Outside-Plant@charter.com
10920 Kenwood Road
Blue Ash, Ohio 45242
513-386-5499 (Kent Rieger)
kent.rieger@charter.com
Metropolitan Communications Group | Chad Harkness | Plans sent to ps4364@att.com
155 Commerce Park Drive, Suite 1
Westerville, Ohio 43082
614-392-2873 (Chad Harkness)
ps4364@att.com
CCSI Networks, LLC | Tim Lapointe | Plans sent to TL0695@ATT.COM
2649 Gardner Rd
Broadview, Illinois 60155
713-830-7437 (Tim Lapointe)
TL0695@ATT.COM
Butler County Engineer's Office | Mark Conner | Plans sent to Connerm@bceo.org
1921 Fairgrove Ave
Hamilton, OH 45011
513-785-4134 (Mark Conner)
Connerm@bceo.org

## Stage 3 Coordination
Utility Contact and Coordination |  | Updated: 11/11/2022
BUT SR 4 23.17
Company | Contact Info | Stage 3 plans sent
Duke Energy Electric - Distribution | Chris Tepe | Plans sent to Chris.Tepe@Duke-Energy.com
2010 Dana Ave
Cincinnati, OH 45207
513-514-8209 (Chris Tepe)
Chris.Tepe@Duke-Energy.com
Duke Energy Electric - Transmission | Tim Meyer | Plans sent to Tim.Meyer@duke-energy.com
139 E. 4th St, Rm 552A
Cincinnati, OH 45202
513-287-1266 (Tim Meyer)
Tim.Meyer@duke-energy.com
Duke Energy Gas | Denise Gross | Plans Sent to OH/KYHouseBill@duke-energy.com
139 East 4th St., Room 460A
Cincinnati, OH 45202
513-287-2532 (Denise Gross)
Denise.Gross@duke-energy.com
AT&T Ohio | Alan Stutes | Plans sent to AS1634@att.com
7201 Far Hills Ave.
Dayton Ohio 45459
937-708-1026 (Alan Stutes)
AS1634@att.com
Southwest Regional Water District | Tom Puckett | Plans sent to Puckettt@swwater.org
3640 Old Oxford Highway
Hamilton, OH 45013
513-863-0828 (Tom Puckett)
Puckettt@swwater.org
Charter Communications | Kent Reiger | Plans Sent to DL-Southern-Ohio-Outside-Plant@charter.com
10920 Kenwood Road
Blue Ash, Ohio 45242
513-386-5499 (Kent Rieger)
kent.rieger@charter.com
Metropolitan Communications Group | Chad Harkness | Plans sent to ps4364@att.com
155 Commerce Park Drive, Suite 1
Westerville, Ohio 43082
614-392-2873 (Chad Harkness)
ps4364@att.com
CCSI Networks, LLC | Tim Lapointe | Plans sent to TL0695@ATT.COM
2649 Gardner Rd
Broadview, Illinois 60155
713-830-7437 (Tim Lapointe)
TL0695@ATT.COM
Butler County Engineer's Office | Mark Conner | Plans sent to Connerm@bceo.org
1921 Fairgrove Ave
Hamilton, OH 45011
513-785-4134 (Mark Conner)
Connerm@bceo.org