## Sheet1
Utility Contact and Coordination |  | Updated: | Updated: 4.3.24 | Utility Conflicts | Updated: | Updated: | Utility Conflicts | Updated: | Updated: | Updated: | Updated:
PID 116550 - Plainfield Rd and Montgomery Rd |  |  |  | and resolution |  |  | and resolution
Company | Contact Info | Stage 1 plans sent: | Stage 1 responded | Conflicts | Stage 2 plans sent: | Stage 2 responded | Conflicts | Stage 2 Repeat responded | Stage 3 plans sent: | Stage 3 responded | Final Plans
Electric - Duke Energy | 7600 Colerain Ave Cincinnati, OH 45207 Nicholas Hamilton (513) 240-8825 Nicholas.Hamilton@duke-energy.com | Stage 1 plans sent on 3/11 |  | Per the Village's request, Duke is looking into the feasibility of relocation aerial electric and comm underground. A meeting was held with Nick Hamilton on 2/19/24 and he stated that he would provide a cost estimate by 3/1. Once this estimate is received, the Village will determine if they want to move forward with this work. It is decided that utilties wil remain aerial. No underground relocation is proposed. Nick Hamilton has provided preliminary poles relocations but is working on final plans. | 2024-08-12 |  | Coordination between TEC and Nick Hamilton has been taking place since Stage 1. Nick sent proposed pole locations which has been incorporated into the plans. Discussion started on 10/16/24 regarding digging near poles. Since the pavement buildup is still under review, affected poles have not been determined. |  | 2025-02-03 |  | Tony Painter and Kellie discussed pole options on 9/25/25. Tony notified TEC that a RR permit would be required to make the necessary changed. TEC estimated that this would not disrupt construction and Duke will proceed with obtaining a permit. | Mitch Ebernez and Tony Dickson responded with pr lighting locations and plans on 10/30/25 | Duke is relocating more poles than previously mentioned per meeting on 1/9/26. Plans have been updated to specify which poles are being moved. They also indicated that some poles are owned by Altafiber.
Electric - Duke Energy (Distribution) | 2010 DANA AVE., CINCINNATI, OHIO 45207 CHRIS TEPE (513) 514-8209 CHRIS.TEPE@DUKE-ENERGY.COM | Plans will be sent to Elec/Comm companies once the decision to move underground or stay aerial has been made | 3/27/24 Tim Meyer No conflicts are anticipated between Duke Energy’s electric transmission line that runs along Blue Ash Road and the work to be performed according to the Stage 1 plans. Thank you for the chance to review and please include me in correspondence at Stage 2, Stage 3, and Final. A screenshot showing the location of Duke Energy’s 138kv poles (shown in green) is attached for reference | Correspondence with Chris Tepe 4.3.24:" I am seeing three poles that are in the proposed roadway.Sta. 305+88, 11’Rt. Existing pole inside of proposed roadway. Sta. 306+53, 12’Rt. Existing pole inside of proposed roadway. Sta. 309+2, 16’Rt. Existing pole inside of proposed roadway. Sta. 320+43, 23’Rt. This pole at the corner of North Ave. @ Plainfield Rd. appears it may be shown in the wrong location. I believe the existing pole in the field is may actually be inside of the proposed access ramp. Can this be reviewed to make sure our pole isn’t in the ramp?" Kellie responded and informed Tim, that decisions have not yet been made on relocating overhead vs underground. |  |  | Duke email TEC on 6/14/24 stating that Nick Hamilton will be handling this project. See comments above regarding coordiation with Nick. |  | 2025-02-03
Gas - Duke Energy | 139 E. FOURTH ST., RM 460A CINCINNATI, OHIO 45202 MARK BRANSCUM (513) 287 - 2517 MARK.BRANSCUM@DUKE-ENERGY.COM OH/KYHOUSEBILL@DUKE-ENERGY.COM | Stage 1 plans sent on 3/11 | [6 empty] | 2025-02-03 | Gas potholed a few areas to determine more accurate depths in June 2025. |  | TEC has been in contact with Duke Gas (Andy McNichols) about the undercut so close to the gas main. There has been no definitive answer from Duke on how to address this. | Andy called on 1/13 and doesn't believe gas will be an issue. The 8" main gets shallow so there was concern but he is looking at approval to abandon the main. He will follow up but says that our plans are good as shown.
Sanitary - Metropolitan Sewer District | 1600 GEST ST. CINCINNATI, OHIO 45204 ROB FRANKLIN (513) 882-8468 MSDUTILITYREVIEW@CINCINNATI-OH.GOV | Stage 1 plans sent on 3/11 | Rob responded on 3/14 -He requested some formatting changed -He requested we super elevate the road to avoid CBs on one side -He stated some laterals were missing -Plans will be updated and sent back for his review | Where the catch basins are going to be constructed over sewers, encasement of the sanitary sewer will be necessary to protect them. TEC has added notes requested by MSD to the plans. |  |  |  |  | 2025-02-03 | Rob provided documenation per ODOT note on 6/13
Telephone (Underground) - ALTAFIBER | 221 E. FOURTH STREET CINCINNATI, OHIO 45201, BLDG. 121-900 BRECK COWAN (513) 566-7043 (513) 287 - 2517 BRECK.COWAN@ALTAFIBER.COM | Stage 1 plans sent on 3/11 | 3/13/24 Kellie talked to Breck over the phone. He is concerned about the schedule. With the deep subgrade, his conduit would need replaced and he doesn't feel he would have time to do the work before Oct 2025. He is going to review the plans in depth and follow up with me. | AltaFiber is working to get TEC more information about the underground duct bank system within the area. The storm sewer system has been updating based on preliminary assumptions of the location of the duct bank. TEC anticpates getting the information in late July. |  |  | Breck and Kellie talked on the phone on 10/30/24 to discuss the critical locations. He is preparing to pot hole those locations. | Breck forwarded an email on 1/27 with possible scheduling of test holes
Telephone (Aerial) - ALTAFIBER | 209 WEST 7TH ST., BLDG 121-900 CINCINNATI, OHIO 45202 BEN DICKASON ROADPROJECTS@ALTAFIBER.COM | Stage 1 plans sent on 3/11 | [9 empty] | On 1/9/26, Duke notified TEC that some poles marked for removal are owned by Alta. Alta had no indicated their ownership. TEC reached out to Ben Dickason to notify him of pole relocations. There has been no response as of 1/12/26.
Telephone/Cable - Verizon Business Group | 8800 GOVERNORS HILL DR. CINCINNATI, OHIO 45129 BRUCE TURKIEWICZ (254) 721-897 BRUCE.TURKIEWICZ@VERIZONWIRELESS.COM | Stage 1 plans sent on 3/11 | 3/12/24, Bruce Turkiewicz responded and provided KMZ files showing existing line details. | [5 empty] | Sent to Rob and copied Bruce on 2/3/25 |  | Cynthia Martinex responded on 8/18 with minor comments that were addressed and resquested a bid date to know when to have their utilities relocated.
Telephone/Cable - Charter Communication/Spectrum | 10920 KENWOOD RD. BLUE ASH, OHIO 45242 DL-Southern-Ohio-Outside-Plant@charter.com JIM O'REILLY 513-386-5483 | Stage 1 plans sent on 3/11 | No response | [5 empty] | 2025-02-03
Water - Greater Cincinnati Water Works | 4747 SPRING GROVE AVE. CINCINNATI, OHIO 45232 MICHAEL COSSINS (513) 591 - 5056 GCWW.UTILITY.REVIEW@GCWW.CINCINNATI-OH.GOV | Stage 1 plans sent on 3/11 | 3/13/24 Dan Louis requested CAD files |  |  |  | GCWW is also concerned about the pavement cut and cover of their utilities. We are going to respond with a solution once a pavement build up is determined. DWGs were sent on 9/25/24 | TEC responded on 1/27 that we will address conflict concerns once test holes are done and pipe inverts are updated | 2025-02-03 | Dan sent conflicts on 3/27/25 TEC sent proposed layout with conflicts addressed on 6/10 | Plans were resent to Dan on 9/25/25 after no response from plans sent in June of 2025. | GCWW mentioned conflicts but have not said where those are located. Plans have not changed since they received them in June of 2025. GCWW also wants to add replacement plans to this project.
Water - City of Loveland Utility | 10980 Loveland Maderia Rd Loveland, OHIO 45140 Scott Wisby (513) 707-6115 swisby@lovelandoh.gov
Lumen (Level 3) | Renoy Thomas Business Analyst - Relocations Tulsa, OK (918) 547-9919 renoy.thomas@lumen.com relocations@lumen.com | Stage 1 plans sent on 3/11 | No Conflict
AT&T TRANSMISSION | DAN GARDNER (LEASED CONDUITS FROM CINCINNATI BELL)
City of Silverton | 6943 MONTGOMERY RD SILVERTON, OHIO 45236 Jack Cameron (513) 936-6240 | Stage 1 plans will be sent on 3/4