## Stage 2 Coordination
PID 116663 - HAM-275-5.25 UTILITY COORDINATION LOG
LISTED MEMBER INFORMATION |  |  | INITIAL COORDINATION (TICKET A514801667) |  | STAGE 2 COORDINATION |  | NOTES
MEMBER ID | LISTED MEMBER | PLAN CONTACT INFORMATION | OUPS TICKET RESPONSE | RECORD INFO RECEIVED | REVIEW COMPLETE | REVIEW COMMENTS | NOTES
CBTP | ALTAFIBER (FORMER CINCINNATI BELL) | 209 W 7TH ST CINCINNATI, OH 45202 CONTACT: TIM SEESTEDT, (513) 817-9131 | YES | YES | YES | NO CONFLICT | 2025-12-10 - CONFIRMED NO CONFLICT.
DUEP | DUKE ENERGY ELECTRIC | 139 E 4TH ST, ROOM 552A CINCINNATI, OH 45202 CONTACT: TIM MEYER, (513) 287-1266 | YES | YES | YES | NO CONFLICT | 2025-12-09 - CONFIRMED NO CONFLICT.
EPOP | ENTERPRISE PRODUCTS OPERATING | 1100 LOUISIANA ST HOUSTON, TX 77002 CONTACT: JIM RONAN, (513) 465-9890 | YES | YES | YES | NO CONFLICT | 2025-01-23 - CONFIRMED NO CONFLICT.
MCIP | MCI TELECOMMUNICATIONS (VERIZON) | 120 RAVINE ST AKRON, OH 44303 CONTACT: STEPHEN HOWELL, (513) 839-3486 | YES | YES | YES | NO CONFLICT | 2025-12-10 - CONFIRMED NO CONFLICT.
ODTCITS | ODOT CENTRAL OFFICE ITS | 1606 W BROAD ST COLUMBUS, OH 43223 CONTACT: PAUL BECK, (614) 387-0695 | YES | YES | YES | NO CONFLICT | 2025-12-17 - CONFIRMED NO CONFLICT. ITS CABINET CAB0004338 FROM RECORDS RECEIVED DURING INITIAL COORDINATION WAS REMOVED. ODOT DEACTIVATED CABINENT IN ODOT TIMS SYSTEM.