## Stage 1I2 Utility Summary
Utility Type LEGEND
E | Electric |  | SAN | San Sewer |  |  | ATG = Adjusted To Grade |  |  | High | Yes
G | Gas |  | STM | Storm Sewer |  |  | TBR = To Be Removed |  |  | Normal | No
L | Lighting |  | TR | Traffic |  |  | TBRL = To Be Relocated |  |  | Low | Maybe
FO | Fiber Optic |  | COMB | Combination
OIL | Oil Pipeline |  | W | Water | [5 empty] | No Longer Conflict
REF. No. | ROUTE | STATION | SIDE | UTILITY TYPE | Conflict Priority | OWNER | CONFLICT Description | EMHT Disposition of Conflict | Owner Further Comment
1 | Bridge St | 201+27 | RT | E | High | AEP | Pole in conflict with proposed bridge construction | Pole to be relocated
2 | Bridge St | 201+41 | LT | E | High | AEP | Pole in conflict with proposed bridge construction | Pole to be relocated
3 | Bridge St | 202+97 | RT | E | High | AEP | Pole in conflict with proposed bridge construction | Pole to be relocated
4 | Bridge St | 201+14 TO 202+64 | RT | G | High | NE OH Gas | In conflict with proposed bridge construction | Gas line to be relocated
5 | Bridge St | 201+27 TO 201+42 | LT | W | High | Village of Bowerston | Within excavation limits for wing wall construction | Waterline relocation included in construction plans
6 | Water Alley | 0+00 TO 0+50 | LT | G | High | NE OH Gas | Potentially within excavation limits for wing wall construction | Gas line to be relocated