## Overview
MEG-33-(7.61)(7.87) (PID 118508)
Utility Conflict Matrix | [16 empty] | Rev. 7/2022
Company | Address | Contact | Aerial or Underground | Utility Type | Location | Ex. Plans Received/ Confirmed | Currently within R/W or Easement | Conflict? | Test Hole Required (Level A) | Protection During Construction | Additional R/W or Easement Required for Relocaiton | Comments | Preliminary Plan to Address Conflicts | Final Plan to Address Conflicts | Received Proposed Relocation Plans (Yes/No with Date) | Relocation Schedule (Yes/No with Date) | Relocation Clear (Yes/No)
GAS
None | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
TELEPHONE/CABLE/FIBER
Frontier Communication | 241 S Nelson Avenue Wilmington, OH 45177 | Rob Latham (973) 382-2222 | Aerial/Underground Services | Communication | None | NO | NO | NO | NO | NO | NO | 5/13/2024 - OH811 Response - Excavation Site is Clear
Suddenlink | 1737 E Seventh Street Parkersburg, WV 26101 | Bill Brown (304) 865-4067 | Aerial/Underground Services | Fiber | None | NO | NO | NO | NO | NO | NO | 5/13/2024 - OH811 Response - Excavation Site is Clear
AT&T | 160 N Sixth Street Zanesville, OH 43701 | Barrett Tamasovich (740) 454-3552 | Aerial/Underground Services | Communication | None | NO | NO | NO | NO | NO | NO | 5/13/2024 - OH811 Response - Excavation Site is Clear
WATER
Tuppers Plains Chester Water District | 39561 Bar 30 Road Reedsville, OH 45772 | Derek Baum (740) 985-3315 | Underground | Water | None | NO | NO | NO | NO | NO | NO | 5/13/2024 - OH811 Response - Excavation Site is Clear
Village of Middleport | 659 Pearl Street Middleport, OH 45760 | Fred Hoffman (740) 992-2705 | Underground | Water | None | NO | NO | NO | NO | NO | NO | 5/13/2024 - OH811 Response - Excavation Site is Clear
ELECTRIC
AEP-Ohio | 38831 S.R. 7 Reedsville, OH 45769 | Clarke Saunders (614) 312-5807 | Aerial/Underground Services | Electric Distribution | None | NO | NO | NO | NO | NO | NO | 5/13/2024 - OH811 Response - Excavation Site is Clear
SANITARY
Village of Middleport | 659 Pearl Street Middleport, OH 45760 | Fred Hoffman (740) 992-2705 | Underground | Sewer | None | NO | NO | NO | NO | NO | NO | 5/13/2024 - OH811 Response - Excavation Site is Clear

## Current Status
Utility Owner | Utility Type | Conflicts | Correspondance
Trumbull County - Water | 10" Waterline with services | Yes | 1/29/21 - Sent utility owner Stage 1 plans
5/3/21 - Notified utility owner (Gary Newbrough) of project
6/11/21 - Received concurrence jacked and bored waterline under SR 82 can remain
9/9/21 - Sent owner Stage 2 utility plans.
10/19/21 - Held utility meeting
From meeting utility owner indicated to include relocations in plan set
1/11/22 - Held utiltiy relocation meeting with owner to discuss relocation requirements and specifications
Trumbull County - Sanitary | 8" Sanitary Sewer | Yes | 1/29/21 - Sent utility owner Stage 1 plans
5/3/21 - Notified utility owner (Gary Newbrough) of project
9/9/21 - Sent owner Stage 2 utility plans.
10/19/21 - Held utility meeting
From meeting no conflicts identified
10/21/21 - After further review notified design team of 2 conflicts with drainage system
12/2/21 - Drainage personnel investigating if drainage can be adjusted to avoid sanitary conflicts
Dominion Gas | 6" Gas Line with services | Yes | 1/29/21 - Sent utility owner Stage 1 plans
9/9/21 - Sent owner Stage 2 utility plans.
10/19/21 - Held utility meeting
From meeting owner indicated they would relocate line where required and lower services as needed.
Charter - Spectrum | Fiber - Cable | Yes | 1/29/21 - Sent utility owner Stage 1 plans
9/9/21 - Sent owner Stage 2 utility plans.
10/19/21 - Held utility meeting
From meeting owner indicated they are currently on City of Niles power poles. Will go under ground when power poles are relocated.
Lumen - CenturyLink | Fiber - Telephone | Yes | 1/29/21 - Sent utility owner Stage 1 plans
9/9/21 - Sent owner Stage 2 utility plans.
10/19/21 - Held utility meeting
From meeting owner indicated they own poles they are currently on, indicated they will relocate as needed.
Ohio Edison | Electric | Yes | 1/29/21 - Sent utility owner Stage 1 plans
9/9/21 - Sent owner Stage 2 utility plans.
10/19/21 - Held utility meeting
From meeting owner indicated they own switching station North of Hunters Trail.
From meeting owner indicated they thought they had utility easement.
City of Niles Power | Electric | Yes | 1/29/21 - Sent utility owner Stage 1 plans
9/9/21 - Sent owner Stage 2 utility plans.
11/2/21 - Held coordination meeting
1/6/22 - Utiltiy indicated they are going to relocate underground
Zayo | Fiber - Cable | Yes | 10/25/21 - Team was made aware of utility was being installed within project limits on.
10/27/21 - Sent Stage 2 plans to utility owner and asked utility to coordinate with design team to avoid upcoming proposed work.
10/27/21 to 11/11/21 - Sent utility various design information as requested.
1/6/22 - Received notification utility installation was completed and received utility location plans set.
1/10/21 - Identified utility is in conflict with proposed drainage structures.