## Sheet1
OUPS 1-800-362-2764 |  | Project Number |  | MIA-TRO-2226 | [5 empty] | Last Updated By: | TJB
PM: | AJH |  | OUPS Ticket: | A415503467-00A and B420601608-00B | [5 empty] | On: | 2026-01-23
Utility Company | Telephone | Contact | Project Notification and Request for Plans | Received Utility Plans or Positive Response | Sent Stage 1 (35%) Plans | Received Comments | Sent Stage 2 (80%) Plans | Received Comments | Sent Stage 3 (95%) Plans | Received Comments | Remarks
Name and Address | No. | Name
STREETS, STORM, SANITARY AND WATER | 937-356-9140
CITY OF TROY | 937-339-55543
100 S. MARKET STREET
TROY, OHIO 45375
ELECTRIC | 937-554-9063 | WILLIAM WARD |  |  | 2025-09-25 | 2025-09-29 |  |  | 2026-01-22 | 2026-01-23 | There are 4 underground 12kV electric powerline
AES OHIO | [10 empty] | crossings…installed at a minimum of 36" below
1900 DRYDEN ROAD | [10 empty] | grade at the time…I'm not aware of any conflicts
DISTRIBUTION ENGINEERING AREA 136 | [10 empty] | with the proposed work and AES Ohio electric
DAYTON, OHIO 45439 | [10 empty] | utilities. - Bill Ward - 9/29/2025
GAS | 937-312-2521 | GREGORY FISHMAN |  |  | 2025-09-25 |  |  |  | 2026-01-26 |  | The project was assigned to Yemi on 10/01/2025.
CENTERPOINT | 937-578-8816 | YEMI OLABISI
6500 CLYO ROAD
CENTERVILLE, OHIO 45459
ENTRUST SOLUTIONS GROUP | 513-297-3545 | MADISON BRAUSCH |  |  |  | 2025-10-09 |  |  | 2026-01-26 |  | Entrust Solutions is working with CenterPoint
400 TECHNE CENTER DRIVE, SUITE 300 | [10 empty] | on this project. There are several gas utilities
MILFORD, OHIO 45150 | [10 empty] | within the area and a basemap was provided.
CABLE | 937-626-6520 | JERROD INGELS |  |  | 2025-09-25 | [5 empty] | There are 7-8 underground crossings. We will
METRONET FIBER | 937-557-8355 | JAY RIGG |  |  | 2025-09-25 | [5 empty] | just need to make sure the contractor has
100 HARRISBURG DRIVE | 937-689-2188 | KEVIN MEHL |  |  |  | 2025-09-26 |  |  | 2026-01-26 |  | these utilities located prior to performing any
ENGLEWOOD, OHIO 45322 | [10 empty] | full-depth pavement repair.
TELEPHONE | 260-715-9906 | ANDY MEGGITT |  |  | 2025-09-25 |  |  |  | 2026-01-26
FRONTIER COMMUNICATIONS
10 MULBERRY STREET
BROOKVILLE, OHIO 45309
CABLE | 937-396-8611 | MARY EVANS |  |  | 2025-09-25 |  |  |  | 2026-01-26
CHARTER COMMUNICATIONS
3691 TURNER ROAD
DAYTON, OHIO 45415

## Sheet2
Utility | Utility Owners Name | Utility Companies Representatives Name | Utility Companies Representatives Address | Utility Companies Representatives Telephone Numbers | Utility Companies Representatives Email Address | Remarks
Telephone
Electric (Transmission)
Electric (Distribution)
Storm Sewer
Cable
Gas (Transmission)
Gas (Distribution)
Water & Sanitary