## Project 1
Survey Progress Checklist |  |  | RW Project? N | Survey Deliverables Due: 06-01-23
CRS: | PUT-SR12-8.00 |  | PID: | 117709 | Coord Sys: OCCS PUTNAM
Completed | Project Details | Completed By | Date Completed | Notes/Comments | other
OWNER ADDRESS LIST
| ODOT Parcel Nubmer Map created | RD | 2023-04-12
| Owner List compiled | RD | 2023-04-12
| PM contacted & Letter Sent | MS
COORD SYSTEM, SEED FILES TEMPLATES & DESIGN FILES
| DTY file replaced | DEE | 2023-05-11
| Seed Files corrected & desc/comments updated | DEE | 2023-05-11
| Templates copied to Reports Folder: ie. Survey Progress Tracker, Survey Parameters, Mon Tables, Survey Certs, Surveyor's Project Notes, RW staking complete report (RW only projects), etc. | DEE | 2023-05-11
| Initial design files created (FB, BR, BK) & desc/comments updated **Follow naming conventions for single and multi-site PIDs | DEE | 2023-05-11
RESEARCH (Hard copy & .pdf)
Auditor/GIS
| Property Cards | DEE | 2023-05-24
| Tax Map | DEE | 2023-05-24
Engineer/GIS
| Surveys | DEE | 2023-05-24
| Road Records | DEE |  | WAITING FOR RESPONSE
| RW widths on County Rd/Twp Rd | DEE |  | WAITING FOR RESPONSE
| Section corner/Stone Records | DEE | 2023-05-24 | DO I NEED MORE THAN JUST SECTION MAP
Recorder
| Deeds | DEE | 2023-05-24
| Easements (Lisa-RW)(Survey Non-RW) | N/A
| Health Dept- septic/water well info | N/A
| DNR - well and gas well logs | N/A |  | ODNR Water Wells (ohiodnr.gov) https://gis.ohiodnr.gov/MapViewer/?config=oilgaswells
| Sanborn Maps | N/A |  | About this Collection ¦ Sanborn Maps ¦ Digital Collections ¦ Library of Congress (loc.gov)
| Existing R/W and Construction Plans | DEE | 2023-05-11
| OHROW (Statewide RW Plans & Mon) | DEE | 2023-05-11 | ArcGIS Web Application (state.oh.us)
| Plan Vault (Statewide Const.) | DEE | 2023-05-11 | ArcGIS Web Application (state.oh.us)
| D1 Plan Vault (Const.) | DEE | 2023-05-11
| D1 RW Plan Vault | DEE | 2023-05-11
Old ODOT Surveys and Field Notes
| Survey Archives(scanned field notes 1950's-present) |  |  | \\d01fs2\Survey_Notes
| S:Field (old project .dgns ect. | DEE | 2023-05-24 | ..\_Field
Atrium Cabinets
| RR val maps(some scanned-see link) | N/A |  | ..\_RAILROADS
| Canal Maps | N/A
| Random County RW take plans | DEE | 2023-05-11
| Color coded RW width maps(top right) and RW printout | DEE | 2023-05-11 | ..\_RW BINDER SCAN JAN 2021_ AND ROAD RW INFO
| Field Books and Index (Circa 1920's-1950's) | DEE | 2023-05-24 | ..\_SURVEY FIELD BOOKS
| R/W Width Binder | DEE | 2023-05-11 | ..\_RW BINDER SCAN JAN 2021_ AND ROAD RW INFO
UTILITIES FOR SURVEY
| OUPS-Plans ordered | GD | 2023-05-03
| OUPS-Field markings ordered | GD | 2023-05-03
| NEWTON PDF saved to project folder | GD | 2023-05-10
| OUPS-Field markings collected | DEE/GD | 2023-05-10
FIELD WORK
HORZ CONTROL - 3 CP's minimum
| Set | DEE/GD | 2023-05-10
| Collected | DEE/GD | 2023-05-10
BENCHMARKS
| Set | DEE/GD | 2023-05-10
| Leveled | DEE/GD | 2023-05-10
CENTERLINE & BOUNDARY MONS
| recovered | DEE | 2023-06-15
| collected | DEE | 2023-06-15
UTILITIES
| OUPS markings | DEE | 2023-05-10
| Observed evidence | DEE | 2023-05-10
GENERAL TOPO ITEMS
| General Topo and features | DEE/GD/KF | 2023-05-31
BRIDGE TOPO ITEMS
| Conventional and Scan completed | N/A
DESIGN FILES
FB- Ex. Topo 3D
Field Book folders to create:
| C-R-S EX Topo (contains all existing ground topo items) (ie ALL-65-1.34 EX Topo) | DEE | 2023-06-27
| C-R-S EX Brdge (contains all Ex. Bridge Deck items) (ie ALL-65-1.34 EX Bridge) | N/A
| C-R-S EX Drainage (contains all Ex. Drainageitems) (ie ALL-65-1.34 EX Drainage) | N/A
| Terrain model created | DEE | 2023-06-26
| .XML of FINAL terrain created(name should match the terrain as named in the .dgn) | DEE | 2023-06-26
| Ex. CB'S/piping shown/labeled (unless in BD) | N/A
| Benchmarks-(downloaded, labeled and described) | DEE | 2023-05-10
| Control Points-(downloaded, ELEV UPDATED TO LEVELED ELEV, labeled and described) | DEE | 2023-05-10
| OHWM | DEE
| UG & OH Utilities shown-line directions corrected | DEE | 2023-05-10
| Project Specific notes (warnings, misc items etc (make notes on DEFAULT LEVEL) | DEE | 2023-06-26
| Survey Parameters/RW/Bearing-Base/Utility Word Document edited | DEE | 2023-06-26
| .PDF's prepared for field check | DEE | 2023-06-26
BK- Ex. Centerlines 2D
| Centerline SR12 created | DEE | 2023-06-26
blank for additonal CL's
blank for additonal CL's
blank for additonal CL's
blank for additonal CL's
blank for additonal CL's
| .PDF of each FINAL c/l alignment created (.pdf name should match exactly to the cl name in the .dgn | DEE | 2023-06-26
| .XML of each FINAL c/l alignment created (.xml name should match exactly to the cl name in the .dgn | DEE | 2023-06-26
| .PDF of each STA/OFFSET Reports | DEE | 2023-06-26
BR- Ex. R/W and Property lines2D
Field Book folders to Create:
| C-R-S Ex. Monuments (contains all existing boundary/cl/rw related monuments as collected in the field) | DEE | 2023-06-15
| C-R-S Ex. R/W & CL (contains RX & CLX & PX points) | DEE | 2023-06-26
| C-R-S PROPOSED R/W & CL (contains RP & CLP points) (only pertains to projects with new RW needed)(This fb folder is created in the BR001/101/201 etc. by survey at points set by referencing in the proposed RW file (ie BR001/102/202 etc)???? We Need to further discuss how this process will go | N/A
| C-R-S SEARCH POINTS (create when needed) | DEE | 2023-06-14
C-R-S AS-SET (only pertains to projects with new RW needed)(created for record as-staked location of RW pins that were set)
| Ex. R/W depicted | DEE | 2023-06-26
| Ex. Property lines Calculated/Depicted | DEE | 2023-06-26 | WILL USE PUTNAM COUNTY GIS FILES FOR NOW - SHOWN APPROXIMATELY
| ODOT Parcel Nubmer Map created | N/A
| Ownership/TP/Acres labeled | DEE | 2023-06-25
| Sec/Twp-Range/Township/County labeled | DEE | 2023-06-27 | SHOWN APPROXIMATELY
| Section Corners & other critical monuments described/labeled | DEE | 2023-06-27
| Corporation Limits Shown | N/A
BD- Ex. Drainage- for large projects/Modeling
| CBs and Pipes modeled/drawn | N/A
BE, .tin and .gpk (SS4/10 only)
TYPICAL LEVELS TO USE: Notes that need to be seen=Default ; Ref. Surveys and Deed Descriptions=Scratch 10 ; Rough Property line Calcs/notes = Scratch 5 ; Rough Centerline Calcs/notes= Scratch 3
SURVEY DELIVERABLE REMINDER CHECKLIST REVIEWED
PROJECT EMAILED TO SOM FOR FIELD CHECK/REVIEW
PROJECT FIELD CHECK/REVIEW COMPLETE
SURVEY DELIVERABLES EMAILED TO PROJECT ENGINEER
POINTS SAVED TO MONUMENT DATABASE
SURVEY DELIVERABLES SAVED TO S:DRIVE
R/W MONUMENTED (Only for projects with R/W)
PAPER FILE SCANNED TO SURVEY ARCHIVE
type lower case "a" to produce checkmark
ver 1-9-2023
LEGAL DESCRIPTIONS (ONLY FOR RW PROJECTS)
Legal description & closure folders created under 300/Survey/Office Data
Preliminary Legals created
Legals reviewed by ODOT
Legals submitted for County Review
Legals approved by County
Final legals completed
signed/sealed and scanned
Combined .pdf copied to Real Estate Folder
ADDITIONAL SURVEY/PROJECT NOTES: