## SAN-6 Slide
|  |  |  | SPREADSHEET | 1) | SAVE THIS FILE TO THE PROPER FOLDER FOR YOUR PROJECT AS THE SAME NAME AS YOUR DGN (I.E. #####GS001.XLSX)
|  |  |  | INSTRUCTIONS: | 2) | ENTER ITEM CODE (FOR EXAMPLE: 201E11000) AND ADDITIONAL DESCRIPTION INTO THE BLUE CELLS
[5 empty] | 3) | ENTER ALL DATA REQUIRED, PAGE # AND SPLIT # MUST BE FILLED OUT.
[5 empty] | 4) | DO NOT REMOVE THE PROTECTION FROM THIS SPREADSHEET, LEAVE THE PROTECTION ON SO THAT YOU DO NOT DELETE NEEDED FORMULAS OR RESIZE SHEET
| Page # | 1 | [21 empty] | 1 | <--- ENTER STARTING SHEET NUMBER
|  | ITEM_CODE | [7 empty] | 203E10000 | 203E20001 | 203E40001 |  |  |  | 203E35110 | 203E35130 |  |  | 203E35001 |  | 204E50000
|  | ADDITIONAL_DESCRIPTION | [17 empty] | (NO. 8 AGGREGATE) |  | , 712.09, TYPE A
| Split # | SHEET NO. | STATION TO STATION |  |  |  | SIDE |  |  | 203 | 203 | 203 |  |  |  | 203 | 203 |  |  | 203 |  | 204
[8 empty] | EXCAVATION - END AREA | EMBANKMENT - END AREA | EXCAVATION | EMBANKMENT, AS PER PLAN | BORROW, AS PER PLAN |  | GRANULAR MATERIAL, TYPE B - END AREA | GRANULAR MATERIAL, TYPE D - END AREA | GRANULAR MATERIAL, TYPE B | GRANULAR MATERIAL, TYPE D |  | GRANULAR EMBANKMENT, AS PER PLAN - END AREA | GRANULAR EMBANKMENT, AS PER PLAN (NO. 8 AGGREGATE) | GEOTEXTILE FABRIC, 712.09, TYPE A - PERIMETER | GEOTEXTILE FABRIC, 712.09, TYPE A
[8 empty] | SF | SF | CY | CY | CY |  | SF | SF | CY | CY |  | SF | CY | FT | SY
EB U.S. 6
|  | 26 | 3240.26 |  |  |  | RT | 678 | 713 |  |  |  |  | 16 | 44 |  |  |  | 64 |  | 98
|  |  | 3240.26 |  | TO | 3250 | RT |  |  | 239 | 258 | 19 |  |  |  | 6 | 16 |  |  | 24 |  | 107
|  | 27 | 3250 |  |  |  | RT | 644 | 712 |  |  |  |  | 16 | 44 |  |  |  | 64 |  | 98
|  |  | 3250 |  | TO | 3300 | RT |  |  | 957 | 1297 | 340 |  |  |  | 30 | 82 |  |  | 119 |  | 545
|  | 28 | 3300 |  |  |  | RT | 389 | 688 |  |  |  |  | 16 | 44 |  |  |  | 64 |  | 98
|  |  | 3300 |  | TO | 3350 | RT |  |  | 774 | 1259 | 485 |  |  |  | 30 | 82 |  |  | 119 |  | 545
|  | 29 | 3350 |  |  |  | RT | 446 | 671 |  |  |  |  | 16 | 44 |  |  |  | 64 |  | 98
|  |  | 3350 |  | TO | 3400 | RT |  |  | 833 | 1226 | 393 |  |  |  | 30 | 82 |  |  | 119 |  | 545
` |  | 30 | 3400 |  |  |  | RT | 453 | 653 |  |  |  |  | 16 | 44 |  |  |  | 64 |  | 98
|  |  | 3400 |  | TO | 3450 | RT |  |  | 840 | 1216 | 376 |  |  |  | 30 | 82 |  |  | 119 |  | 545
|  | 31 | 3450 |  |  |  | RT | 454 | 660 |  |  |  |  | 16 | 44 |  |  |  | 64 |  | 98
|  |  | 3450 |  | TO | 3500 | RT |  |  | 825 | 1232 | 407 |  |  |  | 30 | 82 |  |  | 119 |  | 545
|  | 32 | 3500 |  |  |  | RT | 437 | 670 |  |  |  |  | 16 | 44 |  |  |  | 64 |  | 98
|  |  | 3500 |  | TO | 3550 | RT |  |  | 796 | 1246 | 450 |  |  |  | 29 | 81 |  |  | 119 |  | 545
` |  | 33 | 3550 |  |  |  | RT | 422 | 675 |  |  |  |  | 15 | 43 |  |  |  | 64 |  | 98
|  |  | 3550 |  | TO | 3600 | RT |  |  | 755 | 1255 | 500 |  |  |  | 28 | 78 |  |  | 100 |  | 459
|  | 34 | 3600 |  |  |  | RT | 393 | 680 |  |  |  |  | 15 | 41 |  |  |  | 44 |  | 67
|  |  | 3600 |  | TO | 3650 | RT |  |  | 714 | 1232 | 518 |  |  |  | 27 | 76 |  |  | 81 |  | 370
|  | 35 | 3650 |  |  |  | RT | 378 | 650 |  |  |  |  | 14 | 41 |  |  |  | 43 |  | 66
|  |  | 3650 |  | TO | 3700 | RT |  |  | 668 | 1156 | 488 |  |  |  | 26 | 75 |  |  | 80 |  | 367
|  | 36 | 3700 |  |  |  | RT | 343 | 598 |  |  |  |  | 14 | 40 |  |  |  | 43 |  | 66
|  |  | 3700 |  | TO | 3750 | RT |  |  | 630 | 1063 | 433 |  |  |  | 26 | 75 |  |  | 80 |  | 367
|  | 37 | 3750 |  |  |  | RT | 337 | 549 |  |  |  |  | 14 | 40 |  |  |  | 43 |  | 66
|  |  | 3750 |  | TO | 3800 | RT |  |  | 606 | 975 | 369 |  |  |  | 26 | 75 |  |  | 80 |  | 367
|  | 38 | 3800 |  |  |  | RT | 317 | 503 |  |  |  |  | 14 | 40 |  |  |  | 43 |  | 66
|  |  | 3800 |  | TO | 3850 | RT |  |  | 586 | 896 | 310 |  |  |  | 26 | 75 |  |  | 80 |  | 367
|  | 39 | 3850 |  |  |  | RT | 315 | 464 |  |  |  |  | 14 | 40 |  |  |  | 43 |  | 66
|  |  | 3850 |  | TO | 3900 | RT |  |  | 608 | 850 | 242 |  |  |  | 26 | 75 |  |  | 61 |  | 278
|  | 39 | 3900 |  |  |  | RT | 341 | 454 |  |  |  |  | 14 | 40 |  |  |  | 22 |  | 34
|  |  | 3900 |  | TO | 3950 | RT |  |  | 666 | 806 | 140 |  |  |  | 26 | 75 |  |  | 40 |  | 184
|  | 40 | 3950 |  |  |  | RT | 378 | 416 |  |  |  |  | 14 | 40 |  |  |  | 21 |  | 32
|  |  | 3950 |  | TO | 4000 | RT |  |  | 702 | 718 | 16 |  |  |  | 26 | 75 |  |  | 38 |  | 175
|  | 40 | 4000 |  |  |  | RT | 380 | 359 |  |  |  |  | 14 | 40 |  |  |  | 20 |  | 31
|  |  | 4000 |  | TO | 4050 | RT |  |  | 654 | 652 | -2 |  |  |  | 26 | 75 |  |  | 37 |  | 170
|  | 41 | 4050 |  |  |  | RT | 326 | 345 |  |  |  |  | 14 | 40 |  |  |  | 19 |  | 30
|  |  | 4050 |  | TO | 4100 | RT |  |  | 595 | 609 | 14 |  |  |  | 26 | 75 |  |  | 36 |  | 167
|  | 41 | 4100 |  |  |  | RT | 316 | 312 |  |  |  |  | 14 | 40 |  |  |  | 19 |  | 30
|  |  | 4100 |  | TO | 4150 | RT |  |  | 595 | 549 | -46 |  |  |  | 26 | 75 |  |  | 36 |  | 167
|  | 42 | 4150 |  |  |  | RT | 326 | 280 |  |  |  |  | 14 | 40 |  |  |  | 19 |  | 30
|  |  | 4150 |  | TO | 4200 | RT |  |  | 575 | 495 | -80 |  |  |  | 26 | 75 |  |  | 36 |  | 167
|  | 42 | 4200 |  |  |  | RT | 295 | 254 |  |  |  |  | 14 | 40 |  |  |  | 19 |  | 30
|  |  | 4200 |  | TO | 4250 | RT |  |  | 510 | 453 | -57 |  |  |  | 26 | 75 |  |  | 37 |  | 170
|  | 43 | 4250 |  |  |  | RT | 255 | 235 |  |  |  |  | 14 | 40 |  |  |  | 20 |  | 31
|  |  | 4250 |  | TO | 4300 | RT |  |  | 440 | 409 | -31 |  |  |  | 25 | 71 |  |  | 38 |  | 175
|  | 43 | 4300 |  |  |  | RT | 220 | 206 |  |  |  |  | 13 | 36 |  |  |  | 21 |  | 32
|  |  | 4300 |  | TO | 4350 | RT |  |  | 377 | 360 | -17 |  |  |  | 22 | 59 |  |  | 40 |  | 184
|  | 44 | 4350 |  |  |  | RT | 187 | 182 |  |  |  |  | 10 | 27 |  |  |  | 22 |  | 34
|  |  | 4350 |  | TO | 4370 | RT |  |  | 139 | 129 | -10 |  |  |  | 8 | 19 |  |  | 17 |  | 77
|  | 44 | 4370 |  |  |  | RT | 188 | 164 |  |  |  |  | 9 | 24 |  |  |  | 23 |  | 35
|  |  | 4370 |  | TO | 4380 | RT |  |  | 35 | 33 | -2 |  |  |  | 2 | 5 |  |  | 5 |  | 20
|  | 45 | 4380 |  |  |  | RT | 0 | 10 |  |  |  |  | 0 | 0 |  |  |  | 0 |  | 0
|  |  | 4380 |  | TO | 4391.75 | RT |  |  | 0 | 3 | 3
|  | 45 | 4391.75 |  |  |  | RT | 0 | 2
| Total | TOTALS CARRIED TO NEXT SHEET | [7 empty] | 15119 | 20377 | 5258 |  |  |  | 609 | 1715 |  |  | 1660 |  | 7608
| Page # | 2
|  | ITEM_CODE | [7 empty] | 203E10000 | 203E20001 | 203E40001 |  |  |  | 203E35110 | 203E35130 |  |  | 203E35001 |  | 204E50000
|  | ADDITIONAL_DESCRIPTION | [17 empty] | (NO. 8 AGGREGATE) |  | , 712.09, TYPE A
| Split # | SHEET NO. | STATION TO STATION |  |  |  | SIDE |  |  | 203 | 203 | 203 |  |  |  | 203 | 203 |  |  | 203 |  | 204
[8 empty] | EXCAVATION - END AREA | EMBANKMENT - END AREA | EXCAVATION | EMBANKMENT, AS PER PLAN | BORROW, AS PER PLAN |  | GRANULAR MATERIAL, TYPE B - END AREA | GRANULAR MATERIAL, TYPE D - END AREA | GRANULAR MATERIAL, TYPE B | GRANULAR MATERIAL, TYPE D |  | GRANULAR EMBANKMENT, AS PER PLAN - END AREA | GRANULAR EMBANKMENT, AS PER PLAN (NO. 8 AGGREGATE) | GEOTEXTILE FABRIC, 712.09, TYPE A - PERIMETER | GEOTEXTILE FABRIC, 712.09, TYPE A
[8 empty] | SF | SF | CY | CY | CY |  | SF | SF | CY | CY |  | SF | CY | FT | SY
WB U.S. 6
|  | 49 | 13240.26 |  |  |  | LT | 656 | 665 |  |  |  |  | 12 | 32 |  |  |  | 64 |  | 98
|  |  | 13240.26 |  | TO | 13250 | LT |  |  | 214 | 237 | 23 |  |  |  | 5 | 12 |  |  | 24 |  | 107
|  | 50 | 13250 |  |  |  | LT | 528 | 648 |  |  |  |  | 12 | 32 |  |  |  | 64 |  | 98
|  |  | 13250 |  | TO | 13280 | LT |  |  | 603 | 678 | 75 |  |  |  | 14 | 36 |  |  | 72 |  | 327
|  | 51 | 13280 |  |  |  | LT | 557 | 571 |  |  |  |  | 12 | 32 |  |  |  | 64 |  | 98
|  |  | 13280 |  | TO | 13300 | LT |  |  | 207 | 212 | 5 |  |  |  | 5 | 12 |  |  | 24 |  | 109
|  | 52 | 13300 |  |  |  | LT | 0 | 0 |  |  |  |  | 0 | 0 |  |  |  | 0 |  | 0
|  | 53 | 13350 |  |  |  | LT |  |  |  | 1 | 1
|  | 54 | 13400 |  |  |  | LT |  |  |  | 2 | 2
|  | 55 | 13450 |  |  |  | LT |  |  |  | 3 | 3
|  | 56 | 13500 |  |  |  | LT |  |  |  | 3 | 3
|  | 57 | 13550 |  |  |  | LT |  |  |  | 3 | 3
|  | 58 | 13600 |  |  |  | LT |  |  |  | 2 | 2
|  | 59 | 13650 |  |  |  | LT |  |  |  | 3 | 3
|  | 60 | 13700 |  |  |  | LT |  |  |  | 3 | 3
|  | 61 | 13750 |  |  |  | LT |  |  |  | 3 | 3
|  | 62 | 13800 |  |  |  | LT |  |  |  | 3 | 3
|  | 63 | 13850 |  | TO | 13900 | LT |  |  |  | 4 | 4
|  | 64 | 13950 |  | TO | 14000 | LT |  |  |  | 5 | 5
|  | 65 | 14050 |  | TO | 14100 | LT |  |  |  | 4 | 4
|  | 66 | 14150 |  | TO | 14200 | LT |  |  |  | 5 | 5
|  | 67 | 14250 |  | TO | 14300 | LT |  |  |  | 12 | 12
|  | 68 | 14350 |  | TO | 14400 | LT |  |  |  | 10 | 10
| Total | TOTALS CARRIED FROM PREVIOUS SHEET | [7 empty] | 15119 | 20377 | 5258 |  |  |  | 609 | 1715 |  |  | 1660 |  | 7608
| Total | TOTALS THIS SHEET | [7 empty] | 1024 | 1193 | 169 |  |  |  | 24 | 60 |  |  | 120 |  | 543
| Total | TOTALS CARRIED TO GENERAL SUMMARY | [7 empty] | 16143 | 21570 | 5427 |  |  |  | 633 | 1775 |  |  | 1780 |  | 8151
| Page # | 3
ITEM_CODE
ADDITIONAL_DESCRIPTION
| Split # | SHEET NO. | STATION TO STATION |  |  |  | SIDE
| Total | TOTALS CARRIED FROM PREVIOUS SHEET | [6 empty] | #REF! | 16143 | 21570 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 8151 | #REF!
| Total | TOTALS THIS SHEET
| Total | TOTALS CARRIED TO GENERAL SUMMARY
| Page # | 4
| 44 | ITEM_CODE
ADDITIONAL_DESCRIPTION
| Split # | SHEET NO. | STATION TO STATION |  |  |  | SIDE
| Total | TOTALS CARRIED TO GENERAL SUMMARY
| Page # | 6
ITEM_CODE
ADDITIONAL_DESCRIPTION
| Split # | SHEET NO. | STATION TO STATION |  |  |  | SIDE
| Total | TOTALS CARRIED FROM PREVIOUS SHEET
| Total | TOTALS THIS SHEET
| Total | TOTALS CARRIED TO GENERAL SUMMARY

## TO GENSUM
1
| Page # | 5
| 19 | ITEM_CODE |  |  |  |  | 203E10000 | 203E20001 |  |  |  | 203E35110 | 203E35130 |  |  | 203E35001 |  |  | 204E50000 |  |  | #REF!
|  | ADDITIONAL_DESCRIPTION | [13 empty] | (NO. 8 AGGREGATE) |  |  | , 712.09, TYPE A |  |  | #REF!
| Split # | SHEET NO. | REF NO. | STATION TO STATION | SIDE |  | 203 | 203 |  |  |  | 203 | 203 |  |  | 203 |  |  | 204 |  |  | #REF!
[7 empty] | EXCAVATION | EMBANKMENT, AS PER PLAN |  |  |  | GRANULAR MATERIAL, TYPE B | GRANULAR MATERIAL, TYPE D |  |  | GRANULAR EMBANKMENT, AS PER PLAN (NO. 8 AGGREGATE) |  |  | GEOTEXTILE FABRIC, 712.09, TYPE A |  |  | #REF!
[7 empty] | CY | CY |  |  |  | CY | CY |  |  | CY |  |  | SY |  |  | #REF!
| 1 | 11 |  | TOTALS CARRIED TO GENERAL SUMMARY |  |  | 16143 | 21570 |  |  |  | 633 | 1775 |  |  | 1780 |  |  | 8151 |  |  | #REF!
| Total | TOTALS CARRIED TO GENERAL SUMMARY |  |  |  | 0 | 16143 | 21570 | 0 | 0 | 0 | 633 | 1775 | 0 | 0 | 1780 | 0 | 0 | 8151 | 0 | 0 | #REF! | 0
| Page # | 6
ITEM_CODE
ADDITIONAL_DESCRIPTION
| Split # | SHEET NO. | REF NO. | STATION TO STATION | SIDE
TOTALS CARRIED TO GENERAL SUMMARY
| Total | TOTALS CARRIED TO GENERAL SUMMARY |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0