PID 95771 MOT Notes (To add if they already haven’t been)

Item 614 Maintaining Traffic

SEN-4:

A minimum of one lane in each direction shall be maintained at all times.

SEN-18:

A minimum of one lane in each direction shall be maintained at all times, except for a period not to exceed 21 calendar days, when through traffic may be detoured as listed below to complete pavement planing, pavement repairs and placement of the intermediate pavement.  A disincentive shall be assessed in the amount shown in the windows contract table for each calendar day the roadway remains closed to traffic beyond the specified point.

Local traffic shall be maintained at all times with flaggers per MT-97.10 and MT-97.12

SEN-18 Eastbound Detour:  SR-101 to SR-19

SEN-18 Westbound Detour: The reverse of the route above.

Add the Windows Contract Table

| Description of Critical Work | Calendar Days to Complete | Disincentive per Day | Work Window |  |
| --- | --- | --- | --- | --- |
|  |  |  | Start | End |
| SEN-18: Pavement planing, pavement repairs and placement of intermediate course | 21 Days |  | 6/15/25 | 9/15/25 |
| All work on Project | - | Per C&MS 108.07 | Contract Execution Date | Project Completion Date |

TEM Plan Note 642-8: Notice of Closure Sign

TEM Plan Note 642-11: Signs and Barricades

R11-3 Signs on Type III Barricades

SR-18 Eastbound just east of Elmwood St

SR-18 Westbound just west of TR-159

TEM Plan Note 642-12: Closing MOT Paragraph