## Sheet1
WINDOW CONTRACT TABLE
Description of Critical Work | Calendar Days to Complete | Disincentive per Day | Work Window
|  |  | Start | End
Sen-18: Pavement planing, pavement repairs and placement of intermediate course | 21 Days | 2500 | 2025-06-15 | 2025-09-15
All Work on Project | - | Per C&MS 108.07 | Contract Execution Date | Project Completion Date