## Drawings
Overall | Sheet No. | Sheet Name |  | DRAWN | DESIGN | CHECKED | UPDATED | BACK CHKD | REVIEWED | NOTES
Sheet No.
13 | 1 | Site Plan | SP001 | HLG |  | JWA | HLG |  | RLC
14 | 2 | General Notes | SN001 | HLG |  | JWA | HLG | JWA | RLC
15 | 3 | Estimated Quantities | SQ001 | HLG | MEE | RLC |  |  | RLC | Only Items are req'd. No quantities
16 | 4 | Rear Abutment Removal/Repair Details | SV001 | HLG |  |  |  |  | RLC | Calcs done in LEAP, need reviewed by RLC. MEE Working on ORD Designs
17 | 5 | Rear Abutment Wingwall Repair Details | SV002 | HLG |  |  |  |  | RLC
18 | 6 | Forward Abutment Removal/Repair Details | SV003 | HLG |  |  |  |  | RLC
19 | 7 | Forward Abutment Wingwall Repair Details | SV004 | HLG |  |  |  |  | RLC
20 | 8 | Rear Abutment Details | SR001 | HLG
21 | 9 | Rear Abutment Sections | SR002
22 | 10 | Forward Abutment Details | SF001 | HLG | [5 empty] | Dimensions are typed in. Needs attention
23 | 11 | Forward Abutment Sections | SF002 | [6 empty] | Calcs done in LEAP, need reviewed by RLC. MEE Working on ORD Designs
24 | 12 | Beam Layout | SS001 | HLG | MEE | JWA | HLG |  | RLC
25 | 13 | Beam Details | SS002 | HLG | MEE | JWA | HLG |  | RLC
26 | 14 | Typical Section | ST001 | HLG | MEE | JWA | HLG |  | RLC
27 | 15 | Deck Plan | SD001 |  | MEE |  |  |  | RLC
28 | 16 | Deck Elevations | SD002 |  | MEE |  |  |  | RLC
29 | 17 | Bearing Details | SB001 | HLG | MEE |  |  |  | RLC
30 | 18 | Approach Slab Details | SM001 | JWA |  |  |  |  | RLC | Needed if they do not follow standard
31 | 19 | Reinforcing Steel List | SL001
Henry
Moe
Jake
Rebekah

## Design
Description | Designed | Checked | Updated | Backchecked | Reviewed | Notes | Henry
Water Line Temp Support | [6 empty] | Moe
Drainage Calculations | [5 empty] | Brad said they will be checking drainage, Teams Msg 07/18 8:09am, Brad asked us to do it on 08/29/2023 | Jake
Abutment Design | [6 empty] | Rebekah
Beams | MEE | RLC | MEE | RLC
Beam Camber | MEE | RLC | MEE | RLC
Deck Elevations | MEE | RLC | MEE | RLC
Survey/Skew | RLC |  |  |  |  | Email went out to Dan Lorenz 7/13 requesting a meeting, Met with Dan and email 07/25/2023
Bearing Design | MEE | RLC | MEE | RLC
Setting Beams/Interference with buildings | RLC
Emailed Encore 07/14/2023 (dhenry@encoreprecastllc.com)-Mike Called back and said that was too big for them to handle
Called Prestress Services of Ind. 7/14/2023- They sent me to VM of Glen (didn't hear back), Called 07/17/2023 they gave me the number 330-635-5737 called that number twice, Received a text saying they did not do pretressed box beams, Called the KY location that evening and left a voicemail in sales. Ryan called me back, emailed rhamblen@prestressservices.com 7/17/2023, Recieved email back from Ryan on 8/9/2023
Called and emailed Carr Concrete (LB Foster) 07/14/2023 kkostelac@lbfoster.com, Brandon King emailed back 7/18/2023 saying it might be tight
Construction Schedule
OHWM | [5 empty] | OHW EL 837.5
Bridge Asbestos Inspection Report | [5 empty] | Brad is looking into our scope
PNL
Local Flood Plan Coordination | RLC |  |  |  |  | Email went to Mayor's office via Belle Everett on 08/11/2023
Floodplain Finding Form | RLC |  |  |  |  | Form completed and emailed to Belle Everett on 08/11/2023
Coordination with US Army Corp for Stream Gage | RLC |  |  |  |  | Email went to Fred McCallister 7/14/2023
Floodplain Coordinator
Community Contact List - Query (ohiodnr.gov)