Instructions

- The Project Initiation Package is intended to focus on critical issues that can be identified with existing information from secondary sources and/or identified during a site visit.

- Each specialty area of the Project Initiation Package should be completed by individuals who possess sufficient experience to enable them to correctly identify and evaluate issues arising from the field review.

- In the Location/Comments field provide information concerning potential impacts that is brief but gives enough detail to allow an understanding of the issue(s).

- The scope of services document should account for any issues identified in the Project Initiation Package that have the potential to affect scope, schedule, and budget.

- In some instances, resources/subject areas that may need to be consulted for the secondary source review are identified on this form.

Project Initiation Package Deliverables

Provide an expanded Study Area Map identifying project design, utility, right of way and environmental constraints identified through the Project Initiation Package.  Tables, USGS and/or aerial mapping, photographs keyed to available project mapping, the plan to inform and involve the public, and other support material should also be submitted with the Project Initiation Package to illustrate specific problem areas.

General

| ## Date(s) of field review: | ## TBD |
| --- | --- |

| Project Name (County, Route, Section): | TRU SR 0088 04.30 | PID: | 123665 |
| --- | --- | --- | --- |
| Date Project Initiation Package Completed: | 6/18/25 | Prepared By: | Brian Ross |
| City, Township or Village Name(s): | Farmington Twp | ODOT Project Manager: | TBD |

Project Description: Superstructure replacement of SFN 7805713 TRU-88-0430

Project Limits/Study Area/General Location: Coordinates: 41°23'26.19"N, 80°55'15.04" TRU 88 Exact limits TBD. Assuming SLM 4.27 to 4.34 (150’ forward and rear of exp joints)

| ODOT DISCIPLINE INVOLVEMENT: |  |  |
| --- | --- | --- |
| List name and phone number of individual(s) representing each discipline during the site visit and preparation of the Project Initiation Package. One individual may represent multiple disciplines. |  |  |
| DISCIPLINE | NAME | PHONE NUMBER |
| GENERAL EXISTING INFORMATION | MIKE CRAVER |  |
| LOCAL PLANNING COORDINATION | JIM BRUNER | 330-786-4924 |
| DISTRICT HIGHWAY MANAGEMENT STAFF CONCERN | JOE PARTHEMER |  |
| CRASH DATA | DAVE GRIFFITH |  |
| ENVIRONMENTAL ISSUES | SEAN CARPENTER |  |
| GEOMETRIC DESIGN CONTROLLING CRITERIA | MATT CHANEY / KYLE KOPPES |  |
| OTHER GEOMETRIC DESIGN ISSUES | MATT CHANEY / KYLE KOPPES |  |
| GEOTECHNICAL ISSUES | TOM POWELL |  |
| PAVEMENT ISSUES | BRIAN ROSS |  |
| STRUCTURAL ISSUES | BRIAN ROSS |  |
| HYDRAULIC ISSUES | MIKE PALAGANO |  |
| TSMO CONSIDERATIONS | AARON CONLEY |  |
| TRAFFIC CONTROL ISSUES | MICHELLE CHANEY / AARON CONLEY |  |
| UTILITY ISSUES | PETER DINH |  |
| MAINTENANCE OF TRAFFIC ISSUES | LEN BLANKENSHIP |  |
| RIGHT OF WAY/SURVEY ISSUES | BRIAN HONAKER / TIM WARD |  |
| CONSTRUCTION ISSUES | TOM KOPNICKY | 330-715-9017 |
| PEDESTRIAN AND BICYCLE ISSUES | MATT CHANEY |  |
| AGENCY COORDINATION/PERMIT ISSUES | BRIAN PECK |  |
| SCOPE, SCHEDULE AND BUDGET CONSIDERATIONS | JIM BRUNER | 330-786-4924 |
| EXTERNAL AGENCY INVOLVEMENT: |  |  |
| Indicate external agency involvement during identification of project issues affecting scope development. List the name and phone number of individual(s) representing each agency during the site visit. |  |  |
| AGENCY | NAME | PHONE NUMBER |
| FHWA Engineer*** |  |  |
| Other (LPA, MPO, etc.) |  |  |
| *** The FHWA Engineer should be invited on projects expected to require approval from Federal Highway Administration. |  |  |

| GENERAL EXISTING INFORMATION: Michael Craver |  |
| --- | --- |
| Legal Speed: | 55 |
| Design Speed: | 60 |
| Opening Year ADT (2029): | 3,500 |
| Design Year ADT (2049): | 3,600 |
| Trucks (24 Hour B&C): | 11% |
| Functional Classification: | 4 – Minor Arterial |
| Locale (Rural or Urban): | Rural |
| National Highway System (NHS): | No |

LOCAL PLANNING COORDINATION: Jim Bruner

Briefly describe local planning studies, bike/ped long range plans, aesthetics, etc. that will be considered throughout project development:

None.

DISTRICT HIGHWAY MANAGEMENT STAFF CONCERNS: Joe Parthemer

List any comments/requests from the District Highway Management Staff.

No comments or concerns at this time

| CRASH DATA: |  |  |
| --- | --- | --- |
| Has a Safety Study been completed in the project area within past three years |  | (Yes/No) |
| Is the project area highlighted on the Safety Integrated Project Maps |  | (Yes/No) |
| Based on a spatial query (using GCAT or TIMS) of the three most recent years of crash data, briefly summarize crash history including pedestrian and bicycle crashes. Indicate any design features that may be contributing to the observed crash pattern that may be addressed by the project. |  |  |
| ENVIRONMENTAL ISSUES: Sean Carpenter |  |  |
| Make a preliminary determination on whether the following resources are present within the project area. Is it possible that they will be affected by the project. Include the location and any other pertinent information for resources that may be affected. |  |  |
| Resource/Feature | Location/Comments |  |
| Parkland, nature preserves and wildlife areas {4(f)/6(f)} | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, the Grand River Wildlife Area is located within the project area and may be impacted depending on the need for right-of-way. |  |
| Threatened and Endangered Species and/or habitat | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, potential suitable wooded habitat (SWH) for the Federally-listed Indiana Bat (Myotis sodalis), Northern Long-Eared Bat (Myotis septentrionalis) and Tricolored Bat (Perimyotis subflavus) and State-listed Little Brown Bat (Myotis lucifugus) was identified within the project area. The project area is also located within the range of the Federally-listed Eastern Massasauga Rattlesnake. Potential habitat for the Eastern Massasauga Rattlesnake was identified within and/or adjacent to the project area and may be impacted by the project. Moreover, records for multiple State listed species including Northern Brook Lamprey (Ichthyomyzon fossor), Spotted Turtle (Clemmys guttata), Black Sandshell (Ligumia recta), Round Pigtoe (Pleurobema sintoxia), Kidney Shell (Ptychobranchus fasciolaris), Creek Heelsplitter (Lasmigona compressa), Round Hickorynut (Obovaria subrotunda), Rainbow (Villosa iris), Necklace Sedge (Carex projecta), Closed Gentian (Gentiana clausa), Straw Sedge (Carex straminea), Coarse Smartweed (Persicaria robustior), Spotted Pondweed (Potamogeton pulcher), Keeled Bur-reed (Sparganium androcladum), Northern Harrier (Circus hudsonius), were identified within and/or adjacent to the project area and may be impacted by the project. |  |
| Scenic River | Based on review of the ODOT, Transportation Information Mapping System (TIMS) conducted by ODOT, District 4 Environmental Section personnel in June 2025, no state or national scenic rivers were identified within 1,000 feet of the project area. |  |
| Existing wet areas/existing cattails/wetlands | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, potential high-quality wetlands were identified within and/or adjacent to the project area and may be impacted by the project. |  |
| Stream/river/waterway/jurisdictional ditch | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, several waterways, including Mud Run, were identified within and/or adjacent to the project area and may be impacted by the project. |  |
| Historic Resources (buildings, structures, objects) | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no known historic resources were identified within and/or adjacent to the project area. |  |
| Historic Bridge(s) | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no known historic bridges were identified within and/or adjacent to the project area. |  |
| National Historic Landmarks | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no known National Historic Landmarks were identified within and/or adjacent to the project area. |  |
| Archaeological Sites | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no known archaeological sites were identified within and/or adjacent to the project area. |  |
| Public Facilities | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no public facilities were identified within and/or adjacent to the project area. |  |
| Cemetery (modern and historic cemeteries) | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no known Ohio Genealogical Society (OGS) cemeteries were identified within and/or adjacent to the project area. |  |
| Farmland | Based on review of ODOTs Transportation Information Mapping System conducted by ODOT, District 4 Environmental Section personnel in June 2025, no farmland was identified within and/or adjacent to the project area. |  |
| Watershed Specific (i.e. Darby or Olentangy) NPDES Permit Area | No known Watershed Specific NPDES Permit Area(s) were identified within and/or adjacent to the project area. |  |
| Air Quality non-attainment area or concerns | This project does not add capacity, a new interchange or a new road on new alignment. Hence, this project will not result in any meaningful changes in traffic volumes, vehicle mix, location of the existing facility or any other factor that would cause an increase in emissions impacts relative to the No-Build Alternative. As such, FHWA has determined that this project will generate minimal air quality impacts for Clean Air Act criteria pollutants and has not been linked with any special MSAT concerns. Consequently, this project is exempt from analysis for MSATs. Trumbull County is not in a PM2.5 non-attainment or maintenance area. Therefore, a PM2.5 analysis is not required for this project. The State of Ohio is in attainment for CO at this time and no coordination or analysis is required. Trumbull County is in an Eight-Hour Ozone Nonattainment Area that requires consideration of the regional effects on ozone from federally funded projects or projects of regional significance. As the proposed project is listed in the 2024-2027 STIP and the STIP project description matches the proposed activities, ozone is addressed for the proposed project. |  |
| Landfill, Superfund, CERCLIS, RCRA, NPL, or industrial site(s), and/or evidence of hazardous materials | Based on review of the Ohio Regulated Properties Search (ORPS) Tool conducted by ODOT, District 4 Environmental Section personnel in June 2025, no known landfill, Superfund, CERCLIS, NPL, or industrial sites were identified within and/or adjacent to the project area. |  |
| Federal Emergency Management Agency (FEMA) floodplains | Based on review of the ODOT Transportation Information Mapping System (TIMS) by ODOT, District 4 Environmental Section personnel in June 2025, the project area is located within a designated Special Flood Hazard Area (SFHA) Zone A floodplain. |  |
| Lake Erie Coastal Management Area | Based on review of the ODOT, Transportation Information Mapping System (TIMS) conducted by ODOT, District 4 Environmental Section personnel in June 2025, the project area is not located within and/or adjacent to a Lake Erie Coastal Management Area. |  |
| Sole Source Aquifers | Based on review of the OhioEPA, Drinking Water Source Protection Area electronic mapping system by ODOT, District 4 Environmental Section personnel in June 2025, the project area is not within and/or adjacent to a Federally designated Sole Source Aquifer area. |  |
| Wellhead Protection Areas | Based on review of the OhioEPA, Drinking Water Source Protection Area electronic mapping system by ODOT, District 4 Environmental Section personnel in June 2025, the project area is not located within one (1) mile of a public water system well, intake or source water protection area. |  |
| Noise abatement issues | The proposed project is not a Type I project for noise, i.e. will not cause an increase in traffic volumes, will not substantially change the vehicle mix or speed, will not involve new roadways or substantially change the alignments or shielding effects of the existing roadway. Therefore, this project is deemed unrelated to increased traffic noise traffic. In accordance with the current ODOT Noise Manual, a traffic noise analysis is not required for this project. |  |
| Coordination with Conservancy Districts | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, the project area is not located within and/or adjacent to a Conservancy District. |  |
| Other environmental issues | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no other environmental issues were identified within the project area. |  |

| GEOMETRIC DESIGN CONTROLLING CRITERIA: Matt Chaney |  |
| --- | --- |
| Consider design speed, design functional classification, land use, and available traffic data to make a preliminary determination as to the geometric standards for the project and potential for design exceptions. Note exceptions for low volume roadways. |  |
| Design Criteria | Location/Comments |
| Lane Width | Match existing |
| Shoulder Width | Match existing |
| Horizontal Curve Radius | N/A |
| Maximum Grade | Match existing |
| Stopping Sight Distance (Horizontal and Crest Vertical Curves) | Match existing vertical curve if present |
| Superelevation Rate | N/A |
| Vertical Clearance | N/A |
| Pavement Cross Slope | Meet existing at begin and end of full depth replacement. Transition pavement cross slope to match bridge deck cross slopes. |
| Design Loading Structural Capacity |  |

| OTHER GEOMETRIC DESIGN ISSUES: Matt Chaney |  |
| --- | --- |
| Indicate if the following geometric issues are present or should be considered during project development. Consider work on the mainline as well as any side roads or service roads. Provide additional comments as needed. |  |
| #### Design Issues | #### Location/Comments |
| Does the horizontal alignment have an excessive deflection? | N/A, horizontal alignment should match existing |
| Do the Intersection Angles or Crossroad Alignment meet design standards? | N/A |
| Is driver comfort an issue due to the vertical curvature or breaks in the grade? | No. Match existing vertical curve if present |
| Does the shoulder width on a structure allow for a minimum width of 4’ from the edge of the traveled way to the face of any barrier? | Yes, match existing bridge width. |
| Has a minimum width of 4’ from the edge of the traveled way to the face of any barrier? | Yes, match existing bridge width. Ensure all guardrail is set back a minimum of 4ft from the edge line. |
| Does intersection sight distance need to be improved? | No. Verify that guardrail placement doesn’t create a sight distance issue with adjacent driveways if present. Consider using MGS Type B Anchor Assemblies near driveways. |
| List unprotected hazards that appear to be in the clear zone. | Nothing is apparent |
| Should existing access control be revised to improve safety? | No |
| Are there any drive locations that will require special attention during design (e.g., very steep grades, high volume commercial drives, drives close to bridges or intersections)? | No. But if a driveway apron is within the full depth limits, replace apron as necessary. |
| Do the existing intersection radius returns need to be modified to improve pedestrian crossing safety? | N/A |
| Do the existing intersection radius returns need to be modified or truck aprons added to accommodate turning movements of large trucks? | N/A |
| Does grading need to be upgraded? To what criteria (e.g., clear zone, safety, standard)? Consider potential right of way and other impacts when considering grading method. | No. This is just a superstructure replacement, we will not want to purchase R/W for slope work. |
| Are new or updated curb ramps needed? Refer to the Curb Ramp Measuring Guide | No |
| If constructing a new roadway, will it be a connection between two existing NHS Routes? | N/A |
| If traffic control at an intersection is being changed from stop control to signalization, does the profile of the stop condition road need to be upgraded to accommodate faster traffic? | N/A |
| Are multiple intersection control types being considered? Is an Intersection Control Evaluation (Intersection Control Evaluation (ICE) ¦ Ohio Department of Transportation) applicable? | N/A |
| Are there any other geometric issues? Describe. | No. But, the project should replace the entire runs of guardrail on all approaches. The existing guardrail is Type 5, upgrade to MGS. |

| GEOTECHNICAL ISSUES: |  |
| --- | --- |
| Based on the information compiled during this study indicate whether or not the following geotechnical issues are present or should be further considered during project development. Provide additional comments as needed. Refer to Section 302.2 of the ODOT Specifications for Geotechnical Explorations for literature search resources. |  |
| #### Design Issues | #### Location/Comments |
| Is there evidence of soil drainage problems (e.g., wet or pumping subgrade, standing water, the presence of seeps, wetlands, swamps, bogs)? | N/A |
| Will construction be impacted based on the groundwater table? | N/A |
| Is there evidence of any embankment or foundation problems (e.g., differential settlement, sag, foundation failures, slope failures, scours, evidence of channel migrations)? | N/A |
| Is there evidence of any slope instability (soil or rock)? | N/A |
| Is there evidence of unsuitable materials (e.g., presence of debris or man-made fills or waste pits containing these materials, indications from old soil borings)? | N/A |
| Is there evidence of rock strata (e.g., presence of exposed bedrock, rock on the old borings)? | N/A |
| Is there evidence of active, reclaimed or abandoned surface mines? Evidence of quarries? | N/A |
| Is there information pertaining to the existence of underground mines? | N/A |
| Is there Acid Mine Drainage present within the study area? | N/A |
| Are there any other geotechnical issues? Specify. | N/A |

| PAVEMENT ISSUES: BRIAN ROSS |  |
| --- | --- |
| Indicate if the following pavement issues are present or should be considered during project development. Side road and service road work should be considered in this assessment. Provide additional comments as needed. |  |
| Design Issue | Location/Comments |
| Do dynaflect tests indicate the existing pavement is in poor condition? | N/A |
| Are joint repairs needed? | No. |
| Are pressure relief joints needed? | No. |
| Does curb need to be replaced due to deteriorated condition or lack of curb reveal? | Replace as needed for roadway profile/geometry changes. |
| Has the site received repeated resurfacings in recent years? | No. |
| Does pavement deterioration appear to be caused by drainage or geotechnical problems? | No. |
| Are there any other pavement issues? Specify. | Replace as needed for roadway profile/geometry changes. |

| STRUCTURAL ISSUES: BRIAN ROSS |  |
| --- | --- |
| Indicate if the following structure issues are present or should be considered during project development. Provide additional comments as needed. The Bridge Inspection reports should be evaluated and attached. Provide a separate table for each structure. |  |
| Structure Number: 7805713 | TRU-88-0430 |
| Design Issue | Location/Comments |
| Is it possible for the structure to be replaced with a prefabricated box culvert or 3-sided box? | No. |
| Is the deck delaminated? Specify. | The top flange of box beam members is obscured by an asphalt overlay. The current overlay is in satisfactory condition. See superstructure section below for underside delaminations. |
| Is non-destructive testing needed to determine the Amount of delamination? | Underside can be sounded for possible additional locations. |
| Are there areas to be patched/repaired on the deck? | Delaminations or spalls to box beam members are not reliably repaired by patching. Only replacement can address these issues. |
| Is the bridge a poor candidate for an overlay? Specify type of overlay if known. | Effectiveness of AC overlays has been inconsistent in the past for other non-composite box beam structures. |
| Does the bridge rail violate current standards? | Yes. |
| Is fatigue analysis required? | No. |
| Should all fatigue prone details be retrofitted or replaced? Specify. | No. No steel structural members |
| Is there any evidence of substructure movement (e.g., settlement, rotation)? | None observed at this time. |
| Is elimination of the deck joint possible? What modifications are necessary? | N/A |
| Is it possible for the hinges to be removed to make the members continuous? | N/A |
| Is there any evidence that the bridge does not meet hydraulic capacity? | No evidence of overtopping. |
| Are there existing sidewalks on or adjacent to the bridge? | No. |
| Is Vandal Protection Fencing required in accordance with the BDM? | No. |
| Will the structure work require any special maintenance of traffic (e.g., closing of roadway for erection of beams, maintenance of waterway traffic, location of cut line, etc.)? Specify. | Yes, complete closure will be needed to replace the superstructure. |
| Does the bridge need to accommodate future roadway lanes, bicycle lanes, a shared use path, shoulder, or railroad tracks? | No. |
| Will temporary shoring be required next to the railroad? | N/A. RR is not present at this location. |
| Describe any issues with the bridge deck (curb, sidewalk, railing, surface, median, drainage, expansion joints, etc.). | Spalling in the facia beams at some of the railing anchors. Waterproofing layer is compromised given the presence of efflorescence in box beam joints. |
| Describe any issues with the bridge superstructure (alignment, beams/girders/slab, bearing devices, etc.). | Superstructure and deck are currently rated 5 – fair condition. There is spalling on the deck underside/bottom flange of box beams 9, 7, ,6 and 5 in span 1. Strands are exposed in the edge of beam 7. Significant efflorescence is present at these locations. Facia beams have spalled over the pier caps |
| Describe any issues with the bridge substructure (abutments, piers, backwalls, wingwalls, scour, etc.). | The substructure (rated 7) is in good condition. There is minor horizontal cracking present in both abutments. Tight vertical cracks have been observed in pier 2 above the pile locations. Pile encasements appear to be in great condition. |
| Describe any issues with the channel (i.e. alignment, erosion, etc.) | The channel (rated 8) is in very good condition. There is some vegetation growth in the channel directly downstream. |
| Describe any issues with the bridge approaches (i.e. pavement, guardrail, etc.) | Approach pavement is in satisfactory condition. |
| Are there any other structure related issues? Specify. | Nothing else to add at this time. |
| HYDRAULIC ISSUES: Mike Palagano |  |
| Indicate if the following drainage issues are present or should be considered during project development. Side road and service road work should be considered in this assessment. Any available Culvert Inspection reports should be evaluated and attached. Provide additional comments as needed. |  |
| Design Issue | Comments |
| Does the existing drainage system appear to be appropriately sized and functioning properly? Describe deficiencies. | No historic flooding events or closing of road recorded in TIMS at this location. |
| Is there evidence of alignment or flow velocity problems (e.g., scour, bank erosions, silting) at culvert inlets or outlets? | Do not see evidence of scour at piers. Stream appears to have silt/muck buildup under structure. |
| Are there sinkholes or other deterioration in the pavement that would indicate separations in the existing pipes? | None observed. |
| Is the exposed curb height in existing gutters inadequate to contain flow (include height of proposed resurfacing)? | N/A |
| Does the project affect a wetland or waterway (e.g., stream, river, jurisdictional ditch)? | Over a branch of the Grand River, looks like it’s located within the Grand River Wildlife Area. Not located over state scenic or wild river. Expect jurisdictional stream and wetlands. Zone A floodplains |
| Will channel relocation be required? | No |
| Will post construction BMPs be required that could impact R/W or utilities? | No |
| Are existing underdrain outlets functioning properly? | No evidence of improper underdrain function |
| Does the drainage work warrant any special maintenance of traffic considerations? | Nothing outside of the ordinary for superstructure replacement |
| Are there any other hydraulic issues? Describe. | Unaware of any other hydraulic issues. |

| TSMO CONSIDERATIONS: Aaron Conley |  |
| --- | --- |
| Briefly describe the opportunities for managing congestion or traffic issues using TSMO strategies or improvements. Consider opportunities to upgrade or install systems management and operations infrastructure: TSMO infrastructure includes communications equipment, travel time signs, signals, changeable message signs, traffic cameras, traffic signal systems, other remote field devices and data collection equipment, conduit and any supporting fiber optics. TOAST is the Traffic Operations Assessment System Tool. For additional TSMO information see http://www.dot.state.oh.us/Divisions/Operations/Traffic/miscellaneous/Pages/TSMO.aspx |  |
| Design Issue | Location/Comments |
| Does the project area contain a Hot Spot identified in TOAST? If so, what is the TOAST ranking? | STRUSR00088**C_04.175_13.946_F (Score 84%, Statewide Overall Rank #844) |
| Does the project area have an operations master plan (or has this site been discussed with the District TSMO Coordinator)? | No |
| Would operations benefit from TMC coverage of the project area? (RWIS, travel time boards, cameras, communications) | No |
| Are there opportunities for initiating or upgrading TSMO infrastructure? | No |
| Does this project support any TSMO strategies such as (Smartlane, VSL, Coordinated traffic signals, etc.) | No |
| Does this project require multi-jurisdictional coordination, agreements, funding, etc.? | No |
| What existing TSMO infrastructure is in place? Will it need to be moved or maintained in place? | None |
| Are there any local TSMO infrastructure recommendations in the project area? (ex. Include emergency or transit traffic signal pre-emption, dynamic message signs or signal coordination) | No |
| What MPO ITS architecture is already in place or planned? Consult the MPO ITS architecture plan, if applicable. | Unknown |
| Categories of potential ITS for this study area/project include: Exempt, Low, or High risk? Ref: TEM, 1-pager for CFR 940. | Exempt |
| Could this project expand an existing device or communications system? | No |
| What type of device communications and equipment exists? | None |
| Should this location have communications added or upgraded? | No |
| Will additional conduit be necessary for future infrastructure/communications? (ex. in barrier wall) | No |
| Will existing device power or communications drops be disrupted? | No |
| Does this project require a new traffic signal timing plan? | No |
| Are the current traffic signal(s) being upgraded to a system? | No |
| Are there alternative routes available/identified for incident management? | No |
| Is this a Traffic Incident Management Note eligible project? | Unknown |
| OTHER TSMO Considerations: None |  |
| None |  |

| TRAFFIC CONTROL ISSUES: Aaron Conley |  |
| --- | --- |
| Indicate if the following traffic control (signals, signing, pavement markings, etc.) issues are present or should be considered during project development. Provide additional comments as needed. |  |
| Design Issue | Comments |
| Are there any obvious deviations from requirements of the Ohio Manual of Uniform Traffic Control Devices (OMUTCD)? | No |
| Will coordination with Ohio Rail Development Commission (ORDC) be required (i.e. at-grade railroad crossings located within 400' of an intersection within the project area)? | No |
| Will pavement widening affect pole locations? | N/A |
| Will resurfacing affect signal height? | N/A |
| Does it appear that any traffic control items will fall outside the existing right of way limits (e.g., large signs, strain poles)? | N/A |
| Are there any crashes that can be related to existing signal deficiencies (e.g., timing, lack of protected turn phase)? | N/A |
| Do pedestrian signals and push buttons need to be installed or upgraded? | N/A |
| Do turn lane lengths appear to have sufficient storage capacity? | N/A |
| Does the controller need to be upgraded? | N/A |
| Do proprietary materials need to be specified? | No |
| Should signs or signal installations be supplemented with lighting? | No |
| Are any Tourist Oriented Directional Signs (TODS) or LOGO signs present? | No |
| Are there any other traffic control issues? Specify. | None |

| UTILITY ISSUES: Peter Dinh |  |
| --- | --- |
| Indicate if the following utility issues are present or should be considered during project development. Provide additional comments as needed. |  |
| Design Issue | Location/Comments |
| Do existing utilities need to be relocated? If so, please identify. | Possible. Low hanging telecom and power |
| Would the project benefit from Subsurface Utility Engineering (SUE) Level A? | More than likely, no |
| Are there existing utilities on an existing structure that need to be relocated? | No |
| Are there any specific utility requirements or concerns? Specify. | No |
| Are there water or sanitary lines that will be relocated as part of the ODOT contract? | No |
| Are there any other utility issues? Specify. | No |

| # MAINTENANCE OF TRAFFIC ISSUES: |  |
| --- | --- |
| Indicate if the following maintenance of traffic issues are present or should be considered during project development. Provide additional comments as needed. |  |
| Design Issue | Location/Comments |
| Are there bridge load limits within the work limits or in the nearby area that would limit the available signed official detour or unsigned local alternate routes? | Bridge load limits will not be an issue for the signed official detour using SR 534 / SR 87 / SR-45. Unsigned local alternate routes are in poor condition. |
| Is the project located on the National Truck Network? | Yes. |
| Are there overhead bridges with existing vertical clearance issues or that may become vertical clearance issues (e.g. shifting traffic to the shoulder, adding pavement without milling first, etc.) | N/A |
| Are there pinch points within the work area that that would prevent the installation of temporary pavement for maintaining the existing number of lanes? If yes, identify the location and type of width restraints. (e.g., median wall, at grade bridge, overhead bridge piers, trees, historic markers, etc.) | Temporary pavement could be added to maintain one signalized lane during construction. Considering the traffic volume, detour availability, and the project scope the most efficient and cost-effective MOT option is to close and detour SR-88. |
| Are there visible signs of pavement condition deterioration in the driving lanes? On the shoulders? If yes, identify location and estimated degree of deterioration and if further testing is needed. | No. PCR rating of 90 during 2024 assessment. |
| Are there nearby schools that may be adversely impacted by the proposed work? If yes, identify names, location and school districts. | Busing routes for the Bristol Local School District (330.889.3882) could be affected by this work if closure occurs during the school year. |
| Are there nearby emergency services (e.g., hospital, fire, police, EMS, etc.) that may be adversely impacted by the proposed work? If yes, identify locations and names. | Farmington Township (330.889.3024) Bristol Fire Department (330.889.2176) |
| Are there significant traffic generators nearby that may be adversely impacted by the proposed work? (e.g., industries, factories, sports arenas, etc.) | No. |
| What is the width of the existing pavement? Will temporary pavement be needed to maintain the existing number of travel lanes? | 24’ |
| What geometric features exist within the work area and within the area of influence of the work area that may impact sight distances and/or flow of traffic? (e.g., horizontal/vertical curves, blind driveways, intersections, entrance/exit ramps, railroad crossings, etc.) | N/A |
| Are there sidewalks or paths within or leading to/from the work area that need to be closed? | No. |
| If sidewalk/path needs to be closed, can users be detoured on the existing sidewalk system or will a temporary pedestrian and/or bicycle pathway need to be included in the plan? | N/A |
| Are transit stops present within the work area? | No. |
| Are there culverts within the work area that may need to be lengthened to accommodate temporary widening? If so, identify locations and culvert numbers. | No. |
| Are there any known existing drainage issues within the work limits? If yes, special attention needs to be given to ensuring temporary drainage can be accomplished. | No. |
| Will personal and/or business driveways be adversely impacted or need to be closed for any amount of time? | No. |
| Is the project located in or nearby an area of regional significance with a potential to cause controversy or negative public feedback or political scrutiny? | No. |
| Is there enough width to provide safe construction access? If no, what other means of access can be provided? | Construction access will be provided at the point of roadway closure. |
| Is there potential for the need to require right-of-way acquisition? | Right-of-Way acquisition is not expected for MOT. |
| Is there room in the median for the construction of crossover pavement within the project limits and beyond the project limits on either end? If yes, identify potential locations for crossover locations. | N/A. |
| Are short duration road closures going to be required? (e.g., bridge demo, steel erection, overhead utility installation/removal, etc.). If yes, is there an opportunity for diversion of the traffic to other routes or to the ramps on a diamond interchange? Identify the potential diversion routes. | No. |
| Will there be a need for temporary structures (full or partial) in order to maintain the existing number of lanes? | No. |
| Is there power available within or nearby the project location for temporary lighting and/or temporary signals? | Power is available if a temporary signal is to be used to maintain a signalized lane for MOT. |
| Will there be a need for additional signal heads (drives and/or side roads) or temporary signal timing/coordination? | No. |
| Are there any Traffic Incident Management features, such as hydrants, pull-offs, turn-arounds, etc.? | No. |
| Are there issues that may limit the construction timeframe? (e.g., sporting or other significant regional events, work in streams, suitable wooded habitat, school, etc.). If yes, list them. | No. |
| Would this project potentially benefit from the application of innovative contracting method (e.g., A+B to open bridge to traffic before school starts, etc.)? If yes, which method? | No. |
| Will there be a need to restrict existing movements during construction? (e.g., no left turns, etc.) | The project will be built while SR-88 is closed and detoured. |
| Is there an opportunity (or potential need) to implement any work zone ITS components? (e.g., work zone egress warning, queue detection and warning, CCTV, DDMS, etc.) | No. |
| How big of an impact will the project have on queue lengths and congestion? If significant, a MOT Policy Exception Request may be required per Traffic Management in Work Zones Policy (21-008(P)) and Standard Procedure (123-001(SP)). | N/A. |
| Does this project require an MOTAA? All Path 4 & 5 projects along with Path 3 projects on Interstate/Interstate look-alikes need to have a Maintenance of Traffic Alternatives Analysis Completed. Refer to TEM Section 630-5 | No. |

| RIGHT OF WAY/SURVEY ISSUES: |  |
| --- | --- |
| Indicate if right of way or survey issues are present or should be considered during project development. Provide additional comments as needed. |  |
| Design Issue | Location/Comments |
| Will there be any work beyond the existing right of way limits? | No |
| Will relocation of residences be involved? | No |
| Will relocation of businesses be involved? | No |
| Will the project require modifying the access control to any properties? | No |
| Identify significant right of way encroachments (i.e. large commercial business signs, etc.)? | None |
| Will temporary parcels be needed (e.g., for drive work)? | Maybe |
| Will additional right of way be needed for utility relocations? | Maybe |
| Are there any specific property owner concerns? If so, list property owners and concerns. | No |
| Are work agreements prohibited for any reason? | No |
| Are there any other right of way or survey issues? Specify. | No |

| CONSTRUCTION ISSUES: Tom Kopnicky |  |  |
| --- | --- | --- |
| Indicate if the following issues are present or should be considered during project development. Provide additional comments as needed. |  |  |
| Issue | Location/Comments |  |
| Will any of the construction activity take place over, under, or near railroad property? | No |  |
| Could material with long lead times for delivery have an impact on the construction schedule and/or project completion (e.g., strain poles, large box culverts, steel beams, etc.)? | No |  |
| Are there any concerns related to existing or proposed lighting (e.g., light trespass, river navigation, airway clearance)? |  | No |  |
| Compare the Begin/End construction dates with the Scope of Work. Is the construction schedule reasonable? | Begin end dates to be adjusted once a sale date is nailed down. Suggest 90 day construction duration. |  |
| Examine the existing pavement condition and repair history. Calculate potential pavement repair quantities. | N/A |  |
| Note manhole lid elevations versus proposed paving thickness. Will manhole lids or valve boxes need adjusted after paving? | N/A |  |
| Is there a need for Echelon Paving? | N/A |  |
| Examine the rideability of the approach slab to the roadway/bridge joint. | Acceptable |  |
| Will the project have impacts to nearby residents/businesses? Will site access occur down steep side slopes or through properties adjacent to project site? | Superstructure replacement will require a road closure. |  |
| Examine existing guardrail condition, height and length of need. What is the condition of the slopes behind guardrail? Will additional grading or fill be required for guardrail replacement? | Replace guardrail. Slopes are good and no grading or fill is needed. |  |
| Is more space or room needed for construction? Is Temporary or Permanent R/W required for utility relocations, construction of structures, drainage ditches, etc.? | No |  |
| Is there enough clearance to overhead utility lines for cranes and concrete pump trucks? | Yes |  |
| Will there be instream work? | Possible if substructure repair is required. |  |
| Will Temporary shoring/sheeting, cofferdams or work pads be required to complete the proposed work? Anticipated Permitting (see Agency Coordination/Permit Issues section above) | No |  |
| Will the road need to be detoured to complete construction? What are the possible detour routes? | Yes. SR 534 / SR 87 / SR 45 |  |
| Where are the potential staging areas for the contractor? | Within the road closure limits. |  |

| PEDESTRIAN AND BICYCLE ISSUES: Matt Chaney |  |
| --- | --- |
| Indicate if the following pedestrian and bicycle facilities are present or should be considered for implementation during project development. - Pedestrian facilities: sidewalks, shared use paths, enhanced crossings, signs/signals, and lighting. - Bicycle facilities: bike lanes, improved shoulders, shared use paths, crossing treatments, signs/signals, and lighting. Provide additional comments as needed. For additional bicycle and pedestrian data, see the TIMS Active Transportation Map Viewer: https://gis.dot.state.oh.us/tims/Map/ActiveTransportation and discuss with the District Bike & Ped Contact. |  |
| Issue | Location/Comments |
| Are there visible signs of deterioration on sidewalks or missing sidewalks? | N/A |
| Is there a minimum 4’ clearance along sidewalks? (i.e. poles that obstruct the sidewalk) | N/A |
| Are there visible sign of deterioration in bike lanes/shoulders or missing bike facilities? | N/A |
| Do crossings for bicyclists and/or pedestrians need to be improved or installed? | N/A |
| Is on-street parking set back 20 feet from the crosswalk (both marked and unmarked) at an intersection or set back 30 feet of the approach to any flashing beacon, stop sign or traffic control device? (See ORC 4511.68) | N/A |
| Is there evidence of the need for a midblock crossing? (i.e. pedestrian crashes, signalized intersection spacing exceeds 600 ft., presence of midblock transit stops or path, pedestrian generators and destinations). Refer to FHWA Guide for Improving Pedestrian Safety at Uncontrolled Intersections | N/A |
| Does the project area have an active transportation plan in place (or other multimodal plan such as a bicycle, pedestrian, school travel plan, or metropolitan transportation plan). Contact pertinent local public agencies for more information. | N/A |
| Is there existing bicycle or pedestrian usage along this corridor? (For statewide volume data visit ODOT’s Non-Motorized Database System.) Visible indicators of usage include counts, worn paths, transit stops, etc. | N/A |
| Is the project located on a designated or proposed bike route (local, regional, state or US)? | No |
| What is the Level of Traffic Stress (1-4)? (LTS 1 and 2 are considered comfortable for the mainstream adult population.) (See Level of Traffic Stress calculation tool. This data is pre-calculated for the State & US Bike Route System.) | N/A |
| Does the project area have high Active Transportation Demand and high Active Transportation Need (Scores of 3 or 4)? (Use the Identify Features tool to select project area and view scores for Demand_ Mapping and Need_Mapping. scores.) | No |
| What are the proposed bicycle lane widths? | N/A |
| What are the proposed sidewalk and shared use path widths (and buffer width)? | N/A |
| If bike/ped accommodations require additional ROW not planned for the project, can a future project provide this? | N/A |

| AGENCY COORDINATION/PERMIT ISSUES: Sean Carpenter |  |
| --- | --- |
| Indicate if the following permit issues are present or should be considered during project development. Provide additional comments as needed. |  |
| Issue | Location/Comments |
| Will an Individual US Army Corps of Engineers/ Environmental Protection Agency 404/401 permit be required? | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, potential high-quality wetlands were identified within and/or adjacent to the project area. Additionally, several waterways, including Mud Run, were identified within and/or adjacent to the project area. These resources may be impacted depending on the scope of the project, however, these impacts are unlikely to exceed the thresholds for an individual 404/401 permit. |
| Will a Section 408 Permission be required for work within an USACE Civil Works (dams, levees, locks, navigation channel, etc.)? Refer to the National Levee Database (army.mil); National Inventory of Dams (army.mil); Louisville District (arcgis.com) Not all projects are found within these directories. Consult with OES during planning to discuss Section 408 coordination. (Note, Section 9 or Section 10 permit will most likely trigger Section 408 coordination.) | Based on review of the USACE National Inventory of Dams mapping conducted by ODOT, District 4 Environmental Section personnel in June 2025, no levees, dams or other 408 civil works projects were identified within and/or adjacent to the project area. No Section 408 Permission is required. |
| Will a Coast Guard (Section 9) permit be required? | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, no Section 9 waterways were identified within the project area, therefore, a Coast Guard permit will not be required. |
| Is review by a local public agency or project sponsor required? Specify. | A review by a local public agency or project sponsor is not necessary since this is an ODOT Let project. |
| Is State Historic Preservation Office (SHPO) coordination for work involving historic bridges or historic properties required? | Based on review of the available mapping conducted by ODOT, District 4 Environmental Section personnel in June 2025, no known historic resources, bridges, landmarks, OGS cemeteries or OAI sites were identified within the project area, therefore, coordination with the SHPO is not anticipated. |
| Is coordination with ODNR for work involving State Scenic Rivers, State Wildlife Areas or State Recreational Areas required? | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, the Grand River Wildlife Area is located within the project area, therefore, coordination with ODNR may be required depending on the need for right-of-way. |
| Is coordination with any other agency required? | Based on review of available information by ODOT, District 4 Environmental Section personnel in June 2025, potential suitable wooded habitat (SWH) for the Federally-listed Indiana Bat (Myotis sodalis), Northern Long-Eared Bat (Myotis septentrionalis) and Tricolored Bat (Perimyotis subflavus) and State-listed Little Brown Bat (Myotis lucifugus) was identified within the project area. The project area is also located within the range of the Federally-listed Eastern Massasauga Rattlesnake. Potential habitat for the Eastern Massasauga Rattlesnake was identified within and/or adjacent to the project area and may be impacted by the project. Moreover, records for multiple State listed species including Northern Brook Lamprey (Ichthyomyzon fossor), Spotted Turtle (Clemmys guttata), Black Sandshell (Ligumia recta), Round Pigtoe (Pleurobema sintoxia), Kidney Shell (Ptychobranchus fasciolaris), Creek Heelsplitter (Lasmigona compressa), Round Hickorynut (Obovaria subrotunda), Rainbow (Villosa iris), Necklace Sedge (Carex projecta), Closed Gentian (Gentiana clausa), Straw Sedge (Carex straminea), Coarse Smartweed (Persicaria robustior), Spotted Pondweed (Potamogeton pulcher), Keeled Bur-reed (Sparganium androcladum), Northern Harrier (Circus hudsonius), were identified within and/or adjacent to the project area and may be impacted by the project. Coordination with U.S. Fish and Wildlife Service and ODNR may be required if impacts occur to these species. |

| SCOPE, SCHEDULE AND BUDGET CONSIDERATIONS: Jim Bruner |  |
| --- | --- |
| Based on the responses to the above items, do any of the following need to be modified? |  |
| Issue | Comments |
| Conceptual scope | Not at this time. |
| Work limits | Not at this time |
| Probable environmental document type | C2 |
| Project Path classification | Path 2 |
| Schedule | Possible coordination with PID 121248 SR 534 Chip Seal project. |
| Budget | Not at this time. |