## Basic Schedule Layout
Initial Project Schedule - Q4 FY2029
| Milestone | Date
| Project Initiation Package | 2025-10-02
| Initial Project Scope Complete | 2025-10-24
PE-ENV (FY2026) | Authorized Design Consultant | 2026-05-22 | 4.5 months for consultant (Jan. 2026 programmatic)
| Stage 1 Plans - Submitted | 2027-01-25 | 8 months for stage 1 design
| NEPA Start Date | 2027-02-08
| Stage 1 Plans - Complete | 2027-03-05
| Preliminary R/W Plans - Submitted | 2027-04-02
| Preliminary R/W Plans - Approved | 2027-05-03
| Stage 2 Plans - Submitted | 2027-08-06 | 5 months for stage 2 design
| Compliance R/W Plans - Submitted | 2027-08-06
| Stage 2 Plans - Complete | 2027-09-17
| Compliance R/W Plans - Approved | 2027-09-17
| Environmental Document Submitted | 2027-10-04
| Final R/W Plan Submission - Approved | 2027-10-18
| Environmental Document Approved | 2027-11-05 | 9 months to approve enviro doc
ROW (FY2028) | R/W Authorized | 2027-12-10
PE-DD (FY2028) | Stage 3 Plans - Submitted | 2028-06-16 | 6 months for stage 3 design
| Stage 3 Plans - Complete | 2028-07-28
| Final Tracings - Submitted | 2028-10-27 | 3 months to address stage 3 comments
| R/W Acquisition Complete | 2028-12-08 | 12 months for R/W acquisition
| Final Tracings - Complete | 2028-12-11
| Utility Note Complete | 2028-12-20
| District R/W Certification | 2029-12-22
| Plan Package Submitted to C.O. | 2028-12-29
| Plan Package Received in C.O. | 2029-01-01
| Sale | 2029-04-01
CC/CE (FY2029) | Award | 2029-04-01
| Estimated Begin Construction | 2029-06-11
| Estimated End Construction | 2030-05-24