WAR/CLI US 22 19.24/2.62

PID 124605

Programmatic Scope Narrative

Project Description:

Improve safety by constructing a single lane roundabout at US-22 at Clarksville Rd, and US-22 at SR-380/Creek Rd.

FTP Site:  https://ftp.dot.state.oh.us/pub/Districts/D08/124605/

Upcoming work planned near this project includes:

- PID 116337 is a proposed AC Overlay with Repairs in FY2028 from log point 17.26-19.76

- PID 100640 is a planned AC Overlay without Repairs in FY2026 from log point 0.00-7.21. This project is awarded 12/29/2025.

For more information on planned projects in the area, please visit TIMS or District 8’s MYWP site at http://www.dot.state.oh.us/districts/D08/Pages/District-8-Multi-Year-Work-Plan.aspx.

Stakeholders:

Stakeholders identified at the time of project initiation are as follows:

- ODOT District 8 and Central Office (plan review, detour coordination)

- Warren County Engineer’s Office (plan review, detour coordination)

- Clinton County Engineer’s Office (plan review, detour coordination)

- Washington Township (plan review, detour coordination)

- Adams Township (plan review, detour coordination)

- Utilities within the project limits (plan review)

- Schools (detour notification)

- Emergency responders (detour notification)

- FHWA

- Environmental resource agencies (USACE, EPA, SHPO, USFW)

- Residents, business owners and farmers along the corridor (detour notification)

Discipline specific scope items have been identified below.

Roadway:

- Follow ODOT’s L&D Manuals for geometrics.

- The Intersection Design Vehicle for this project shall be a WB-67.  The Intersection Check Vehicle shall be a WisDOT WB-92 traveling through both intersections on US 22. Coordination with CO Permits needed to determine movements to be analyzed. (i.e. do turns to or from Clarksville Rd or Creek Rd need to be analyzed?)

- The roundabout central truck apron and outside truck aprons shall be designed to accommodate the Design Check Vehicle.

  - To accommodate lowboy trailers, the profile grade of the circulatory profile shall be within the range of 0.75% - 1.00%, and cross slopes of truck aprons shall be 1%.

- The design shall accommodate agricultural equipment.

  - Provide 10’ graded shoulders (consider less for ROW) beyond the back of Type 3 curb on US 22 and Clarksville Rd and SR-380 to accommodate large agricultural equipment navigating around vertical elements.  Provide a 2’ graded shoulder beyond the back of curb on outside truck aprons.

  - Large tractors and combines will need to offtrack past the curb lines, thus curbs shall be easily mountable and not cause rubbing on tire sidewalls.

    - Use Type 3 curb rolled curb on the approaches to the roundabout.

    - Use Type 9 curb on the truck aprons.

    - Use a Type 9 style curb on splitter islands.  A gutter does not need to be provided unless necessary for drainage.

  - Offset the spacing of all vertical elements including utility poles, signs, light poles, etc. to avoid pinch points for wide agricultural equipment and oversized loads.

- A pre-stage 1 geometric submission will be required to set the roundabout design parameters.  Allow standard 30-day review by ODOT. This review will be required prior to the designer completing detailed design efforts for the stage 1 submission.  The following shall be included in this submission:

  - Figure 403-2 Roundabout Design Parameters.

  - Entry Angle.

  - Fastest Path Analysis.

  - Roundabout Geometric Layout.

  - Roundabout Sight Distance.

  - Turning Templates showing all movements of the Design and Check Vehicles.

- At this time, no pedestrian facilities (sidewalk, curb ramps, crosswalks, etc. ) are anticipated to be included with this project.

Aesthetics

- The ODOT District 8 Roundabout Aesthetic Design Elements guide shall be used to identify baseline treatments for the roundabout intersection.

- The ODOT Project Manager shall coordinate with Warren County Engineer’s Office, Clinton County Engineer’s Office, Washington Township and Adams Township to confirm they support proceeding with the District 8 roundabout baseline aesthetics.  If the local public agencies choose to construct upgraded central island aesthetics via permit after the project is constructed, then the central island shall be seeded in lieu of the District 8 baseline treatment.

- Detailed information and an example location has been uploaded to the FTP site.

Traffic Control:

- Replace existing pavement markings.  Use Item 644 - Thermoplastic on asphalt surfaces and Item 646 - Epoxy on concrete surfaces.

- Install RPMs on US 22 and SR-380. Coordinate with Warren/Clinton County Engineer’s Office regarding RPM’s on local routes.

- Replace the intersection ahead warning signs with the appropriate intersection warning signs for a roundabout, with advisory speed, per the OMUTCD and ODOT’s TEM. Flashing warning signs on US 22 to remain (just switch out intersection type)

- Install all new signs per the OMUTCD and ODOT’s TEM.

- Intersection lighting for the new roundabout will be required per ODOT standards. All light poles shall be offset from the back of curb on roadway approaches to allow space for agricultural equipment. Light poles may need to be taller or have longer bracket arms to meet lighting criteria at this offset. Glare shields may also be necessary, depending on the crops that abut the roundabout.

- Signs shall be located at a location from the back of curb on roadway approaches to allow space for agricultural equipment. There may be alternate locations to place signs outside of splitter islands to reduce vehicle impacts. Signs in islands can use a median mounted support to make reinstallation easier.

Traffic Analysis:

Not applicable.

Design Designations:

The design designations were developed by utilizing ODOT’s Traffic Forecast Management System. (Design designation values not available on side roads Clarksville Rd or Creek Rd)

| LOCATION | US-22 SLM 18.26-19.76 | US-22 SLM 0.00-2.62 | US-22 SLM 2.62-4.07 | SR-380 SLM 0.00-0.49 |
| --- | --- | --- | --- | --- |
| Functional Classification | 05 Major Collector (Rural) | 05 Major Collector (Rural) | 05 Major Collector (Rural) | 05 Major Collector (Rural) |
| OPENING YEAR AADT (2029) | 2,200 | 3,000 | 5,000 | 2,400 |
| DESIGN YEAR AADT (2049) | 2,400 | 3,100 | 5,100 | 2,600 |
| DESIGN HOURLY VOLUME (2049) | 300 | 450 | 700 | 450 |
| DIRECTIONAL DISTRIBUTION | 0.56 | 0.60 | 0.54 | 0.64 |
| TRUCKS (24 HOUR B&C) | 9% | 6% | 5% | 9% |
| TRUCKS (DESIGN HOUR) | 3% | 6% | 5% | 10% |
| NHS PROJECT | No | No | No | No |
| Posted Speed (mph) | 55 | 55 | 55 | 55 |
| Design Speed (mph) | 60 | 60 | 60 | 60 |

Survey:

- ODOT will complete all necessary survey for the project and provide it to the consultant upon authorization to proceed.

Railroads:

Not applicable. There are no railroads within the project limits.

Maintenance of Traffic:

Maintain traffic as follows:

- MOT scheme will depend on the final location of the roundabout.

- At some point, a full closure of both intersections will likely be needed.

  - Coordinate with WCEO, CCEO, Washington Township and Adams Township to develop a detour route for the local roads.  The detour route for US 22 shall use XXXXXXXXXXXX, in both directions.

  - Provide a detour map for each road being closed.

  - Include a window contract to require the closure during the Schools summer break.  The closure duration shall not exceed 60 days.

Geotechnical:

- Follow ODOT’s Specifications for Geotechnical Explorations (SGE) Manual.

- Geotechnical borings will be required for design of this project.

- Draft geotechnical report and soil profile sheets are to be submitted at Stage 1

Drainage:

- WAR US 22 19.24

  - Pipe 13 (1839769)

    - Pipe is rated a 7 (good condition), no need to repair or replace

    - Pipe can be lengthened, but there is damage to the inlet bell/joint so the extension should eliminate that section

    - Build-up in the ditches therefore grading of the ditches or raising (replacement) of the pipe may be needed.

    - Project cost.

  - Pipe 14 (1855157)

    - Pipe rated a 5 (fair condition); some open joints showing signs of possible infiltration. ; very minor cracking;

    - Pipe is 30”, too small to enter and repair joints;

    - Inlet is nearly clogged.

    - Pipe can be lengthened, but the extension should start at the disjointed section.

    - Build-up in the ditches therefore grading of the ditches or raising (replacement) of the pipe may be needed.

    - Project cost.

  - Pipe 15

    - Condition is fine and can be extended.

    - Water is backing up into the pipe from a private pond.

    - Discuss with drainage if this will be a constructability or hydraulic challenge.

    - Project cost.

- CLI US22 2.62

  - Pipe 32 (1881398)

    - Pipe rated a 5 (fair condition); some minor joint separation (no infiltration from photos) warrants possible joint repairs down the road that does not necessarily need to be part of project

    - Pipe is 48” large enough to enter and repair joints.

    - Probably won’t be affected by project, but if project does needing to extend the pipe, may want to consider a CIPP liner.

  - Pipe 33 (not ODOT’s)

    - At least one open/offset joint (last stick leading to outlet), but does not show signs of infiltration; concrete residual leftover near outlet; deteriorating headwall;

    - This pipe appears to be approximately 18”;

    - I would rate a GA of 6 (satisfactory condition)

    - Likely needs extended with the project. If keeping the pipe instead of fully replacing, the pipe needs to be cleaned out and the extension should start at the first disjointed pipe.

    - Project cost.

- The design should ensure that the existing drainage patterns are maintained. It is assumed that catch basins will be needed prior to the roundabout. Attempt to locate storm sewer pipes outside of the roundabout so only a leg would need closed for future replacement.

- Inlet Spacing calculations are required for all proposed runs of curb.

- Storm Sewer Calculations are required for all proposed storm sewer.

- It is assumed that the project would not impact the bridge or the Zone A floodplain

- These project locations are considered non-contiguous, so each intersection would look at the Project EDA separately from the other project. If either project earth disturbed area exceeds 1 acre, then post construction BMPs will be required for the intersection with the Project EDA over 1 acre.  Design for BMPs early as they can impact the project right of way needs.

  - It may be possible to use the 10’ graded shoulder plus 5’ of a 3:1 or flatter ditch foreslope as Vegetated Filter Strip

Structures:

Not anticipating any impacts to bridge SFN 1400061. Discuss with bridge engineer if impacts are unavoidable.

Environmental:

The environmental document for this project is to be completed by the consultant team.

- This project will be a C2 Level CE document.

- ODOT will complete the Section 106-Cultural Resources scoping request form.

- Mitigation site covers the entire northeast corner of the US 22/SR-380/Creek Rd intersection. Land is not allowed to be touched. Might need to negotiate with OEPA/USACE to add replacement land to the mitigation site in exchange for the amount needed for project. Designer to adjust design to avoid this corner if possible.

- See RMR, PI and all other Environmental requirements below.

Pavements:

Use the following pavement composition:

| 1.5” | Item 442 – Asphalt Concrete Surface Course, 12.5mm Type A (446) |
| --- | --- |
|  | Item 407 – Non Tracking Tack Coat |
| 1.75” | Item 442 – Asphalt Concrete Intermediate Course, 12.5mm, Type A (446) |
|  | Item 407 – Non Tracking Tack Coat |
| 6” | Item 301 – Asphalt Concrete Base PG64-22 (449) |
| 6” | Item 304 – Aggregate Base |
| 12” | Subgrade Treatment – Undercut |

For the Concrete aprons

| 9” | Item 452 – Non-Reinforced Concrete Pavement, Class QC1P |
| --- | --- |
| 6” | Item 304 – Aggregate Base |
| 12” | Subgrade Treatment – Undercut |

Public Involvement:

- The consultant team will be required to send property owner notification letters.  ODOT will send project information letters to adjacent property owners and project stakeholders.

- Right of entry notification letters shall be sent by the consultant team prior to beginning survey work for the project.  These letters should be sent to only adjacent property owners.

- Project information letters shall be sent by ODOT after the stage 1 plan review is complete.  These letters should include basic project information, road closure information, detour information, and a link/QR code to the Public Input website.  These letters should be sent to adjacent property owners and project stakeholders (local public agencies, schools, police, EMS, and fire per NEPA and ODOT guidelines).

- Coordinate draft PI materials with ODOT District 8 staff.

- If Authorized Task:

  - The consultant team will develop a static, virtual open house meeting on a Public Input website to inform the public about the project.  The website should focus on the project history, purpose and need, crash history, impacts, and general roundabout and left turn lane information.  There will not be a formal public involvement meeting, so a newspaper advertisement will not be needed.  The Public Input website should be active after the stage 1 plan review is complete.

  - The consultant team shall develop a 1-page plan view graphic to represent the project for use on the website.  This graphic shall be an aerial image with the roundabout and left turn lane designs shaded in, approximate construction limits, proposed R/W limits, street names, addresses of homes, north arrow, scale, etc.

Real Estate:

- Central Office to develop right of way plan sheets.

- At this time, it is expected that 8-10 parcels could be impacted.

Utilities:

- There are multiple underground utilities within the project limits which may be impacted by the project.

- Given the MOT closure duration of 60 days, it will be imperative to have all utilities relocated prior to the beginning of the closure to ensure the roundabout can be constructed on schedule.

- All utility poles on approaches shall be offset behind curb to allow space for agricultural equipment to pass through the intersection.

Consultant to try to avoid utility conflicts throughout design while holding to the scope of work.  If utility conflicts cannot be avoided, they should be minimized.  Consultant to provide a copy of the OUPS ticket information to ODOT PM (if applicable).  Up to date utility contacts shall be used at each plan submission.  Utility contact information can be requested by consultant from ODOT PM.  If OUPS and OGPUPS ticket are more than two (2) years old, a design non-marking ticket shall be requested to obtain most up to date Utility Members List.  The ticket does not need to be submitted to obtain the Utility Members List.

Consultant to provide a utility set of plans with the utility lines shown in color using the most recent version of ODOTcadd_UTPen.tbl at each plan submission.  This file is found in the standard ODOTcadd executable file that can be downloaded from the CADD services webpage.

Consultant to prepare a summary of potential utility conflicts at each plan submission. Summary to be provided to Utility Companies at each plan submission. Summary to include, but not limited to station and offset of conflict, type of conflict (direct, decreased cover, proximity, etc.), utility owner (if known) and utility type.

Consultant to compile Utility Company responses and forward to the ODOT PM. Final compilation of utility correspondence is due 35 days after plan submission to utilities.  A “no response” from a utility on a plan submission review cannot be considered as “no comment”, “no conflicts” and/or “a confirmation of the consultant’s findings” from the utility.  A written response (email is sufficient) must be received from the utility verifying that they have no comments, no conflicts and/or they agree with the conflicts identified by the consultant.

Consultant to review the Utility Company responses and evaluate. The evaluation of the responses shall include validating that a conflict does exist or that a utility may remain in place. If a conflict does exist, consultant should provide an evaluation of the feasibility of potential resolutions.  A disposition of utility status (i.e. utility to stay in place, utility facility relocation plan in writing or plan format) is required at the Stage 3 submission.  This disposition shall be included to the utilities with the Stage 3 plan submission.  This disposition shall be formulated based on utility responses from previous plan submissions.

Project Management:

The project will require submissions for preliminary R/W plans, compliance R/W plans, pre-stage 1 geometrics, stage 1 plans, stage 2 plans, stage 3 plans, and final tracings. All submittals listed will require at least a 30-45 day review timeframe.

The programmatic scope narrative, project initiation package, and other relevant project information has been uploaded to the project FTP site:

Funding:

This project will utilize 100% federal safety funds (4HJ7).

There is 1 plan split for this project:  01/SAF.