LPA SCOPE OF SERVICES FORM

A. Project Identification

| County-Route-Section (Project Name): |  |  | TUS Towpath Trail - Dover |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Sponsor / Maintenance Responsibility: |  |  |  | City of Dover |  |
| ☐ | Local Let |  |  | PID (ODOT assigned): | 124723 |
| ☒ | ODOT Let |  |  |  |  |
| Scope Field Review: |  | October 6, 2025 |  | Scope Meeting: | October 6, 2025 |
| Proposed Sale Date: |  | April 2028 |  | State Fiscal Year: | 2028 |
| Highway Functional Classification: |  |  | 04 – Minor Arterial (Tuscarawas Ave); 07 – Local (Shafer Ave); 05 – Major Collector (Union Ave) |  |  |
| Federal Aid System (ODOT assigned): |  |  | Yes (Enhancement) |  |  |

B. Design Standard

ODOT Location and Design Manuals

C. Project Description

Addition of three (3) segments of the Ohio & Erie Towpath Trail within the city of Dover. Work on each segment will include either widened sidewalk or buffered bike lanes from Canal Dover Park southeast along Tuscarawas Avenue, east along Shafer Avenue, and south along Union Avenue to the Dover/New Philadelphia border as well as high visibility crosswalks, improved signage, and enhanced striping.

| Prior studies / plan (identify): |
| --- |
| Ped/Bike Special Solicitation Short Term Infrastructure Application (December 2024) |  |

| Estimate Project Length: (begin pavement to end pavement including bridge) | 1.3 miles +/- |
| --- | --- |
| Work Length: (including project length & approach work) | 1.3 miles +/- |

| Alignment: | ☒ |  | Existing |  |
| --- | --- | --- | --- | --- |
|  | ☐ |  | Relocated (explain) |  |
| Profile: | ☒ |  | Existing |  |
|  | ☐ |  | New (explain) |  |
| Logical Termini: (w/ explanation) |  | See Certified Cost Estimate and Project Countermeasures Map from Application; Segment 500, Segment 600, and Segment 700 only (Segment 400 is complete) |  |  |

D. Typical Sections

| Existing | Pavement Width: | Varies | ☒ | curb to curb | Graded Shoulder: | Varies |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | ☒ | edge to edge | Treated Shoulder: | Varies |
|  | R/W Width: | Tuscarawas Ave – 60’ +/-; Shafer Ave – 60’ +/-; Union Ave – 80’ +/- |  |  |  |  |
|  | Bridge Width: | N/A | ☐f/f of rails, ☐t/t of curbs, or ☐t/t of parapets |  |  |  |

| Existing | Yes | No | Comment / Type |  |
| --- | --- | --- | --- | --- |
| Median | ☐ | ☒ |  |  |
| Curbs | ☒ | ☐ | Majority of project length, but not all |  |
| Curb ramps | ☒ | ☐ | Not at all required locations, and not all ADA compliant |  |
| Sidewalks | ☒ | ☐ | Width: | Varies |
| Guardrail | ☐ | ☒ |  |  |

Additional Things To Note About Existing Typical Section:

| Proposed | Pavement Width: | Varies | ☒ | curb to curb | Graded Shoulder: | Varies |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | ☒ | edge to edge | Treated Shoulder: | Varies |
|  | R/W Width: | Tuscarawas Ave – 60’ +/-; Shafer Ave – 60’ +/-; Union Ave – 80’ +/- (all work to be within existing R/W) |  |  |  |  |
|  | Bridge Width: | N/A | ☐f/f of rails, ☐t/t of curbs, or ☐t/t of parapets |  |  |  |

| Proposed | Yes | No | Comment / Type |  |
| --- | --- | --- | --- | --- |
| Median | ☐ | ☒ |  |  |
| Curbs | ☒ | ☐ |  |  |
| Curb ramps (*) | ☒ | ☐ | ADA Compliant curb ramps to be added as required |  |
| Sidewalks | ☒ | ☐ | Width: | Varies (per design standards and existing R/W) |
| Guardrail | ☐ | ☒ |  |  |

Note (*) – Curb ramps must be updated to current ADA standards.

| Additional Things To Note About Proposed Typical Section: |
| --- |
| Widened sidewalks preferred along Tuscarawas Ave and Shafer Ave; buffered bike lanes recommended on Union Ave |  |

Supplemental Information: Tuscarawas Ave/Union Ave (Shafer Unknown – assume low volume)

| ADT (2028) |  | 6500/3600 |  | Design ADT (2040) | 6900/3800 |
| --- | --- | --- | --- | --- | --- |
| DHV (2040) |  | 690/418 |  | Certified Traffic | N/A |
| T24 |  | 8% |  | Legal Speed | 25 MPH-35 MPH |
| Design Speed |  | 25 MPH-35 MPH |  |
| Comments: |
| Opening Year – 2028; Design Year - 2040 |  |  |  |  |  |

E. Right-of-Way

|  |  | Yes | No | Remarks |
| --- | --- | --- | --- | --- |
| Right-of-Way Plan: |  | ☐ | ☒ |  |
| Approximate Number of Parcels: |  |  |  | 0 |
| Known Relocations: |  | ☐ | ☒ |  |
| Railroad Involvement: |  | ☒ | ☐ | Yes, one crossing along Tuscarawas Ave segment. |
| Railroad Name: |  |  |  | R.J. Corman Railroad Group |
| Encroachments: |  | ☐ | ☒ | To be verified by City/Consultant |
| Airway Highway Clearance: |  | ☐ | ☒ | Required equipment will not exceed height of existing trees. |
| Airport Name: |  |  |  |  |
| Comments: |  |  |  |  |

Note: Provide a footprint of proposed and existing right of way limits as soon as available to the District Environmental Coordinator and District Real Estate Administrator.

Caution: Environmental needs to be clear prior to the beginning of right of way acquisition.

F. Utilities

|  |  |  | Yes | No | Name of Company |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Aerial | Phone |  | ☒ | ☐ | Frontier |  |  |
|  | Cablevision |  | ☒ | ☐ | Spectrum, OmniFiber, Frontier |  |  |
|  | Power |  | ☒ | ☐ | City of Dover |  |  |
| Underground | Phone |  | ☒ | ☐ | Frontier |  |  |
|  | Cablevision |  | ☒ | ☐ | Spectrum, OmniFiber, Frontier |  |  |
|  | Power |  | ☒ | ☐ | City of Dover |  |  |
|  | Gas |  | ☒ | ☐ | Enbridge |  |  |
|  | Pipelines: |  | ☒ | ☐ |  |  |  |
|  |  |  |  |  | Private | Public | Name of Company |
|  | Water |  | ☒ | ☐ | ☐ | ☐ | City of Dover |
|  | Sanitary |  | ☒ | ☐ | ☐ | ☐ | City of Dover |
|  | Storm |  | ☒ | ☐ | ☐ | ☐ | City of Dover |
| Other: |  |  |  |  |  |  |  |
| Comments: |  |  |  |  |  |  |  |

G. Structure Requirements – N/A

| Existing Structure Information: | Structure type: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Bridge No.: |  |  | Structural File No.: |  |  |
|  | Sufficiency Rating: |  |  | General Appraisal: |  |  |
|  | Crossing: |  |  |  |  |  |
|  | Bridge Length: |  |  | Number of Spans: |  |  |
|  | Eligible for the National Historical Register: |  | ☐ Yes ☐ No |  |  |  |

| Proposed Structure Information: | New Structure: | ☐ Yes ☐ No |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rehabilitate Existing Bridge by: |  |  |  |  |  |  |
|  | Structure Type: |  |  |  |  |  |  |
|  | Beam Type: |  | ☐ Concrete Box; ☐ Steel; ☐ n/a |  |  |  |  |
|  | Structure Width: |  |  |  |  | Number of Spans: |  |
|  | Local must have proposed structure’s load rating on file Other Design Considerations / Explanation of Change in Line/Grade: |  |  |  |  |  |  |
|  | Guardrail Type: |  |  |  |  |  |  |

H. Design Exception(s) Required

| ☐ Yes | Explain: | Low Speed Roadways |
| --- | --- | --- |
| ☒ No |  |  |

I. Traffic Control

|  | Yes | No | Remarks |
| --- | --- | --- | --- |
| Signing: | ☒ | ☐ | See Certified Cost Estimate and Project Countermeasures Map from Application |
| Striping: | ☒ | ☐ | See Certified Cost Estimate and Project Countermeasures Map from Application |
| Lighting: | ☐ | ☒ |  |
| Signals: | ☐ | ☒ |  |
| RPMs: | ☐ | ☒ |  |

J. Maintenance of Traffic

| Type of MOT: | ☐ Detour, ☒ Part Width, ☒ Daily Flagging |  |  |
| --- | --- | --- | --- |
| Remarks/Describe: |  |  |  |
| Will Pedestrian Traffic need to be maintained? |  |  | Yes, in segments with existing sidewalk pedestrian detours will be required. |
| Remarks/Describe: |  |  |  |

K. Driveways

| ☒ Yes | Type: | Commercial and residential drives of various types |
| --- | --- | --- |
| ☐ No |  |  |

L. Project Funding

| Project Cost Estimate: | $2,133,973.50 |  |  |
| --- | --- | --- | --- |
| Quantity splits needed in plans to differentiate funding participation: |  | ☐ Yes ☒ No | Comments: |
| Coordination with Concurrent Projects Required: |  | ☒ Yes ☐ No | Comments: TUS Towpath Trail – New Phila (PID 124728) |

Funding Source: TAP (4B37) & Safety (4HJ7)	Federal Maximum: $2,150,000 	Funding Split: 100% (80/20)

Cost Estimates:

|  | Local Information |  |  | Federal Information |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | SAC | Total Local Funds | Percent Split | SAC | Total Federal Funds | Percent Split |  |
| Preliminary Engineering |  |  |  | 4B37/4HJ7 | $160,000 | 100 | $160,000 |
| Detailed Design |  |  |  | 4B37/4HJ7 | $40,000 | 100 | $40,000 |
| Construction |  |  |  | 4B37/4HJ7 | $1,807,451.87 | 100 | $1,807,451.87 |
| Construction Engineering |  |  |  | 4B37/4HJ7 | $126,521.63 | 100 | $126,521.63 |
| Totals: |  |  |  |  | $2,133,973.50 |  | $2,133,973.50 |

| Additional remarks about funding: |
| --- |
| Utilizing 100% Federal funds (80% TAP-4B37 matched with 20% Safety-4HJ7) up to Federal max. |  |

M. Cost Recovery Does the LPA intend to recover any Direct Labor Costs associated with this project?; ☐ Yes; ☒ No. Does the LPA intend to recover any Fringe and Overhead Costs associated with this project?; ☐ Yes; ☒ No. If the LPA does intend to recover Fringe and Overhead Costs, by what method do they intend to recover those costs? ☐ 1. Direct Labor only (no indirect cost recovery for fringe benefit or overhead costs) ☐ 2. Direct Labor plus indirect costs determined using the Federal De Minimis Indirect Cost Rate ☐ 3. Direct Labor plus Approved Fringe Benefit Costs (fringe benefits only) ☐ 4. Direct Labor plus indirect costs determined using the approved applicable Cost Allocation Plan rate ☐ 5. No cost recovery of any LPA direct labor, fringe benefits, or overhead costs.. Does the LPA currently have a timekeeping system in place?; ☐ Yes; ☐ No. If so, does that system track both payroll and project hours concurrently?; ☐ Yes; ☐ No. If different systems, how does the LPA reconcile project hours to payroll?. How often are payroll records prepared?. For employees working on multiple activities, does the LPA track daily time by activity/project on the time sheets? (Tracking hours worked, without activities, on Federal projects is non-compliant. All activity hours must be shown); ☐ Yes; ☐ No. Does the LPA ensure that timecards are signed by the employee?; ☐ Yes; ☐ No.

N. Environmental – see Environmental (NEPA) Scope of Services

O. Roles/Responsibilities

Note: Consultants used for development of Construction plans, R/W plans, R/W acquisition/appraisals, and Construction inspection must be pre-qualified by ODOT.

| Construction Plan Development: | ODOT Prequalified Consultant |
| --- | --- |
| Proposal/Specification Development: | ODOT |
| LPA Agreement: | ODOT/LPA |
| Form and Preliminary Legislation: | ODOT/LPA |
| Environmental Tasks: | ODOT Prequalified Consultant/ODOT (see Environmental SOS) |
| Advertising and Award of Contract: | ODOT |
| Construction Inspection: | ODOT |
| R/W Plan Development: | N/A |
| R/W Acquisition / Appraisals: | N/A |
| Utility Relocation: | Coordination and relocation by LPA/ODOT Prequalified Consultant (responsible for completion of the Utility Note for any relocations) |

P. Field Review – held with ODOT D11 and City of Dover personnel on October 6, 2025

Q. Commitment Dates